## Tasks by Client
RDS Project Hub — Task Report (2026-05-22)
CLIENT: Formcrete ¦ 8 Project(s) ¦ Tasks 227
# | Task | Project | Status | Priority | Assignee | Due Date
▸ 2460 Australian (Ocean Tower) (26 tasks, deadline: 2026-06-17)
1 | STEEL COLUMNS | Australian Ave | Done | High | Sai | 2026-02-09
2 | PILE CAPS | Australian Ave | Done | High | Sridevi | 2026-04-13
3 | GRADE BEAMS | Australian Ave | Done | High | Dhanush | 2026-04-13
4 | SLAB ON GRADE | Australian Ave | Done | High | Balaram | 2026-04-20
5 | LIFT -1 VERTICALS CMU & COLUMS | Australian Ave | Done | High | Dhanush | 2026-04-24
6 | TUNNEL WALLS | Australian Ave | Done | High | Balaram | 2026-04-24
7 | 2ND FLR. SLAB & BEAMS | Australian Ave | Done | High | Balaram | 2026-04-27
8 | LIFT -2 VERTICALS CMU & COLUMS | Australian Ave | Done | High | Dhanush | 2026-04-30
9 | RETAIINING WALL | Australian Ave | Done | High | Dhanush | 2026-04-30
10 | 3RD FLR. SLAB & BEAMS | Australian Ave | Done | High | Dhanush | 2026-05-04
11 | LIFT -3 VERTICALS CMU & COLUMS | Australian Ave | Done | High | Dhanush | 2026-05-05
12 | 4TH FLR. SLAB & BEAMS | Australian Ave | In Progress | Medium | Dhanush | 2026-05-26
13 | LIFT -4 VERTICALS CMU & COLUMS | Australian Ave | In Progress | Medium | Dhanush | 2026-05-26
14 | 5TH FLR. SLAB & BEAMS | Australian Ave | To Do | Medium | Dhanush | 2026-05-26
15 | LIFT -5 VERTICALS CMU & COLUMS | Australian Ave | To Do | Medium | Dhanush | 2026-05-26
16 | 6TH FLR. SLAB & BEAMS | Australian Ave | To Do | Medium | Dhanush | 2026-05-26
17 | LIFT -6 VERTICALS CMU & COLUMS | Australian Ave | To Do | Medium | Dhanush | 2026-06-17
18 | 7TH FLR. SLAB & BEAMS | Australian Ave | To Do | Medium | Dhanush | 2026-06-17
19 | LIFT -7 VERTICALS CMU & COLUMS | Australian Ave | To Do | Medium | Dhanush | 2026-06-17
20 | 8TH FLR. SLAB & BEAMS | Australian Ave | To Do | Medium | Dhanush | 2026-06-17
21 | LIFT -8 VERTICALS CMU & COLUMS | Australian Ave | To Do | Medium | Dhanush | 2026-06-17
22 | ROOF SLAB & BEAMS WITH PARAPET | Australian Ave | To Do | Medium | Dhanush | 2026-06-17
23 | Submittal 13- Ground Floor Slab (EOR) | Australian Ave | To Do | Medium | Dhanush | 2026-06-17
24 | Submittal 10- Steel Column Shop Drawings (EOR) | Australian Ave | Done | Medium | Sai | 2026-05-04
25 | Pour separation (EOR) | Australian Ave | To Do | Medium | Dhanush | 2026-06-17
26 | Lift-1 Column modifcation per RFI 057 and (EOR) | Australian Ave | In Progress | High | Dhanush | 2026-05-22
▸ Modera Boca Raton (17 tasks, , deadline: 2026-06-19)
1 | GROUND LEVEL TO 2ND LEVEL TC & CMU WALLS | Modera Boca Raton | Done | High | Balaram & Swathi | 2026-05-26
2 | 2ND LEVEL TO 3RD LEVEL TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
3 | 3RD LEVEL TO 4TH LEVEL TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
4 | 4TH LEVEL TO 5TH LEVEL TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
5 | 5TH LEVEL TO 6TH LEVEL TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
6 | 6TH LEVEL TO 7TH LEVEL TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
7 | 7TH LEVEL TO 8TH LEVEL TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
8 | 8TH LEVEL TO 9TH LEVEL TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
9 | 9TH LEVEL TO 10TH LEVEL TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
10 | 10TH LEVEL TO 11TH LEVEL TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
11 | 11TH LEVEL TO 12TH LEVEL TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
12 | 12TH LEVEL TO 12TH MEZZ LEVEL TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
13 | 12TH MEZZ LEVEL TO ROOF LEVEL TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
14 | ROOF LEVEL TO HIGH ROOF TC & CMU WALLS | Modera Boca Raton | To Do | High | Balaram | 2026-06-19
15 | Ground Level Slab FFU drawings and bar lists. RFI #79(EOR) | Modera Boca Raton | Done | High | Nanaji | 2026-05-04
16 | Revision per RFI #50, #67, #78 responses (EOR) | Modera Boca Raton | Done | High | Nanaji | 2026-05-08
17 | Pet Wash details addition (EOR) | Modera Boca Raton | Done | High | Nanaji | 2026-05-12
▸ 4541-Gables Cypress Creek (44 Task , deadline: 2026-07-13)
1 | BUILDING TYPE-I LIFT-1 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-05
2 | BUILDING TYPE-I 2ND FLR. SLAB & BEAMS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-12
3 | BUILDING TYPE-I LIFT-2 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-19
4 | BUILDING TYPE-I 3rd FLR. SLAB & BEAMS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-19
5 | BUILDING TYPE-I LIFT-3 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-19
6 | BUILDING TYPE-I 4th FLR. SLAB & BEAMS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-19
7 | BUILDING TYPE-I LIFT-4 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-19
8 | BUILDING TYPE-I 5th FLR. SLAB & BEAMS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-19
9 | BUILDING TYPE-I LIFT-5 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-19
10 | BUILDING TYPE-I ROOF SLAB & BEAMS WITH PARAPET | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-26
11 | BUILDING TYPE-II TUNNEL WALLS | 4541-Gables Cypress Creek | To Do | High | Mouli | 2026-05-29
12 | BUILDING TYPE-II LIFT-1 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-26
13 | BUILDING TYPE-II 2ND FLR. SLAB & BEAMS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-26
14 | BUILDING TYPE-II LIFT-2 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-06
15 | BUILDING TYPE-II 3rd FLR. SLAB & BEAMS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-06
16 | BUILDING TYPE-II LIFT-3 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-06
17 | BUILDING TYPE-II 4th FLR. SLAB & BEAMS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-06
18 | BUILDING TYPE-II LIFT-4 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-06
19 | BUILDING TYPE-II 5th FLR. SLAB & BEAMS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-06
20 | BUILDING TYPE-II LIFT-5 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-06
21 | BUILDING TYPE-II ROOF SLAB & BEAMS WITH PARAPET | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-06
22 | BUILDING TYPE-III LIFT-2 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-06
23 | BUILDING TYPE-III 3rd FLR. SLAB & BEAMS | 4541-Gables Cypress Creek | Done | High | Trisha | 2026-05-18
24 | BUILDING TYPE-III LIFT-3 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
25 | BUILDING TYPE-III 4th FLR. SLAB & BEAMS | 4541-Gables Cypress Creek | Done | Medium | Trisha | 2026-05-18
26 | BUILDING TYPE-III LIFT-4 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
27 | BUILDING TYPE-III 5th FLR. SLAB & BEAMS | 4541-Gables Cypress Creek | Done | Medium | Trisha | 2026-05-18
28 | BUILDING TYPE-III LIFT-5 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
29 | BUILDING TYPE-III ROOF SLAB & BEAMS WITH PARAPET | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
30 | BUILDING TYPE-IV LIFT-2 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
31 | BUILDING TYPE-IV LIFT-3 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
32 | BUILDING TYPE-IV LIFT-4 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
33 | BUILDING TYPE-IV 5th FLR. SLAB & BEAMS | 4541-Gables Cypress Creek | Done | Medium | Trisha | 2026-05-04
34 | BUILDING TYPE-IV LIFT-5 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
35 | BUILDING TYPE-IV ROOF SLAB & BEAMS WITH PARAPET | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
36 | BUILDING TYPE-V LIFT-1 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
37 | BUILDING TYPE-V LIFT-2 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
38 | BUILDING TYPE-V LIFT-3 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
39 | BUILDING TYPE-V LIFT-4 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
40 | BUILDING TYPE-V LIFT-5 VERTICALS | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
41 | Bldg. Type IV - Level-2 (EOR) | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-07-13
42 | Building Type V - Floor slabs Pour separtions(EOR) | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-06-05
43 | Building Type IV - Floor slabs Pour separtions(EOR) | 4541-Gables Cypress Creek | To Do | Medium | Trisha | 2026-05-28
44 | Building Type III - Floor slabs Pour separtions(EOR) | 4541-Gables Cypress Creek | In Progress ⚠ | High | Trisha | 2026-05-25
▸ NOMI-6 ( 27 Tasks , deadline: 2026-06-17)
1 | LIFT-6 & 7 SHEAR WALLS | NOMI-6 | Completed | High | Sai | 2026-05-04
2 | 8th FLOOR SLAB & BEAMS | NOMI-6 | Completed | Medium | Sai | 2026-05-09
3 | 9th FLOOR SLAB & BEAMS | NOMI-6 | Completed | Medium | Sai | 2026-05-09
4 | 10th FLOOR SLAB & BEAMS | NOMI-6 | Completed | Medium | Sai | 2026-05-28
5 | 11th FLOOR SLAB & BEAMS | NOMI-6 | Completed | Medium | Sai | 2026-06-18
6 | ROOF FLOOR SLAB & BEAMS | NOMI-6 | In Progress ⚠ | Medium | Sai | 2026-06-25
7 | LIFT-9 & 10 COLUMNS | NOMI-6 | Completed | Medium | Sai | 2026-06-15
8 | LIFT-8 & 9 SHEAR WALLS | NOMI-6 | Completed | Medium | Sai | 2026-06-02
9 | LIFT-11 COLUMNS | NOMI-6 | Completed | Medium | Sai | 2026-06-15
10 | LIFT-10 & 11 SHEAR WALLS | NOMI-6 | Completed | Medium | Sai | 2026-06-17
11 | STAIRS (LEVEL-6 TO LEVEL-8) | NOMI-6 | Completed | Medium | Sai | 2026-06-05
12 | STAIRS (LEVEL-8 TO LEVEL-10) | NOMI-6 | Completed | Medium | Sai | 2026-06-05
13 | STAIRS (LEVEL-10 TO LEVEL-ROOF) | NOMI-6 | Completed | Medium | Sai | 2026-06-05
25 | lvl-5 barlists & lvl-4 release separation (ERO) | NOMI-6 | Completed | High | Sai | 2026-05-18
26 | Missing rebar for slab transitions on pool deck slab (ERO) | NOMI-6 | Completed | High | Sai | 2026-05-18
27 | grade 80 grade 60 bars (ERO) | NOMI-6 | Completed | Medium | Sai | 2026-05-20
▸ Magnolia Point (69 Tasks , deadline: 2026-)
1 | BLDG 1 | Magnolia Point | To Do | Medium | TBD
2 | BLDG 2 | Magnolia Point | To Do | Medium | TBD
3 | BLDG 3 | Magnolia Point | To Do | Medium | TBD
4 | BLDG 4 | Magnolia Point | To Do | Medium | TBD
5 | BLDG 5 | Magnolia Point | To Do | Medium | TBD
6 | Clubhouse | Magnolia Point | To Do | Medium | TBD
7 | BLDG 1 - Foundations & SOG | Magnolia Point | To Do | Medium | TBD
8 | BLDG 1 - 2nd floor slab | Magnolia Point | To Do | Medium | TBD
9 | BLDG 1 - 3rd floor slab | Magnolia Point | To Do | Medium | TBD
10 | BLDG 1 - 4th floor slab | Magnolia Point | To Do | Medium | TBD
11 | BLDG 1 - 5th floor slab | Magnolia Point | To Do | Medium | TBD
12 | BLDG 1 - 6th floor slab | Magnolia Point | To Do | Medium | TBD
13 | BLDG 1 - Roof level slab | Magnolia Point | To Do | Medium | TBD
14 | BLDG 1 - Lift-1 verticals | Magnolia Point | To Do | Medium | TBD
15 | BLDG 1 - Lift-2 verticals | Magnolia Point | To Do | Medium | TBD
16 | BLDG 1 - Lift-3 verticals | Magnolia Point | To Do | Medium | TBD
17 | BLDG 1 - Lift-4 verticals | Magnolia Point | To Do | Medium | TBD
18 | BLDG 1 - Lift-5 verticals | Magnolia Point | To Do | Medium | TBD
19 | BLDG 1 - Lift-6 & parapet verticals | Magnolia Point | To Do | Medium | TBD
20 | BLDG 2 - Foundations & SOG | Magnolia Point | To Do | Medium | TBD
21 | BLDG 2 - 2nd floor slab | Magnolia Point | To Do | Medium | TBD
22 | BLDG 2 - 3rd floor slab | Magnolia Point | To Do | Medium | TBD
23 | BLDG 2 - 4th floor slab | Magnolia Point | To Do | Medium | TBD
24 | BLDG 2 - 5th floor slab | Magnolia Point | To Do | Medium | TBD
25 | BLDG 2 - 6th floor slab | Magnolia Point | To Do | Medium | TBD
26 | BLDG 2 - Roof level slab | Magnolia Point | To Do | Medium | TBD
27 | BLDG 2 - Lift-1 verticals | Magnolia Point | To Do | Medium | TBD
28 | BLDG 2 - Lift-2 verticals | Magnolia Point | To Do | Medium | TBD
29 | BLDG 2 - Lift-3 verticals | Magnolia Point | To Do | Medium | TBD
30 | BLDG 2 - Lift-4 verticals | Magnolia Point | To Do | Medium | TBD
31 | BLDG 2 - Lift-5 verticals | Magnolia Point | To Do | Medium | TBD
32 | BLDG 2 - Lift-6 & parapet verticals | Magnolia Point | To Do | Medium | TBD
33 | BLDG 3 - Foundations & SOG | Magnolia Point | To Do | Medium | TBD
34 | BLDG 3 - 2nd floor slab | Magnolia Point | To Do | Medium | TBD
35 | BLDG 3 - 3rd floor slab | Magnolia Point | To Do | Medium | TBD
36 | BLDG 3 - 4th floor slab | Magnolia Point | To Do | Medium | TBD
37 | BLDG 3 - 5th floor slab | Magnolia Point | To Do | Medium | TBD
38 | BLDG 3 - 6th floor slab | Magnolia Point | To Do | Medium | TBD
39 | BLDG 3 - Roof level slab | Magnolia Point | To Do | Medium | TBD
40 | BLDG 3 - Lift-1 verticals | Magnolia Point | To Do | Medium | TBD
41 | BLDG 3 - Lift-2 verticals | Magnolia Point | To Do | Medium | TBD
42 | BLDG 3 - Lift-3 verticals | Magnolia Point | To Do | Medium | TBD
43 | BLDG 3 - Lift-4 verticals | Magnolia Point | To Do | Medium | TBD
44 | BLDG 3 - Lift-5 verticals | Magnolia Point | To Do | Medium | TBD
45 | BLDG 3 - Lift-6 & parapet verticals | Magnolia Point | To Do | Medium | TBD
46 | BLDG 4 - Foundations & SOG | Magnolia Point | To Do | Medium | TBD
47 | BLDG 4 - 2nd floor slab | Magnolia Point | To Do | Medium | TBD
48 | BLDG 4 - 3rd floor slab | Magnolia Point | To Do | Medium | TBD
49 | BLDG 4 - 4th floor slab | Magnolia Point | To Do | Medium | TBD
50 | BLDG 4 - 5th floor slab | Magnolia Point | To Do | Medium | TBD
51 | BLDG 4 - Roof level slab | Magnolia Point | To Do | Medium | TBD
52 | BLDG 4 - Lift-1 verticals | Magnolia Point | To Do | Medium | TBD
53 | BLDG 4 - Lift-2 verticals | Magnolia Point | To Do | Medium | TBD
54 | BLDG 4 - Lift-3 verticals | Magnolia Point | To Do | Medium | TBD
55 | BLDG 4 - Lift-4 verticals | Magnolia Point | To Do | Medium | TBD
56 | BLDG 4 - Lift-5 & parapet verticals | Magnolia Point | To Do | Medium | TBD
57 | BLDG 4 - Foundations & SOG | Magnolia Point | To Do | Medium | TBD
58 | BLDG 4 - 2nd floor slab | Magnolia Point | To Do | Medium | TBD
59 | BLDG 4 - 3rd floor slab | Magnolia Point | To Do | Medium | TBD
60 | BLDG 4 - Roof level slab | Magnolia Point | To Do | Medium | TBD
61 | BLDG 4 - Lift-1 verticals | Magnolia Point | To Do | Medium | TBD
62 | BLDG 4 - Lift-2 verticals | Magnolia Point | To Do | Medium | TBD
63 | BLDG 4 - Lift-3 & parapet verticals | Magnolia Point | To Do | Medium | TBD
64 | Clubhouse - Foundations & SOG | Magnolia Point | To Do | Medium | TBD
65 | Clubhouse - Lift-1 verticals | Magnolia Point | To Do | Medium | TBD
66 | Clubhouse - Roof slab | Magnolia Point | To Do | Medium | TBD
67 | Clubhouse - Parapet & Trellis slab | Magnolia Point | To Do | Medium | TBD
68 | Trash enclosure | Magnolia Point | To Do | Medium | TBD
69 | Steel columns shop drawings (all bldgs) | Magnolia Point | In Progress | High | Tekla team | 2026-05-26
▸ Hilltop Gardens ( 7 Tasks , deadline: 2026-05-27)
1 | Building _1 Type III (Steel Columns shops only) | Hilltop Gardens | In Progress | Medium | Tekla team | 2026-05-27
2 | Building _2 Type II (Steel Columns shops only) | Hilltop Gardens | In Progress | Medium | Tekla team | 2026-05-27
3 | Building _3 Type II (Steel Columns shops only) | Hilltop Gardens | In Progress | Medium | Tekla team | 2026-05-27
4 | Building _4 Type I (Steel Columns shops only) | Hilltop Gardens | In Progress | Medium | Tekla team | 2026-05-27
5 | Building _5 Type I (Steel Columns shops only) | Hilltop Gardens | In Progress | Medium | Tekla team | 2026-05-27
6 | Building _6 Type I (Steel Columns shops only) | Hilltop Gardens | In Progress | Medium | Tekla team | 2026-05-27
7 | Clubhouse (Steel Columns shops only) | Hilltop Gardens | In Progress | Medium | Tekla team | 2026-05-27
▸ Altis Delray ( 5 Tasks , deadline: 2026-05-28)
1 | Building Type I (Steel Columns shops only) | Altis Delray | In Progress | Medium | Tekla team | 2026-05-28
2 | Building Type II (Steel Columns shops only) | Altis Delray | In Progress | Medium | Tekla team | 2026-05-28
3 | Building Type IIM (Steel Columns shops only) | Altis Delray | In Progress | Medium | Tekla team | 2026-05-28
4 | Building Type III (Steel Columns shops only) | Altis Delray | In Progress | Medium | Tekla team | 2026-05-28
5 | Clubhouse (Steel Columns shops only) | Altis Delray | In Progress | Medium | Tekla team | 2026-05-28
▸ Octavia (33 Tasks , deadline: 2026)
1 | Steel columns | Octavia | Done | High | Tekla team | 2026-05-21
2 | Sector-A Foundations - Deep ftgs | Octavia | In Progress | High | Mouli | 2026-05-29
3 | Sector-A Foundations - Pad ftgs | Octavia | To Do | Medium
4 | Sector-A Foundations - Cont ftgs | Octavia | To Do | Medium
5 | Sector-B Foundations - Deep ftgs | Octavia | To Do | Medium
6 | Sector-B Foundations - Pad ftgs | Octavia | To Do | Medium
7 | Sector-B Foundations - Cont ftgs | Octavia | To Do | Medium
8 | Sector-A Slab on grade | Octavia | To Do | Medium
9 | Sector-B Slab on grade | Octavia | To Do | Medium
10 | Sector-A Shear walls | Octavia | To Do | Medium
11 | Sector-B Shear walls | Octavia | To Do | Medium
12 | Sector-A Columns | Octavia | To Do | Medium
13 | Sector-B Columns | Octavia | To Do | Medium
14 | Sector-A Stairs | Octavia | To Do | Medium
15 | Sector-B Stairs | Octavia | To Do | Medium
16 | Sector-A Level-1.5 slab & beams | Octavia | To Do | Medium
17 | Sector-A 2nd floor slab & beams | Octavia | To Do | Medium
18 | Sector-B 2nd floor slab & beams | Octavia | To Do | Medium
19 | Sector-A 3rd floor slab & beams | Octavia | To Do | Medium
20 | Sector-B 3rd floor slab & beams | Octavia | To Do | Medium
21 | Sector-A 4th floor slab & beams | Octavia | To Do | Medium
22 | Sector-B 4th floor slab & beams | Octavia | To Do | Medium
23 | Sector-A 5th floor slab & beams | Octavia | To Do | Medium
24 | Sector-B 5th floor slab & beams | Octavia | To Do | Medium
25 | Sector-A 6th floor slab & beams | Octavia | To Do | Medium
26 | Sector-B 6th floor slab & beams | Octavia | To Do | Medium
27 | Sector-A 7th floor slab & beams | Octavia | To Do | Medium
28 | Sector-B 7th floor slab & beams | Octavia | To Do | Medium
29 | Sector-A 8th floor slab & beams | Octavia | To Do | Medium
30 | Sector-B 8th floor slab & beams | Octavia | To Do | Medium
31 | Sector-A Roof floor slab & beams | Octavia | To Do | Medium
32 | Sector-B Roof floor slab & beams | Octavia | To Do | Medium
33 | Upper roof slab & beams | Octavia | To Do | Medium
▸ Adella 2 (5 Tasks , deadline: 06/13/2026)
1 | Level-2 & 3 slabs | Adella | Completed | High | Sai | 2026-06-02
2 | Level-4 slab | Adella | Completed | High | Sai | 2026-06-09
3 | Level-5 slab | Adella | Completed | Medium | Sai | 2026-06-13
4 | Level-6 slab | Adella | Completed | Medium | Sai | 2026-06-13
5 | Roof slab | Adella | Completed | Medium | Sai | 2026-06-13