## May 1st Week
Rebar Department Weekly Project Status Report-April 2026
Date Range |  | 05/04/2026 to 05/09/2026
Projects & Actives for Above dates
S.no | Client | Project name | Description | Tonnage | Hours | Status | Remarks |  | Detaielrs
1
2
3
4
5
Total |  |  |  | 0 | 0 |  |  | 0
Projects & Actives Planned to This week
Total |  |  |  | 0 | 0 |  |  | 0
Work in hand
1 |  | 143 Reef Road | Lift - 1 Verticals
Lift - 1 Beams & 2nd floor slab
Roof beams
2 |  | 6017 Le Lac Road (Weiner Residence) | Lift - 2 Verticals and roof beams (Main Building)
Lift - 1 Verticals, 2nd floor slab and beams (2-story residence)
Lift - 2 Verticals and roof beams (2-story residence)
3 |  | 164 Seminole | Slab on grade | [5 empty] | Siva Kumar
|  |  | Lift - 1 Verticals, 2nd floor slab and beams | [5 empty] | Siva Kumar
|  |  | Lift - 2 Verticals and roof beams | [5 empty] | Siva Kumar
4 |  | Roy & Shelley Silverman | Lift - 1 Beams | [5 empty] | Nanaji
|  |  | Lift - 2 Verticals & Roof beams | [5 empty] | Sridivi/Nanaji
5 |  | Valencia Del Mar Clubhouse | Lift - 1 Verticals and beams
Lift - 2 Verticals and beams
6 |  | Burns Residence | Lift - 1 Verticals and Beams
Lift - 2 Verticals and beams
7 |  | 320 S atlantic Drive | Lift - 1 Verticals, 2nd Floor slab & beams
Lift - 2 Verticals and Roof beams
8 |  | Custom Residence (515 lido drive) | Lift - 1 Verticals, 2nd floor slab & beams
Lift - 2 Verticals & Roof beams
9 |  | Jandrews Residence | Lift - 1 Verticals and beams
Lift - 2 Verticals and beams
10 |  | 5900 Powerline Garage | Lift - 1 Verticals and Roof beams | [5 empty] | Pradeep
11 |  | South Florida Jewish Cemetery | Foundations and slab on grade | [5 empty] | Vaishnavi
Lift - 1 Verticals and Roof Beams
12 |  | 20 Hudson Ave | Foundations & slab on grade
Lift - 1 Verticals and Beams
Lift - 2 Verticals and Beams
13 |  | Baig Residence | 3rd Floor tie beams
14 |  | SW Ranches | Lower Roof Deck
Total |  |  |  | 0 | 60 |  |  | 60
Bar listing & FFU drawings. (Non billable work)
1
2
3
3
4
5
6
7
Total |  |  |  | 0 | 0
Frist Week Weight+hours |  | Second week Weight + hours | Third week weight+hours | Fourth week Weight + hours |  |  | Total
0 |  | 0 | 0 | 0 |  |  | 0
Rebar @ Structural Steel
S.No | Engineers |  | Leaves | Permissions | Over Time | Remarks
1 | Eswar | Project management
2 | Nanaji | Rebar Detailing/QC
3 | Y Siva kumar | Estimations and rebar detailing
4 | Lokesh reddy | Rebar Detailing
5 | Sridevi | Rebar Detailing
6 | Vaishnavi | Rebar Detailing
7 | Pradeep | Rebar Detailing

## White Cap Work Schedule
White Cap
PROJECT NAME | COMPONENTS OF WORK | STATUS | CLIENT SUB. DATE | DET. WT. | DETAILER | CHECKER
Felies Residence | Foundations and slab on grade | Completed | 2026-12-01 | 2.8 | Praveena | Chandra Mouli
| Lift - 1 Verticals & beams, 2nd floor slab & beams | Completed | 01-29-2026 | 6.354 | Praveena | Anji Reddy
| Lift - 2 verticals & beams, Roof slab & beams | Completed | 2026-06-02 | 3.835 | Praveena | Anji Reddy
Valencia Del Mar Pickleball | Foundations and slab on grade | Completed | 01-19-2026 | 6.057 | Danush | Kameshwari
| Lift - 1 Verticals & beams | Completed | 01-23-2026 | 8.112 | Danush | Kameshwari
| Lift - 2 Verticals & beams | Completed | 01-23-2026 | 4.434 | Danush | Kameshwari
| Double Dumpster Enclosure | Completed | 02-18-2026 | 0.251 | Praveena | Kameshwari
| Single Dumpster Enclosure | Completed | 02-18-2026 | 0.197 | Praveena | Kameshwari
| Mail Pavilion | Completed | 02-18-2026 | 1.661 | Praveena | Kameshwari
| Monument sign | Completed | 2026-01-06 | 0.131 | Pradeep | Nanaji
City of temple terrace-fire station #01 | Foundations | Completed | 01-19-2026 | 13.923 | Swathi | Chandra Mouli
| Slab on grade | Completed | 02-14-2026 | 0.516 | Sri Lalitha | Kameshwari
| Lift - 1 Verticals, 2nd floor slab & beams | Completed | 02-25-2026 | 9.701 | Sri Lalitha | Kameshwari
| Lift - 2 Verticals and Roof beams | Completed | 02-25-2026 | 9.489 | Sri Lalitha | Kameshwari
228 Rutland | Foundations and slab on grade | Completed | 01-13-2026 | 2.598 | Allu Sai | Kameshwari
| Lift - 1 Verticals and Bond beams | Completed | 2026-03-02 | 2.152 | Allu Sai | Kameshwari
| Low Roof beams & Slab | Completed | 02-19-2026 | 2.587 | Vaishnavi | Kameshwari
| Lift - 2 Verticals, Bond beams & Roof beams | Completed | 2026-02-03 | 1.643 | Siva Kumar | Kameshwari
Palmetto Lakes Industrial Park | Foundations and slab on grade | Completed | 01-14-26 | 5.041 | Sri Lalitha | Chandra Mouli
| Lift - 1 walls, Columns & Beams | Completed | 01-27-26 | 6.914 | Sri Lalitha | Chandra Mouli
| Lift - 2 walls, Columns & Beams | Completed | 01-27-26 | 6.722 | Sri Lalitha | Chandra Mouli
Frenchman's Creek Operations Center | Building - A Foundations & slab on grade | Completed | 01-26-2026 | 16.64 | Pradeep | Anji Reddy
| Building - B Foundations & slab on grade | Completed | 01-21-2026 | 5.301 | Pradeep | Narayana
| Building - C Foundations & slab on grade | Completed | 01-21-2026 | 17.953 | Praveena | Anji Reddy
| Building - D Foundations & slab on grade | Completed | 01-26-2026 | 0.675 | Pradeep | Anji Reddy
| Building - E Foundations & slab on grade | Completed | 01-28-2026 | 7.23 | Pradeep | Anji Reddy
| Building - F Foundations & slab on grade | Completed | 01-31-2026 | 7.875 | Pradeep | Anji Reddy
Miami Shores Residence (R+R bluenest) | Foundations | Completed | 01-27-2026 | 9.474 | Swathi | Chandra Mouli
| Slab on grade | Completed | 2026-03-03 | 1.208 | Praveena | Chandra Mouli
| Lift - 1 Verticals, 2nd floor slab & beams | Completed | 2026-09-03 | 15.747 | Jagadeesh | Chandra Mouli
| Lift - 2 Verticals and Roof beams | Completed | 03-20-2026 | 2.904 | Praveena | Kameshwari
| Updated drawings received (Cantilever Beams) | Completed | 2026-06-26 | 0.619 | Praveena | eswar
Licata Residence 2726 Appaloosa trail | Foundations & slab on grade | Completed | 01-23-2026 | 0.764 | Swathi | Anji Reddy
| Lift - 1 Verticals and Roof beams | Completed | 01-23-2026 | 1.818 | Swathi | Anji Reddy
4669 S. Flagler Dr | Footings & Stem Walls | Completed | 2026-04-02 | 5.907 | Vaishnavi | Chandra Mouli
| Stem wall & Slab on grade | Completed | 02-20-2026 | 1.335 | Vaishnavi | Chandra Mouli
| Lift - 1 Verticals, 2nd floor slab & beams | Completed | 2026-04-03 | 27.935 | Vaishnavi | Chandra Mouli
| Lift - 2 Verticals & Roof beams | Completed | 2026-06-03 | 2.141 | Vaishnavi | Chandra Mouli
Harrison Residence | Foundations and slab on grade | Completed | 2026-05-02 | 0.256 | Sri Lalitha | Chandra Mouli
| Lift - 1 Verticals and Beams | Completed | 2026-02-03 | 0.834 | Sri Lalitha | Chandra Mouli
PBIA - Revenue Control Building | Foundations and slab on grade | Completed | 02-14-2026 | 11.285 | Praveena | Anji Reddy
| Lift - 1 Verticals and Roof beams | Completed | 02-19-2026 | 6.364 | Praveena | Anji Reddy
127 EL Bravo Way | Basement Foundations | Completed | 02-17-2026 | 13.887 | Danush | Anji Reddy
| Basement Walls | Completed | 02-21-2026 | 5.577 | Danush | Anji Reddy
| Level - 1 Foundations | Completed | 2026-12-03 | 22.202 | Danush | Chandra Mouli
| Lift - 1 Verticals | Completed | 03-16-2026 | 4.159 | Danush | Chandra Mouli
| Lift - 1 Beams | Completed | 03-28-2026 | 10.828 | Danush | Chandra Mouli
| Lift - 2 Verticals | Completed | 03-31-2026 | 1.709 | Danush | Chandra Mouli
| Roof beams | Completed | 03-31-2026 | 1.544 | Danush | Chandra Mouli
Blue Water Cove 6 | Foundations & slab on grade | Completed | 02-25-2026 | 12.306 | Allu Sai/Nanaji
| Lift-1 & 2 Verticals, 2nd floor slab, & Roof beams | Completed | 03-18-2026 | 6.168 | Allu Sai | Chandra Mouli
| Site walls | Inprogress | 07-29-2026 |  | Praveena
1050 N Lake way | Foundations and slab on grade | Completed | 02-17-2026 | 3.991 | Lokesh Reddy/Nanaji | Narayana
| Lift - 1 Verticals, 2nd floor slab & beams | Completed | 02-23-2026 | 9.309 | Lokesh Reddy | Kameshwari
| Lift - 2 Verticals & Roof beams | Completed | 03-13-2026 | 2.787 | Praveena | Kameshwari
143 Reef Road | Foundations and slab on grade | Completed | 03-13-2026 | 16.785 | Kunal | Chandra Mouli
| Lift - 1 Verticals | Completed | 05-15-2026 | 1.331 | Kunal | NANAJI
| 2nd floor slab & Beams | Completed | 05-15-2026 | 3.234 | Kunal | NANAJI
| Lift-2 verticals & Roof beams | Completed | 06-20-2026 |  | Kunal
Cutler Bay SHS | Foundations and slab on grade | Completed | 2026-04-03 | 2.305 | Swathi | Rds
| Lift - 1 Verticals and beams | Completed | 2026-04-03 | 2.027 | Swathi | Rds
| Lift - 2 Verticals and Low Roof slab & beams | Completed | 2026-04-03 | 1.242 | Swathi | Rds
| Lift - 3 Verticals and High Roof slab & beams | Completed | 2026-04-03 | 0.786 | Swathi | Rds
Ackerman Residence | Foundations & slab on grade | Completed | 2026-03-03 |  | Lokesh Reddy
| Lift - 1 Verticals, 2nd floor slab & beams | Completed | 03-21-2026 | 4.853 | Lokesh Reddy | Kameshwari
| Lift - 2 Verticals & Roof beams | Completed | 2026-02-04 | 1.285 | Lokesh Reddy | Kameshwari
Blue Water Cove 3 | Foundations & slab on grade | Completed | 2026-06-03 | 2.592 | Vaishnavi | Kameshwari
| Lift - 1 Verticals and Roof beams | Completed | 03-16-2026 | 4.562 | Vaishnavi | Kameshwari
BOKOR 432 SUNSHINE BLVD | Foundations and slab on grade | Completed | 2026-07-03 | 5.062 | Eswar | Eswar
| Lift - 1 Verticals, 2nd floor slab & beams | Completed | 03-13-2026 | 3.298 | Vaishnavi | Chandra Mouli
| Lift - 2 Verticals and Roof beams | Completed | 03-13-2026 | 1.695 | Vaishnavi | Chandra Mouli
Cloyd | Foundations and slab on grade | Completed | 03-11.-2026 | 2.267 | Vaishnavi | Chandra Mouli
| Lift - 1 Verticals and beams | Completed | 03-20.-2026 | 1.214 | Vaishnavi | Chandra Mouli
| Lift - 2 Verticals and beams | Completed | 03-20.-2026 | 0.835 | Vaishnavi | Chandra Mouli
6017 Le Lac Road (Weiner Residence) | Foundations and slab on grade (East Garage) | Completed | 03-21-2026 | 0.679 | Sri lalitha | Kameshwari
| Lift - 1 Verticals and Roof beams (East Garage) | Completed | 03-26-2026 | 1.643 | Praveena | Kameshwari
| Foundations and slab on grade (Main Building) | Completed | 03-25-2026 | 2.64 | Praveena | Kameshwari
| Lift - 1 Verticals, 2nd floor slab and beams (Main Building) | Completed | 2026-01-05 | 5.594 | Sridevi/Vaishnavi
| Lift - 2 Verticals and roof beams (Main Building) | Completed | 05-28-2026 | 4.782 | Vaishnavi | Eswar
| Foundations and slab on grade (2-story residence) | Completed | 04-21-2026 | 4.162 | Praveena | Chandra Mouli
| Lift - 1 Verticals, 2nd floor slab and beams (2-story residence) | Completed | 05-19-2026 | 12.373 | Vaishnavi | NANAJI
| Lift - 2 Verticals and roof beams (2-story residence) | Completed | 2026-05-06 | 2.935 | Vaishnavi
| Foundations and slab on grade (site work) | Completed | 2026-04-04 | 1.37 | Sri lalitha | Kameshwari
Bluewater cove 11 | Foundations and slab on grade | Completed | 03-24-2026 | 3.041 | Vaishnavi
| Lift - 1 Verticals and Roof beams | Completed | 2026-01-05 | 4.261 | Vaishnavi
Bluewater cove 9 | Foundations and slab on grade | Completed | 03-31-2026 | 15.362 | Vaishnavi | Kameshwari
| Lift - 1 Verticals and Roof Beams | Completed | 2026-01-05 | 5.012 | Nanaji/pradeep
164 Seminole | Foundations | Completed | 2026-08-04 | 2.269 | Siva kumar | Chandra Mouli
| Slab on grade | Completed | 05-18-2026 | 9.296 | Siva kumar | NANAJI
| Lift - 1 Verticals, 2nd floor slab and beams | job canceled |  |  | Siva kumar | NANAJI
| Lift - 2 Verticals and roof beams | job canceled
Roy & Shelley Silverman | Foundations and slab on grade | Completed | 2026-10-04 | 3.789 | Danush | Chandra Mouli
| Lift - 1 Verticals | Completed | 2026-04-05 | 3.191 | Danush | Chandra Mouli
| Lift - 1 slab & Beams | Completed | 2026-04-05 | 5.85 | Nanaji/Sridevi
| Lift - 2 Verticals & Roof beams | Completed | 2026-11-05 | 2.95 | Vaishnavi/Shiva | NANAJI
50 SE OLIVE | Foundations & columns | Completed | 2026-08-04 | 0.674 | Danush | Chandra Mouli
| Bond beams | Completed | 2026-08-04 | 0.174 | Danush | Chandra Mouli
Valencia Del Mar Clubhouse | Foundations and slab on grade | Completed | 2026-06-04 | 22.524 | Vaishnavi | Chandra Mouli
| Lift - 1 Verticals and beams (pour-1) | Completed | 2026-12-05 | 5.781 | Vaishnavi/Sridevi | NANAJI
| Lift - 1 Verticals and beams (pour-2) | Completed | 05-16-2026 | 10.773 | Sridevi | NANAJI
| Lift - 1 Verticals and beams (pour-3) & (pour-4) | Completed | 05-27-2026 | 10.014 | Sridevi | NANAJI
| Lift - 2 Verticals and beams (pour-1) | Completed | 05-29-2026 | 4.784 | Sridevi
| Lift - 2 Verticals and beams (pour-2) | Completed | 2026-03-06 | 3.643 | Sridevi
| Lift - 2 Verticals and beams (pour-3) | Completed | 2026-12-06 | 14.818 | Sridevi | NANAJI
| Monument walls | Completed | 04-27-2026 | 0.576 | Vaishnavi | Chandra Mouli
| Tennis & Bocce Courts Restrooms | Completed | 2026-09-05 | 0.123 | Eswar
910 S Ocean | Basement Foundations | Completed | 2026-08-04 |  | Sridevi | Narayana
| Lift - 1 Verticals & roof beams | Completed | 2026-10-04 |  | Sridevi | Narayana
| Retaining wall & Planter walls & stairs | Completed | 04-21-2026 |  | Sridevi | Narayana
Burns Residence | Foundations and slab on grade | Completed | 2026-06-04 | 7.45 | Praveena | Chandra Mouli
| Lift - 1 Verticals and Beams | Completed | 05-21-2026 | 7.962 | Siva kumar | NANAJI
| Lift - 2 Verticals and beams | Completed | 05-21-2026 | 0.175 | Siva kumar | NANAJI
5940 North Bay Road (NEW SINGLE FAMILY RESIDENCE) | Foundations | Completed | 2026-08-04 | 140.399 | Balaram/Jagadeesh | Chandra Mouli
320 S atlantic Drive | Foundations | Completed | 04-18-2026 | 6.817 | Sridevi | Chandra Mouli/NNJ
| Stem wall & Slab on grade | Completed | 2026-01-05 | 4.869 | Sridevi | Chandra Mouli/NNJ
| Lift - 1 Verticals, 2nd Floor slab & beams | Completed | 06-13-2026 | 15.352 | Vaishnavi | Chandra Mouli
| Lift - 2 Verticals and Roof beams | Completed | 06-18-2026 |  | Vaishnavi | NANAJI
Custom Residence (515 lido drive) | Foundations and slab on grade | Completed | 04-24-2026 | 22.418 | Vaishnavi | Chandra Mouli
| Lift - 1 Verticals | Completed | 2026-04-06 | 4.206 | Siva kumar | NANAJI
| 2nd floor slab & beams | Completed | 06-18-2026 | 11.165 | Jagadeesh | NANAJI
| Lift - 2 Verticals & Roof beams | Completed | 06-18-2026 | 3.221 | Balaram | NANAJI
Jandrews Residence | Foundations and slab on grade | Completed | 04-23-2026 | 16.272 | Praveena | Chandra Mouli
| Lift - 1 Verticals and beams | Completed | 2026-05-16 | 10.859 | Lokesh Reddy
| Lift - 2 Verticals and beams | Completed | 2026-06-03 |  | Lokesh Reddy
6024 Lelac Rd | Foundations and slab on grade | Completed | 2026-10-04 | 1.04 | Vaishnavi | Chandra Mouli
| Lift - 1 Verticals, loft floor slab & beams | Completed | 2026-10-04 | 1.18 | Vaishnavi | Chandra Mouli
| Lift - 2 Verticals and roof beams | Completed | 2026-10-04 | 1.26 | Vaishnavi | Chandra Mouli
| Foundations & slab on grade (Summer kitchen) | Completed | 04-22-2026 | 1.02 | Sridevi | NANAJI
| Lift - 1 Verticals, slab and beams (Summer kitchen) | Completed | 04-23-2026 | 1.69 | Sridevi
5900 Powerline Garag | Grade beams | Completed | 04-20-2026 | 16.4 | Sri lalitha
| Slab on grade, Lift - 1 Verticals and Roof beams | Completed | 2026-09-05 | 26.761 | Pradeep | NANAJI
South Florida Jewish Cemetery | Foundations and slab on grade | Completed | 2026-05-05 | 1.661 | Vaishnavi | Eswar
| Lift - 1 Verticals and Roof Beams | Completed | 05-22-2026 | 2.453 | Pradeep | NANAJI
1820 S Federal Hwy - Fifth Third Bank | Foundations and slab on grade | Completed | 04-24-2026 | 2.762 | Pradeep | Narayana
| Lift - 1 Verticals and Roof beams | Completed | 04-24-2026 | 1.259 | Pradeep | Narayana
20 Hudson Ave | Foundations & slab on grade | Completed | 05/26/26 |  | Eswar
| Lift - 1 Verticals and Beams | Completed | 06-18-2026 |  | Praveena | Kameshwari
| Lift - 2 Verticals and Beams | Completed | 06-18-2026 |  | Swathi | Kameshwari
South Rd Office Building E | Foundations and slab on grade | Completed | 04-24-2026 | 1.577 | Vaishnavi | NANAJI
| Lift - 1 Verticals and beams | Completed | 2026-01-05 | 4.107 | Lokesh/vaishnavi
Baig Residence | 3rd Floor tie beams | Completed | 2026-05-06 | 0.978 | Lokesh
| 2nd Floor slab | Completed | 2026-05-07 |  | Lokesh
SW Ranches | Lower Roof Deck | Completed | 2026-05-15 | 29.74 | Eswar
| Lift - 1 verticals | Completed | 2026-06-01 | 2.45 | Pradeep | NANAJI
2651 Southcast 10th court | Pool deck slab and beams | Completed | 2026-09-05 |  | Siva kumar
Country inn Pet Resort | Foundations and slab on grade | Completed | 05-22-2026 | 3.691 | Vaishnavi | NANAJI
| Lift - 1 verticals and beams | Completed | 2026-05-06 |  | Vaishnavi
2960 Greenbriair | Foundations | Completed | 2026-05-06 | 20.784 | Lokesh Reddy
| Slab on grade | Completed | 06-19-2026 |  | Sri Lalitha | NANAJI
| Lift - 1 verticals, beams and 2nd floor slab | Completed | 2026-02-07 |  | Sridevi
| Lift - 2 verticals and roof beams | Completed | 07-13-2026 |  | Praveena
Gallery at Somi Parc Phase 1 | Foundations (Residential) part - 1 | Completed | 06-17-2026 |  | Eswar/Nanaji
| Foundations (Residential) part - 2 | Completed | 06-18-2026 |  | Eswar/Nanaji
| Slab on grade (Residential) part - 1 & 2 | Completed | 2026-03-07 |  | Eswar
| Columns (Residential) lift - 1 to Roof verticals | Completed | 07-23-2026 |  | Eswar
| Shear walls (Residential) lift - 1 to Roof verticals | Completed | 07-17-2026 |  | Eswar
| 2nd Floor slab (Residential) | Not Yet Started |  |  | Siva kumar
| Cmu walls lift - 1 verticals | Not Yet Started |  |  | Sridevi
| 3rd Floor slab (Residential) | Not Yet Started
Cmu walls lift - 3 verticals
| 3rd Floor slab (Residential) | Not Yet Started
Cmu walls lift - 4 verticals
| 4th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 5 verticals
| 5th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 6 verticals
| 6th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 7 verticals
| 7th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 8 verticals
| 8th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 9 verticals
| 9th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 10 verticals
| 10th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 11 verticals
| 11th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 12 verticals
| 12th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 13 verticals
| 13th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 14 verticals
| 14th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 15 verticals
| 15th floor slab (Residential) | Not Yet Started
Cmu walls lift - 16 verticals
| Roof Floor slab (Residential) | Not Yet Started
| Parapet walls (Residential) verticals | Not Yet Started
| Foundations (Garage) | Not Yet Started
| Slab on grade (Garage) | Not Yet Started
| Columns (Garage) | Not Yet Started
| Shear walls (Garage) | Not Yet Started
| 2nd Floor slab (Garage) | Not Yet Started
| 3rd Floor slab (Garage) | Not Yet Started
| 4th Floor slab (Garage) | Not Yet Started
| 5th Floor slab (Garage) | Not Yet Started
| 6th Floor slab (Garage) | Not Yet Started
6007 Le Lac (Furing residence) | Foundations & Walls (scope added) | Completed | 05-16-2026 | 1.513 | Pradeep | NANAJI
| Cabana slab on grade | Completed | 06-25-2026 |  | Pradeep
| Cabana Columns & Beams | Completed | 07-21-2026 |  | Pradeep
90 Stingaree | Slab on grade | Completed | 2026-05-06 |  | siva kumar
| Lift - 1 verticals and beams | Completed | 2026-06-07 |  | Praveena
O.B. (Scattered Lots) | Foundaitons & sog. | Completed | 05-18-2026 | 0.725 | Lokesh Reddy | ESWAR
| Lift - 1 verticals and beams | Completed | 05-23-2026 |  | Lokesh Reddy
840 Denery Ln. Residence | Foundaitons & Slab on grade | Completed | 07-27-2026 |  | Out source (kumaran)
| Lift - 1 verticals and bond beams | Completed | 07-27-2026 |  | Out source (kumaran)
| 2nd floor slab & beams | Completed | 07-27-2026 |  | Out source (kumaran)
| Lift - 2 verticals and bond beams | Completed | 07-27-2026 |  | Out source (kumaran)
| Roof beams | Completed | 07-27-2026 |  | Out source (kumaran)
Nuvo | Bldg. Type 1 (A, C, D & G)
| Foundations and slab on grade | Completed | 2026-12-06 |  | siva kumar
| Lift - 1 verticals and beams | Completed | 06-13-2026 |  | Sridevi
| 2nd floor slab and beams | Completed | 2026-03-07 |  | siva kumar/sridevi
| Lift - 2 verticals and beams | Completed | 2026-03-07 |  | Nanaji/Sridevi
| 3rd floor slab and beams | Completed | 2026-03-07 |  | Lokesh reddy/Sridevi
| Lift - 3 verticals and beams | Completed | 2026-03-07
| 4th floor slab and beams | Completed | 2026-03-07
| Lift - 4 verticals and beams | Completed | 2026-03-07
| Roof slas, beams & parapet walls | Completed | 2026-03-07
Bldg. Type 2 (E & H)
| Foundations and slab on grade | Completed | 2026-03-07 |  | Lokesh Reddy
| Lift - 1 verticals and beams | Completed | 06-15-2026 |  | siva kumar
| 2nd floor slab and beams | Completed | 2026-10-07 |  | Lokesh Reddy
| Lift - 2 verticals and beams | Completed | 2026-10-07 |  | Lokesh Reddy
| 3rd floor slab and beams | Completed | 2026-10-07 |  | Lokesh Reddy
| Lift - 3 verticals and beams | Completed | 2026-10-07
| 4th floor slab and beams | Completed | 2026-10-07
| Lift - 4 verticals and beams | Completed | 2026-10-07
| Roof slas, beams & parapet walls | Completed
Bldg. Type 3 (B & F)
| Foundations and slab on grade | Completed | 2026-10-07 |  | Lokesh Reddy
| Lift - 1 verticals and beams | Completed | 2026-10-07 |  | siva kumar
| 2nd floor slab and beams | Completed | 2026-10-07 |  | Lokesh Reddy/Siva kumar
| Lift - 2 verticals and beams | Completed | 2026-10-07 |  | Lokesh Reddy/Siva kumar
| 3rd floor slab and beams | Completed | 2026-10-07
| Lift - 3 verticals and beams | Completed | 2026-10-07
| 4th floor slab and beams | Completed | 2026-10-07
| Lift - 4 verticals and beams | Completed | 2026-10-07
| Roof slas, beams & parapet walls | Completed | 2026-10-07
Bus Shelter - Footings
| Bg Thru 1st lift | Not Yet Started |  |  | Pradeep
Clubhouse
| Bg Thru Abv Roof beams | Completed | 2026-05-06 |  | siva kumar
Garage Type 1
| Bg Thru Abv Roof beams | Completed | 07-31-2026 |  | Pavan sai
Garage Type 2
| Bg Thru Abv Roof beams | Inprogress | 2026-03-08 |  | Pavan sai
Mail Kiosk - Slab on grade
| Slab on grade | Not Yet Started |  |  | Pradeep
Trash Compactor
| Bg Thru 1st lift | Completed | 07-31-2026 |  | Pavan sai
Pool Pavilion
| Bg Thru Roof beams | Inprogress | 2026-03-08 |  | Pavan sai
Raised Planters
| Bg Thru 1st lift | Not Yet Started |  |  | Pradeep
BBQ Station
| Bg Thru Roof beams | Not Yet Started |  |  | Pradeep
Cabana Footings
| Bg Thru 1st lift | Inprogress |  |  | Pradeep
Trellis Footings
| Bg Thru 1st lift | Inprogress |  |  | Pradeep
| Retaining Wall | Completed | 2026-12-06 | 29.997 | Pradeep | NANAJI
| Bg Thru 1st lift | Completed | 2026-12-06 |  | Pradeep
The Syed Residence | Foundations & Slab on grade | Completed | 2026-06-05 |  | Eswar
| Lift - 1 verticals and beams | Completed | 07-13-2026 |  | Lalitha
| Lift - 2 verticals and beams | Completed | 07-21-2026 |  | Nanaji
810 S Swinton Ave Residence | Foundations and slab on grade | Completed | 2026-09-06 |  | Praveena
| Lift - 1 verticals and beams | Completed | 07-21-2026 |  | Praveena
| Lift - 2 verticals and beams | Completed | 07-31-2026 |  | Praveena
Custom Residence (134 Worth CTN) | Foundations | Completed | 06-13-2026 |  | Praveena
| Slab on grade | Completed | 06-13-2026 |  | Vaishnavi
| Lift - 1 verticals and beams | Completed | 07-17-2026 |  | Jagadeesh
| Lift - 2 verticals and beams | Completed | 07-17-2026
Rancano | Foundations & slab on grade | Completed | 2026-11-06 | 6.108 | Eswar
| Lift - 1 verticals and Roof beams | Completed | 06-17-2026 | 1.66 | Sridevi | NANAJI
799 Park Drive | Foundations & Slab on grade | Completed | 2026-06-16 | 2.264 | Pradeep | Nanaji
| Lift - 1 verticals and beams | Completed | 2026-06-20 | 3.621 | Pradeep | Chandra mouli
| Lift - 2 verticals and beams | Completed | 2026-06-26 | 1.412 | Pradeep | Chandra mouli
Chateau De La Duchess (925 Hillsboro) | Entry Garages foundations and slab on grade | Completed | 07-23-2026 |  | Pradeep
| Entry Garages lift - 1 verticals and beams | Completed | 07-23-2026 |  | Pradeep
| Entry Garages lift - 2 verticals and beams | Completed | 07-23-2026 |  | Pradeep
Masucci Residence | Foundations & slab on grade | Completed | 06-26-2026
| Lift - 1 verticals and beams | Completed | 2026-09-07 |  | Out Source (Kumaran)
| 2nd floor slab and beams | Completed | 2026-09-07 |  | Out Source (Kumaran)
| Lift - 2 verticals and beams | Completed | 2026-11-07 |  | Out Source (Kumaran)
The Bueller family | Foundations & slab on grade | Completed | 06-26-2026 |  | siva kumar
| Lift - 1 verticals and beams | Completed | 06-26-2026 |  | siva kumar
SPOTLOT 28810 SW 207 AVE | Foundations & slab on grade | Completed | 06-26-2026 | 1.087 | Eswar
| Lift - 1 verticals and beams | Completed | 06-26-2026 | 1.032 | Lokesh
Broken Sound Club | Foundations & slab on grade | Completed | 06-23-2026 |  | siva kumar
| Lift - 1 verticals and beams | Completed | 06-23-2026 |  | siva kumar
128 Worth CT N | Foundations & slab on grade | Completed | 2026-11-07 |  | Pradeep
| Lift - 1 verticals and beams | Inprogress | 2026-07-08 |  | Pavan sai
| Lift - 2 verticals and beams | Not Yet Started | 2026-07-08
2235 Mangolia Drive | Foundations & slab on grade | Completed | 2026-10-07 |  | Praveena
| Lift - 1 verticals and beams | Inprogress | 2026-07-08 |  | Praveena
| Lift - 2 verticals and beams | Not Yet Started | 08-14-2026
270 Celestial Way | Slab and beams | Completed | 07-14-2026 |  | Sri lalitha
501 Diplomat - Porte Cochere | Columns, Cmu walls, tie beams & concrete caps | Completed | 07-23-2026 |  | Praveena
| Roof slab | Not Yet Started | 2026-10-07 |  | Praveena
Zen Elite Equestrian Center | Foundations & Slab on grade | Completed | 07-24-2026 |  | Pradeep
| Lift - 1 Verticals and beams | Completed | 07-24-2026
Belle Meade Residence | Foundations | Completed | 07-31-2026 |  | Sri lalitha
| Slab on grade | Inprogress | 2026-07-08 |  | Sri lalitha
| Lift - 1 Verticals and beams | Not Yet Started | 08-14-2026
| 2nd floor slab and beams | Not Yet Started | 08-14-2026
| Lift - 2 Verticals and beams | Not Yet Started | 08-14-2026
The Duhl Residence | Foundations | Completed | 07-31-2026 |  | Sridevi
| Slab on grade | Completed | 07-31-2026
| Lift - 1 Verticals and beams | Not Yet Started | 08-14-2026
| Lift - 2 Verticals and beams | Not Yet Started | 08-14-2026
1105 Northlake Way | Foundations and slab on grade | Completed | 07-28-2026 |  | Out Source (Kumaran)
| Lift - 1 Verticals and beams | Completed | 07-28-2026 |  | Out Source (Kumaran)
Miller Residence | Foundations | Completed | 07-24-2026 |  | Praveena
| Slab on grade | Completed | 07-28-2026
| Lift - 1 Verticals and beams | Not Yet Started | 2026-07-08
| 2nd floor slab and beams | Not Yet Started | 2026-07-08
| Lift - 2 Verticals and beams | Not Yet Started | 2026-07-08
Mdag Miami Dad Spot Lots | Foundations & slab on grade | Completed | 07-17-2026 |  | siva kumar
| Lift - 1 Verticals and beams | Not Yet Started | 2026-07-08
| Lift - 2 Verticals and beams | Not Yet Started | 2026-07-08
Arrigo Residence | Foundations | Completed | 07-28-2026 |  | siva kumar
| Slab on grade | Completed | 07-29-2026
| Lift - 1 Verticals and beams | Not Yet Started | 2026-07-08
| Lift - 2 Verticals and beams | Not Yet Started | 2026-07-08
| Pool house foundations & slab on grade | Completed | 07-29-2026
| Lift - 1 Verticals and roof beams | Not Yet Started | 2026-07-08
New Luse Residence (9401 Residence) | Foundations | Completed | 07-31-2026 |  | Lokesh Reddy
| Slab on grade | Completed | 07-31-2026
| Lift - 1 Verticals and beams | Not Yet Started | 08-14-2026
| Lift - 2 Verticals and beams | Not Yet Started | 08-14-2026
| Site walls | Not Yet Started | 08-14-2026
Riopelle Residence | Foundations & slab on grade | Completed | 07-31-2026 |  | Pradeep
| Lift -1 Verticals and roof beams | Completed | 07-31-2026
Coy Residence | Garage Building
| Foundations & slab on grade | Inprogress | 2026-06-08
| Lift - 1 Verticals & beams | Inprogress | 2026-11-08
| Lift - 2 Verticals & beams | Inprogress | 2026-11-08
Main Building
| Foundations & Slab on grade | Inprogress | 2026-06-08
| Lift - 1 Verticals & beams | Inprogress | 2026-11-08
| Lift - 2 Verticals and beams | Inprogress | 2026-11-08
Dolce Residence | Foundations and slab on grade | Inprogress | 2026-05-08
| Lift - 1 Verticals beams | Not Yet Started | 08-14-2026
| Lift - 2 Verticals and roof beams | Not Yet Started | 08-14-2026
Residential Duplex | Foundations and slab on grade | Not Yet Started | 2026-07-08 |  | siva kumar
| Lift - 1 Verticals beams | Not Yet Started | 08-14-2026
| Lift - 2 Verticals and roof beams | Not Yet Started | 08-14-2026
Gensis (Scattered Lots) | Foundations and slab on grade | Inprogress | 2026-05-08 |  | Lokesh Reddy
| Lift - 1 Verticals beams | Not Yet Started | 08-14-2026
| Lift - 2 Verticals and roof beams | Not Yet Started | 08-14-2026
MCCOY RESIDENCE | Foundations & slab on grade | Not Yet Started | 2026-07-08
| Lift - 1 Verticals | Not Yet Started | 2026-07-08
1042 Palm Way rd NPB Pinsonnault Residence | Foundations and slab on grade | Not Yet Started
Verticals&beams
OLD PROJECTS MODIFICATIONS
1333 Bvld | Shear walls and columns Barlists | Completed | 2026-07-05 |  | Lokesh Reddy
Valencia Del Mar Clubhouse | Slab on grade Barlists | Completed | 2026-05-05 |  | Vaishnavi
320 S atlantic Drive | Foundations Barlists | Completed | 2026-05-05 |  | Sridevi
910 S Ocean | Comments received on basement R1series dwgs | Completed | 2026-06-05 |  | Sridevi
6024 Le lac Rd | Comments received on pool cabana & outdoor kitchen | Completed | 2026-07-05 |  | Sridevi / Vaishnavi
6017 Le Lac Road (Weiner Residence) | Barlists requested for 2story building lift - 1 verticals | Completed | 2026-06-05 |  | Vaishnavi
South Rd Office Building E | Lift - 1 Verticals and beams | Completed | 2026-07-05 |  | Vaishnavi
559 Nw 43 st | Stairs barlists | Completed | 2026-06-05 |  | Danush
PBIA - Revenue Control Building | Rfi-029 received on foundaitons | Completed | 2026-08-05 |  | Vaishnavi
Sands residence (3223 N Ocean) | Ssk-017 Received for 2nd for slab at balcony | Completed | 2026-08-05 |  | Eswar
5900 Powerline Garage | Foundations (Grade beams) | Completed | 2026-08-05 |  | Pradeep
1050 N Lake way | 2nd lift - 2 verticals and beams | Completed | 2026-09-05 |  | Lokesh Reddy
Baig Residence | 2nd floor slab | Completed | 2026-09-05 |  | Lokesh Reddy
South Rd Office Building E | Need patch lists for cmu walls at stem walls | Completed | 2026-09-05 |  | Lokesh Reddy
Valencia Del Mar Clubhouse | Lift - 1 verticals section #3 | Completed | 05-19-2026
South Rd Office Building E | Lift -1 verticals barlists | Completed | 05-13-2026 |  | Lokesh Reddy
2651 SE 10th Court | Pool deck slab and beams barlists | Completed | 05-18-2026
6017 Le Lac Road (Weiner Residence) | Orange section #2 1st lift verticals | Completed | 05-19-2026
1333 Bvld | Stem walls barlists | Completed | 05-18-2026
2651 SE 10th Court | Update received on the pool deck | Completed | 05-19-2026
cannatelli | Foundations and slab on grade Barlists | Completed | 05-18-2026
6017 Le Lac Road (Weiner Residence) | Lift - 1 verticals and beams for Blue section | Completed
401 SE Atlantic Drive | Barlists for R3 series drawings | Completed | 05-20-2026
515 Lido Drive | Column ties for upto 4'-0" | Completed | 05-20-2026
143 Reef Road | 1st floor beams and second floor slab | Completed
PBIA - Revenue Control Building | Revised drawings received on cmu verticals | Completed | 05-22-2026
515 Lido Drive | Garage slab barlists | Completed | 05-21-2026
cannatelli | Foundations and slab on grade Barlists | Completed | 05-23-2026
1042 Palm Way Road | Roof beams and slab | Completed | 05-28-2026
South Rd Office Building E | Comments received on 1st lift verticals and beams | Completed | 05-22-2026
910 S Ocean | Basement slab barlists | Completed | 05-27-2026
Valencia Del Mar Clubhouse | Lift - 2 verticals and beams for green section #2 | Completed | 05-28-2026
Valencia Del Mar Clubhouse | Lift - 2 verticals and beams for Yellow section #1 | Completed | 05-28-2026
Burns Residence | Slab on grade barlists | Completed | 05-28-2026
1900 NE 22ND Terrance | Comments received on slab on grade | Completed | 05-28-2026
975.703
Note: Submittal dates may change according to client request / RFI Clarification /Priorities