## May 1st Week
Rebar Department Weekly Project Status Report-April 2026
Date Range |  | 05/04/2026 to 05/09/2026
Projects & Actives for Above dates
S.no | Client | Project name | Description | Tonnage | Hours | Status | Remarks |  | Detaielrs
1
2
3
4
5
Total |  |  |  | 0 | 0 |  |  | 0
Projects & Actives Planned to This week
Total |  |  |  | 0 | 0 |  |  | 0
Work in hand
1 |  | 143 Reef Road | Lift - 1 Verticals
Lift - 1 Beams & 2nd floor slab
Roof beams
2 |  | 6017 Le Lac Road (Weiner Residence) | Lift - 2 Verticals and roof beams (Main Building)
Lift - 1 Verticals, 2nd floor slab and beams (2-story residence)
Lift - 2 Verticals and roof beams (2-story residence)
3 |  | 164 Seminole | Slab on grade | [5 empty] | Siva Kumar
|  |  | Lift - 1 Verticals, 2nd floor slab and beams | [5 empty] | Siva Kumar
|  |  | Lift - 2 Verticals and roof beams | [5 empty] | Siva Kumar
4 |  | Roy & Shelley Silverman | Lift - 1 Beams | [5 empty] | Nanaji
|  |  | Lift - 2 Verticals & Roof beams | [5 empty] | Sridivi/Nanaji
5 |  | Valencia Del Mar Clubhouse | Lift - 1 Verticals and beams
Lift - 2 Verticals and beams
6 |  | Burns Residence | Lift - 1 Verticals and Beams
Lift - 2 Verticals and beams
7 |  | 320 S atlantic Drive | Lift - 1 Verticals, 2nd Floor slab & beams
Lift - 2 Verticals and Roof beams
8 |  | Custom Residence (515 lido drive) | Lift - 1 Verticals, 2nd floor slab & beams
Lift - 2 Verticals & Roof beams
9 |  | Jandrews Residence | Lift - 1 Verticals and beams
Lift - 2 Verticals and beams
10 |  | 5900 Powerline Garage | Lift - 1 Verticals and Roof beams | [5 empty] | Pradeep
11 |  | South Florida Jewish Cemetery | Foundations and slab on grade | [5 empty] | Vaishnavi
Lift - 1 Verticals and Roof Beams
12 |  | 20 Hudson Ave | Foundations & slab on grade
Lift - 1 Verticals and Beams
Lift - 2 Verticals and Beams
13 |  | Baig Residence | 3rd Floor tie beams
14 |  | SW Ranches | Lower Roof Deck
Total |  |  |  | 0 | 60 |  |  | 60
Bar listing & FFU drawings. (Non billable work)
1
2
3
3
4
5
6
7
Total |  |  |  | 0 | 0
Frist Week Weight+hours |  | Second week Weight + hours | Third week weight+hours | Fourth week Weight + hours |  |  | Total
0 |  | 0 | 0 | 0 |  |  | 0
Rebar @ Structural Steel
S.No | Engineers |  | Leaves | Permissions | Over Time | Remarks
1 | Eswar | Project management
2 | Nanaji | Rebar Detailing/QC
3 | Y Siva kumar | Estimations and rebar detailing
4 | Lokesh reddy | Rebar Detailing
5 | Sridevi | Rebar Detailing
6 | Vaishnavi | Rebar Detailing
7 | Pradeep | Rebar Detailing

## White Cap Work Schedule
White Cap PROJECT STATUS
PROJECT NAME | Tasks | STATUS | CLIENT SUB. DATE | DETAILER | CHECKER
Felies Residence | Foundations and slab on grade | Completed | 2026-12-01 | Praveena | Chandra Mouli
| Lift - 1 Verticals & beams, 2nd floor slab & beams | Completed | 01-29-2026 | Praveena | Anji Reddy
| Lift - 2 verticals & beams, Roof slab & beams | Completed | 2026-06-02 | Praveena | Anji Reddy
Valencia Del Mar Pickleball | Foundations and slab on grade | Completed | 01-19-2026 | Dhanush | Kameshwari
| Lift - 1 Verticals & beams | Completed | 01-23-2026 | Dhanush | Kameshwari
| Lift - 2 Verticals & beams | Completed | 01-23-2026 | Dhanush | Kameshwari
| Double Dumpster Enclosure | Completed | 02-18-2026 | Praveena | Kameshwari
| Single Dumpster Enclosure | Completed | 02-18-2026 | Praveena | Kameshwari
| Mail Pavilion | Completed | 02-18-2026 | Praveena | Kameshwari
| Monument sign | Completed | 2026-01-06 | Pradeep | Nanaji
City of temple terrace-fire station #01 | Foundations | Completed | 01-19-2026 | Swathi | Chandra Mouli
| Slab on grade | Completed | 02-14-2026 | Sri Lalitha | Kameshwari
| Lift - 1 Verticals, 2nd floor slab & beams | Completed | 02-25-2026 | Sri Lalitha | Kameshwari
| Lift - 2 Verticals and Roof beams | Completed | 02-25-2026 | Sri Lalitha | Kameshwari
228 Rutland | Foundations and slab on grade | Completed | 01-13-2026 | Sai | Kameshwari
| Lift - 1 Verticals and Bond beams | Completed | 2026-03-02 | Sai | Kameshwari
| Low Roof beams & Slab | Completed | 02-19-2026 | Vaishnavi | Kameshwari
| Lift - 2 Verticals, Bond beams & Roof beams | Completed | 2026-02-03 | Siva Kumar | Kameshwari
Palmetto Lakes Industrial Park | Foundations and slab on grade | Completed | 01-14-26 | Sri Lalitha | Chandra Mouli
| Lift - 1 walls, Columns & Beams | Completed | 01-27-26 | Sri Lalitha | Chandra Mouli
| Lift - 2 walls, Columns & Beams | Completed | 01-27-26 | Sri Lalitha | Chandra Mouli
Frenchman's Creek Operations Center | Building - A Foundations & slab on grade | Completed | 01-26-2026 | Pradeep | Anji Reddy
| Building - B Foundations & slab on grade | Completed | 01-21-2026 | Pradeep | Narayana
| Building - C Foundations & slab on grade | Completed | 01-21-2026 | Praveena | Anji Reddy
| Building - D Foundations & slab on grade | Completed | 01-26-2026 | Pradeep | Anji Reddy
| Building - E Foundations & slab on grade | Completed | 01-28-2026 | Pradeep | Anji Reddy
| Building - F Foundations & slab on grade | Completed | 01-31-2026 | Pradeep | Anji Reddy
Miami Shores Residence (R+R bluenest) | Foundations | Completed | 01-27-2026 | Swathi | Chandra Mouli
| Slab on grade | Completed | 2026-03-03 | Praveena | Chandra Mouli
| Lift - 1 Verticals, 2nd floor slab & beams | Completed | 2026-09-03 | Jagadeesh | Chandra Mouli
| Lift - 2 Verticals and Roof beams | Completed | 03-20-2026 | Praveena | Kameshwari
| Updated drawings received (Cantilever Beams) | Completed | 2026-06-26 | Praveena | eswar
Licata Residence 2726 Appaloosa trail | Foundations & slab on grade | Completed | 01-23-2026 | Swathi | Anji Reddy
| Lift - 1 Verticals and Roof beams | Completed | 01-23-2026 | Swathi | Anji Reddy
4669 S. Flagler Dr | Footings & Stem Walls | Completed | 2026-04-02 | Vaishnavi | Chandra Mouli
| Stem wall & Slab on grade | Completed | 02-20-2026 | Vaishnavi | Chandra Mouli
| Lift - 1 Verticals, 2nd floor slab & beams | Completed | 2026-04-03 | Vaishnavi | Chandra Mouli
| Lift - 2 Verticals & Roof beams | Completed | 2026-06-03 | Vaishnavi | Chandra Mouli
Harrison Residence | Foundations and slab on grade | Completed | 2026-05-02 | Sri Lalitha | Chandra Mouli
| Lift - 1 Verticals and Beams | Completed | 2026-02-03 | Sri Lalitha | Chandra Mouli
PBIA - Revenue Control Building | Foundations and slab on grade | Completed | 02-14-2026 | Praveena | Anji Reddy
| Lift - 1 Verticals and Roof beams | Completed | 02-19-2026 | Praveena | Anji Reddy
127 EL Bravo Way | Basement Foundations | Completed | 02-17-2026 | Dhanush | Anji Reddy
| Basement Walls | Completed | 02-21-2026 | Dhanush | Anji Reddy
| Level - 1 Foundations | Completed | 2026-12-03 | Dhanush | Chandra Mouli
| Lift - 1 Verticals | Completed | 03-16-2026 | Dhanush | Chandra Mouli
| Lift - 1 Beams | Completed | 03-28-2026 | Dhanush | Chandra Mouli
| Lift - 2 Verticals | Completed | 03-31-2026 | Dhanush | Chandra Mouli
| Roof beams | Completed | 03-31-2026 | Dhanush | Chandra Mouli
Blue Water Cove 6 | Foundations & slab on grade | Completed | 02-25-2026 | Sai/Nanaji
| Lift-1 & 2 Verticals, 2nd floor slab, & Roof beams | Completed | 03-18-2026 | Sai | Chandra Mouli
1050 N Lake way | Foundations and slab on grade | Completed | 02-17-2026 | Lokesh/Nanaji | Narayana
| Lift - 1 Verticals, 2nd floor slab & beams | Completed | 02-23-2026 | Lokesh | Kameshwari
| Lift - 2 Verticals & Roof beams | Completed | 03-13-2026 | Praveena | Kameshwari
143 Reef Road | Foundations and slab on grade | Completed | 03-13-2026 | Kunal | Chandra Mouli
| Lift - 1 Verticals | Completed | 05-15-2026 | Kunal | Nanaji
| 2nd floor slab & Beams | Completed | 05-15-2026 | Kunal | Nanaji
| Lift-2 verticals & Roof beams | Completed | 06-20-2026 | Kunal
Cutler Bay SHS | Foundations and slab on grade | Completed | 2026-04-03 | Swathi
| Lift - 1 Verticals and beams | Completed | 2026-04-03 | Swathi
| Lift - 2 Verticals and Low Roof slab & beams | Completed | 2026-04-03 | Swathi
| Lift - 3 Verticals and High Roof slab & beams | Completed | 2026-04-03 | Swathi
Ackerman Residence | Foundations & slab on grade | Completed | 2026-03-03 | Lokesh
| Lift - 1 Verticals, 2nd floor slab & beams | Completed | 03-21-2026 | Lokesh | Kameshwari
| Lift - 2 Verticals & Roof beams | Completed | 2026-02-04 | Lokesh | Kameshwari
Blue Water Cove 3 | Foundations & slab on grade | Completed | 2026-06-03 | Vaishnavi | Kameshwari
| Lift - 1 Verticals and Roof beams | Completed | 03-16-2026 | Vaishnavi | Kameshwari
BOKOR 432 SUNSHINE BLVD | Foundations and slab on grade | Completed | 2026-07-03 | Eswar | Eswar
| Lift - 1 Verticals, 2nd floor slab & beams | Completed | 03-13-2026 | Vaishnavi | Chandra Mouli
| Lift - 2 Verticals and Roof beams | Completed | 03-13-2026 | Vaishnavi | Chandra Mouli
Cloyd | Foundations and slab on grade | Completed | 03-11.-2026 | Vaishnavi | Chandra Mouli
| Lift - 1 Verticals and beams | Completed | 03-20.-2026 | Vaishnavi | Chandra Mouli
| Lift - 2 Verticals and beams | Completed | 03-20.-2026 | Vaishnavi | Chandra Mouli
6017 Le Lac Road (Weiner Residence) | Foundations and slab on grade (East Garage) | Completed | 03-21-2026 | Sri lalitha | Kameshwari
| Lift - 1 Verticals and Roof beams (East Garage) | Completed | 03-26-2026 | Praveena | Kameshwari
| Foundations and slab on grade (Main Building) | Completed | 03-25-2026 | Praveena | Kameshwari
| Lift - 1 Verticals, 2nd floor slab and beams (Main Building) | Completed | 2026-01-05 | Sridevi
| Lift - 2 Verticals and roof beams (Main Building) | Completed | 05-28-2026 | Vaishnavi | Eswar
| Foundations and slab on grade (2-story residence) | Completed | 04-21-2026 | Praveena | Chandra Mouli
| Lift - 1 Verticals, 2nd floor slab and beams (2-story residence) | Completed | 05-19-2026 | Vaishnavi | Nanaji
| Lift - 2 Verticals and roof beams (2-story residence) | Completed | 2026-05-06 | Vaishnavi
| Foundations and slab on grade (site work) | Completed | 2026-04-04 | Sri lalitha | Kameshwari
Bluewater cove 11 | Foundations and slab on grade | Completed | 03-24-2026 | Vaishnavi
| Lift - 1 Verticals and Roof beams | Completed | 2026-01-05 | Vaishnavi
Bluewater cove 9 | Foundations and slab on grade | Completed | 03-31-2026 | Vaishnavi | Kameshwari
| Lift - 1 Verticals and Roof Beams | Completed | 2026-01-05 | Nanaji/pradeep
164 Seminole | Foundations | Completed | 2026-08-04 | Siva Kumar | Chandra Mouli
| Slab on grade | Completed | 05-18-2026 | Siva Kumar | Nanaji
| Lift - 1 Verticals, 2nd floor slab and beams | job canceled |  | Siva Kumar | Nanaji
| Lift - 2 Verticals and roof beams | job canceled
Roy & Shelley Silverman | Foundations and slab on grade | Completed | 2026-10-04 | Dhanush | Chandra Mouli
| Lift - 1 Verticals | Completed | 2026-04-05 | Dhanush | Chandra Mouli
| Lift - 1 slab & Beams | Completed | 2026-04-05 | Nanaji/Sridevi
| Lift - 2 Verticals & Roof beams | Completed | 2026-11-05 | Vaishnavi/Shiva | Nanaji
50 SE OLIVE | Foundations & columns | Completed | 2026-08-04 | Dhanush | Chandra Mouli
| Bond beams | Completed | 2026-08-04 | Dhanush | Chandra Mouli
Valencia Del Mar Clubhouse | Foundations and slab on grade | Completed | 2026-06-04 | Vaishnavi | Chandra Mouli
| Lift - 1 Verticals and beams (pour-1) | Completed | 2026-12-05 | Vaishnavi/Sridevi | Nanaji
| Lift - 1 Verticals and beams (pour-2) | Completed | 05-16-2026 | Sridevi | Nanaji
| Lift - 1 Verticals and beams (pour-3) & (pour-4) | Completed | 05-27-2026 | Sridevi | Nanaji
| Lift - 2 Verticals and beams (pour-1) | Completed | 05-29-2026 | Sridevi
| Lift - 2 Verticals and beams (pour-2) | Completed | 2026-03-06 | Sridevi
| Lift - 2 Verticals and beams (pour-3) | Completed | 2026-12-06 | Sridevi | Nanaji
| Monument walls | Completed | 04-27-2026 | Vaishnavi | Chandra Mouli
| Tennis & Bocce Courts Restrooms | Completed | 2026-09-05 | Eswar
910 S Ocean | Basement Foundations | Completed | 2026-08-04 | Sridevi | Narayana
| Lift - 1 Verticals & roof beams | Completed | 2026-10-04 | Sridevi | Narayana
| Retaining wall & Planter walls & stairs | Completed | 04-21-2026 | Sridevi | Narayana
Burns Residence | Foundations and slab on grade | Completed | 2026-06-04 | Praveena | Chandra Mouli
| Lift - 1 Verticals and Beams | Completed | 05-21-2026 | Siva Kumar | Nanaji
| Lift - 2 Verticals and beams | Completed | 05-21-2026 | Siva Kumar | Nanaji
5940 North Bay Road (NEW SINGLE FAMILY RESIDENCE) | Foundations | Completed | 2026-08-04 | Balaram/Jagadeesh | Chandra Mouli
320 S atlantic Drive | Foundations | Completed | 04-18-2026 | Sridevi | Chandra Mouli
| Stem wall & Slab on grade | Completed | 2026-01-05 | Sridevi | Chandra Mouli
| Lift - 1 Verticals, 2nd Floor slab & beams | Completed | 06-13-2026 | Vaishnavi | Chandra Mouli
| Lift - 2 Verticals and Roof beams | Completed | 06-18-2026 | Vaishnavi | Nanaji
Custom Residence (515 lido drive) | Foundations and slab on grade | Completed | 04-24-2026 | Vaishnavi | Chandra Mouli
| Lift - 1 Verticals | Completed | 2026-04-06 | Siva Kumar | Nanaji
| 2nd floor slab & beams | Completed | 06-18-2026 | Jagadeesh | Nanaji
| Lift - 2 Verticals & Roof beams | Completed | 06-18-2026 | Balaram | Nanaji
Jandrews Residence | Foundations and slab on grade | Completed | 04-23-2026 | Praveena | Chandra Mouli
| Lift - 1 Verticals and beams | Completed | 2026-05-16 | Lokesh
| Lift - 2 Verticals and beams | Completed | 2026-06-03 | Lokesh
6024 Lelac Rd | Foundations and slab on grade | Completed | 2026-10-04 | Vaishnavi | Chandra Mouli
| Lift - 1 Verticals, loft floor slab & beams | Completed | 2026-10-04 | Vaishnavi | Chandra Mouli
| Lift - 2 Verticals and roof beams | Completed | 2026-10-04 | Vaishnavi | Chandra Mouli
| Foundations & slab on grade (Summer kitchen) | Completed | 04-22-2026 | Sridevi | Nanaji
| Lift - 1 Verticals, slab and beams (Summer kitchen) | Completed | 04-23-2026 | Sridevi
5900 Powerline Garag | Grade beams | Completed | 04-20-2026 | Sri lalitha
| Slab on grade, Lift - 1 Verticals and Roof beams | Completed | 2026-09-05 | Pradeep | Nanaji
South Florida Jewish Cemetery | Foundations and slab on grade | Completed | 2026-05-05 | Vaishnavi | Eswar
| Lift - 1 Verticals and Roof Beams | Completed | 05-22-2026 | Pradeep | Nanaji
1820 S Federal Hwy - Fifth Third Bank | Foundations and slab on grade | Completed | 04-24-2026 | Pradeep | Narayana
| Lift - 1 Verticals and Roof beams | Completed | 04-24-2026 | Pradeep | Narayana
20 Hudson Ave | Foundations & slab on grade | Completed | 05/26/26 | Eswar
| Lift - 1 Verticals and Beams | Completed | 06-18-2026 | Praveena | Kameshwari
| Lift - 2 Verticals and Beams | Completed | 06-18-2026 | Swathi | Kameshwari
South Rd Office Building E | Foundations and slab on grade | Completed | 04-24-2026 | Vaishnavi | Nanaji
| Lift - 1 Verticals and beams | Completed | 2026-01-05 | Lokesh/vaishnavi
Baig Residence | 3rd Floor tie beams | Completed | 2026-05-06 | Lokesh
| 2nd Floor slab | Completed | 2026-05-07 | Lokesh
SW Ranches | Lower Roof Deck | Completed | 2026-05-15 | Eswar
| Lift - 1 verticals | Completed | 2026-06-01 | Pradeep | Nanaji
2651 Southcast 10th court | Pool deck slab and beams | Completed | 2026-09-05
Country inn Pet Resort | Foundations and slab on grade | Completed | 05-22-2026 | Vaishnavi | Nanaji
| Lift - 1 verticals and beams | Completed | 2026-05-06 | Vaishnavi
2960 Greenbriair | Foundations | Completed | 2026-05-06 | Lokesh
| Slab on grade | Completed | 06-19-2026 | Sri Lalitha | Nanaji
| Lift - 1 verticals, beams and 2nd floor slab | Inprogress | 2026-03-07 | Sridevi
| Lift - 2 verticals and roof beams | Inprogress | 2026-03-07 | Praveena
Gallery at Somi Parc Phase 1 | Foundations (Residential) part - 1 | Completed | 06-17-2026 | Eswar/Nanaji
| Foundations (Residential) part - 2 | Completed | 06-18-2026
| Slab on grade (Residential) part - 1 & 2 | Inprogress | 06-26-2026
| Columns (Residential) lift - 1 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 1 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 1 verticals | Not Yet Started | 2026-10-07
| 2nd Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 2 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 2 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 2 verticals | Not Yet Started | 2026-10-07
| 3rd Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 3 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 3 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 3 verticals | Not Yet Started | 2026-10-07
| 3rd Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 4 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 4 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 4 verticals | Not Yet Started | 2026-10-07
| 4th Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 5 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 5 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 5 verticals | Not Yet Started | 2026-10-07
| 5th Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 6 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 6 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 6 verticals | Not Yet Started | 2026-10-07
| 6th Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 7 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 7 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 7 verticals | Not Yet Started | 2026-10-07
| 7th Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 8 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 8 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 8 verticals | Not Yet Started | 2026-10-07
| 8th Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 9 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 9 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 9 verticals | Not Yet Started | 2026-10-07
| 9th Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 10 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 10 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 10 verticals | Not Yet Started | 2026-10-07
| 10th Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 11 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 11 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 11 verticals | Not Yet Started | 2026-10-07
| 11th Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 12 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 12 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 12 verticals | Not Yet Started | 2026-10-07
| 12th Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 13 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 13 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 13 verticals | Not Yet Started | 2026-10-07
| 13th Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 14 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 14 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 14 verticals | Not Yet Started | 2026-10-07
| 14th Floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 15 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 15 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 15 verticals | Not Yet Started | 2026-10-07
| 15th floor slab (Residential) | Not Yet Started | 2026-10-07
| Columns (Residential) lift - 16 verticals | Not Yet Started | 2026-10-07
| Shear walls (Residential) lift - 16 verticals | Not Yet Started | 2026-10-07
| Cmu walls lift - 16 verticals | Not Yet Started | 2026-10-07
| Roof Floor slab (Residential) | Not Yet Started | 2026-10-07
| Parapet walls (Residential) verticals | Not Yet Started | 2026-10-07
|  | Not Yet Started | 2026-10-07
| Foundations (Garage) | Not Yet Started | 2026-10-07
| Slab on grade (Garage) | Not Yet Started | 2026-10-07
| Columns (Garage) | Not Yet Started | 2026-10-07
| Shear walls (Garage) | Not Yet Started | 2026-10-07
| 2nd Floor slab (Garage) | Not Yet Started | 2026-10-07
| 3rd Floor slab (Garage) | Not Yet Started | 2026-10-07
| 4th Floor slab (Garage) | Not Yet Started | 2026-10-07
| 5th Floor slab (Garage) | Not Yet Started | 2026-10-07
| 6th Floor slab (Garage) | Not Yet Started | 2026-10-07
6007 Le Lac (Furing residence) | Foundations & Walls (scope added) | Completed | 05-16-2026 | Pradeep | Nanaji
| Cabana slab on grade | Completed | 06-25-2026
90 Stingaree | Slab on grade | Completed | 2026-05-06 | Siva Kumar
| Lift - 1 verticals and beams | Inprogress | 2026-03-07 | Praveena
O.B. (Scattered Lots) | Foundaitons & sog. | Completed | 05-18-2026 | Lokesh | ESWAR
| Lift - 1 verticals and beams | Completed | 05-23-2026
840 Denery Ln. Residence | Foundaitons & Slab on grade | Completed | 05-30-2026 | eswar/siav kumar | ESWAR
| Lift - 1 verticals and bond beams | Completed | 05-30-2026 | siav kumar | ESWAR
| 2nd floor slab & beams | Inprogress | 2026-03-07 | Sridevi
| Lift - 2 verticals and bond beams | Not Yet Started | 2026-03-07 | Praveena
| Roof beams | Not Yet Started | 2026-03-07 | Praveena/Sridevi
Nuvo | Bldg. Type 1 (A, C, D & G) | Not Yet Started | 2026-10-07
| Foundations and slab on grade | Completed | 2026-12-06 | Siva Kumar
| Lift - 1 verticals and beams | Completed | 06-13-2026 | Sridevi
| 2nd Flr. Thru 2nd lift & 2nd floor beams | Inprogress | 2026-03-07 | Siva Kumar/sridevi
| 3rd Flr. Thru 3rd lift & 3rd floor beams | Not Yet Started | 2026-03-07 | Nanaji/Sridevi
| 4th Flr. Thru Roof & Abv Roof beams | Inprogress | 2026-03-07 | Lokesh/Sridevi
|  | Not Yet Started | 2026-10-07
| Bldg. Type 2 (E & H) | Not Yet Started | 2026-10-07
| Foundations and slab on grade | Completed | 2026-03-07 | Lokesh
| Lift - 1 verticals and beams | Completed | 06-15-2026 | Siva Kumar
| 2nd Flr. Thru 2nd lift & 2nd floor beams | Not Yet Started | 2026-03-07 | Lokesh
| 3rd Flr. Thru 3rd lift & 3rd floor beams | Not Yet Started | 2026-03-07 | Lokesh
| 4th Flr. Thru Roof & Abv Roof beams | Not Yet Started | 2026-03-07 | Lokesh
|  | Not Yet Started | 2026-10-07
| Bldg. Type 3 (B & F) | Not Yet Started | 2026-10-07
| Elevator Pits & Stairs, Bg Thru 1st lift | Inprogress | 06-16-2026 | Lokesh
| 2nd Flr. Thru 2nd lift & 2nd floor beams | Not Yet Started | 2026-03-07 | Siva Kumar
| 3rd Flr. Thru 3rd lift & 3rd floor beams | Not Yet Started | 2026-03-07 | Lokesh/Siva Kumar
| 4th Flr. Thru Roof & Abv Roof beams | Not Yet Started | 2026-03-07 | Lokesh/Siva Kumar
|  | Not Yet Started | 2026-10-07
| Bus Shelter - Footings | Not Yet Started | 2026-10-07
| Bg Thru 1st lift | Not Yet Started | 07-24-2026 | Pradeep
|  | Not Yet Started | 07-24-2026
| Clubhouse | Not Yet Started | 07-24-2026
| Bg Thru Abv Roof beams | Completed | 2026-05-06 | Siva Kumar
|  | Not Yet Started | 07-24-2026
| Garage Type 1 | Not Yet Started | 07-24-2026
| Bg Thru Abv Roof beams | Inprogress | 2026-10-07 | Pavan sai
|  | Not Yet Started | 07-24-2026
| Garage Type 2 | Not Yet Started | 07-24-2026
| Bg Thru Abv Roof beams | Inprogress | 2026-10-07 | Pradeep
|  | Not Yet Started | 07-24-2026
| Mail Kiosk - Slab on grade | Not Yet Started | 07-24-2026
| Slab on grade | Inprogress | 2026-10-07 | Pradeep
|  | Not Yet Started | 07-24-2026
| Trash Compactor | Not Yet Started | 07-24-2026
| Bg Thru 1st lift | Not Yet Started | 2026-10-07 | Pradeep
|  | Not Yet Started | 07-24-2026
| Pool Pavilion | Not Yet Started | 07-24-2026
| Bg Thru Roof beams | Not Yet Started | 07-17-2026 | Pradeep
|  | Not Yet Started | 07-24-2026
| Raised Planters | Not Yet Started | 07-24-2026
| Bg Thru 1st lift | Not Yet Started | 2026-10-07 | Pradeep
|  | Not Yet Started | 07-24-2026
| BBQ Station | Not Yet Started | 07-24-2026
| Bg Thru Roof beams | Not Yet Started | 07-17-2026 | Pradeep
|  | Not Yet Started | 07-24-2026
| Cabana Footings | Not Yet Started | 07-24-2026
| Bg Thru 1st lift | Not Yet Started | 07-17-2026 | Pradeep
|  | Not Yet Started | 07-24-2026
| Trellis Footings | Not Yet Started | 07-24-2026
| Bg Thru 1st lift | Not Yet Started | 07-17-2026 | Pradeep
|  | Not Yet Started | 07-24-2026
| Retaining Wall | Completed | 2026-12-06 | Pradeep | Nanaji
| Bg Thru 1st lift | Completed | 2026-12-06 | Pradeep
The Syed Residence | Foundations & Slab on grade | Completed | 2026-06-05 | Eswar
| Lift - 1 verticals and beams | Not Yet Started | 2026-03-07 | Jagadeesh
| Lift - 2 verticals and beams | Not Yet Started | 2026-03-07 | Nanaji
810 S Swinton Ave Residence | Foundations and slab on grade | Inprogress | 2026-09-06 | Praveena
| Lift - 1 verticals and beams | Not Yet Started | 2026-03-07
| Lift - 2 verticals and beams | Not Yet Started | 2026-03-07
Custom Residence (134 Worth CTN) | Foundations | Completed | 06-13-2026 | Praveena
| Slab on grade | Completed | 06-13-2026 | Vaishnavi
| Lift - 1 verticals and beams | Not Yet Started | 2026-10-07 | Jagadeesh
| Lift - 2 verticals and beams | Not Yet Started | 2026-10-07
Rancano | Foundations & slab on grade | Completed | 2026-11-06 | Eswar
| Lift - 1 verticals and Roof beams | Completed | 06-17-2026 | Sridevi | Nanaji
799 Park Drive | Foundations & Slab on grade | Completed | 2026-06-16 | Pradeep | Nanaji
| Lift - 1 verticals and beams | Completed | 2026-06-20 | Pradeep | Chandra mouli
| Lift - 2 verticals and beams | Completed | 2026-06-26 | Pradeep | Chandra mouli
Chateau De La Duchess (925 Hillsboro) | Entry Garages foundations and slab on grade | Inprogress | 2026-03-07
| Entry Garages lift - 1 verticals and beams | Not Yet Started | 2026-03-07
| Entry Garages lift - 2 verticals and beams | Not Yet Started | 2026-03-07
Masucci Residence | Foundations & slab on grade | Completed | 06-26-2026
| Lift - 1 verticals and beams | Inprogress | 2026-03-07
| 2nd floor slab and beams | Inprogress | 2026-03-07
| Lift - 2 verticals and beams | Inprogress | 2026-03-07
The Bueller family | Foundations & slab on grade | Completed | 06-26-2026
| Lift - 1 verticals and beams | Completed | 06-26-2026
SPOTLOT 28810 SW 207 AVE | Foundations & slab on grade | Completed | 06-26-2026
| Lift - 1 verticals and beams | Completed | 06-26-2026
Broken Sound Club | Foundations & slab on grade | Completed | 06-23-2026
| Lift - 1 verticals and beams | Completed | 06-23-2026
128 Worth CT N | Foundations & slab on grade | Not Yet Started | 07-24-2026
| Lift - 1 verticals and beams | Not Yet Started | 07-24-2026
| Lift - 2 verticals and beams | Not Yet Started | 07-24-2026
2235 Mangolia Drive | Foundations & slab on grade | Not Yet Started | 07-24-2026
| Lift - 1 verticals and beams | Not Yet Started | 07-24-2026
| Lift - 2 verticals and beams | Not Yet Started | 07-24-2026