## White Cap Work Schedule
White Cap
PROJECT NAME | SCOPE | COMPONENTS OF WORK | STATUS | CLIENT SUB. DATE | DET. WT. | DETAILER | CHECKER
Felies Residence | CIP&CMU | Foundations and slab on grade | Completed | 2026-12-01 | 2.8 | Praveena | Chandra Mouli
|  | Lift - 1 Verticals & beams, 2nd floor slab & beams | Completed | 01-29-2026 | 6.354 | Praveena | Anji Reddy
|  | Lift - 2 verticals & beams, Roof slab & beams | Completed | 2026-06-02 | 3.835 | Praveena | Anji Reddy
Valencia Del Mar Pickleball | CIP&CMU | Foundations and slab on grade | Completed | 01-19-2026 | 6.057 | Danush | Kameshwari
|  | Lift - 1 Verticals & beams | Completed | 01-23-2026 | 8.112 | Danush | Kameshwari
|  | Lift - 2 Verticals & beams | Completed | 01-23-2026 | 4.434 | Danush | Kameshwari
|  | Double Dumpster Enclosure | Completed | 02-18-2026 | 0.251 | Praveena | Kameshwari
|  | Single Dumpster Enclosure | Completed | 02-18-2026 | 0.197 | Praveena | Kameshwari
|  | Mail Pavilion | Completed | 02-18-2026 | 1.661 | Praveena | Kameshwari
|  | Monument sign | Completed | 2026-01-06 | 0.131 | Pradeep | Nanaji
City of temple terrace-fire station #01 | CIP&CMU | Foundations | Completed | 01-19-2026 | 13.923 | Swathi | Chandra Mouli
|  | Slab on grade | Completed | 02-14-2026 | 0.516 | Sri Lalitha | Kameshwari
|  | Lift - 1 Verticals, 2nd floor slab & beams | Completed | 02-25-2026 | 9.701 | Sri Lalitha | Kameshwari
|  | Lift - 2 Verticals and Roof beams | Completed | 02-25-2026 | 9.489 | Sri Lalitha | Kameshwari
228 Rutland | CIP&CMU | Foundations and slab on grade | Completed | 01-13-2026 | 2.598 | Allu Sai | Kameshwari
|  | Lift - 1 Verticals and Bond beams | Completed | 2026-03-02 | 2.152 | Allu Sai | Kameshwari
|  | Low Roof beams & Slab | Completed | 02-19-2026 | 2.587 | Vaishnavi | Kameshwari
|  | Lift - 2 Verticals, Bond beams & Roof beams | Completed | 2026-02-03 | 1.643 | Siva Kumar | Kameshwari
Palmetto Lakes Industrial Park | CIP&CMU | Foundations and slab on grade | Completed | 01-14-26 | 5.041 | Sri Lalitha | Chandra Mouli
|  | Lift - 1 walls, Columns & Beams | Completed | 01-27-26 | 6.914 | Sri Lalitha | Chandra Mouli
|  | Lift - 2 walls, Columns & Beams | Completed | 01-27-26 | 6.722 | Sri Lalitha | Chandra Mouli
Frenchman's Creek Operations Center | CIP&CMU | Building - A Foundations & slab on grade | Completed | 01-26-2026 | 16.64 | Pradeep | Anji Reddy
|  | Building - B Foundations & slab on grade | Completed | 01-21-2026 | 5.301 | Pradeep | Narayana
|  | Building - C Foundations & slab on grade | Completed | 01-21-2026 | 17.953 | Praveena | Anji Reddy
|  | Building - D Foundations & slab on grade | Completed | 01-26-2026 | 0.675 | Pradeep | Anji Reddy
|  | Building - E Foundations & slab on grade | Completed | 01-28-2026 | 7.23 | Pradeep | Anji Reddy
|  | Building - F Foundations & slab on grade | Completed | 01-31-2026 | 7.875 | Pradeep | Anji Reddy
Miami Shores Residence (R+R bluenest) | CIP&CMU | Foundations | Completed | 01-27-2026 | 9.474 | Swathi | Chandra Mouli
|  | Slab on grade | Completed | 2026-03-03 | 1.208 | Praveena | Chandra Mouli
|  | Lift - 1 Verticals, 2nd floor slab & beams | Completed | 2026-09-03 | 15.747 | Jagadeesh | Chandra Mouli
|  | Lift - 2 Verticals and Roof beams | Completed | 03-20-2026 | 2.904 | Praveena | Kameshwari
|  | Updated drawings received (Cantilever Beams) | Completed | 2026-06-26 | 0.619 | Praveena | eswar
Licata Residence 2726 Appaloosa trail | CIP&CMU | Foundations & slab on grade | Completed | 01-23-2026 | 0.764 | Swathi | Anji Reddy
|  | Lift - 1 Verticals and Roof beams | Completed | 01-23-2026 | 1.818 | Swathi | Anji Reddy
4669 S. Flagler Dr | CIP&CMU | Footings & Stem Walls | Completed | 2026-04-02 | 5.907 | Vaishnavi | Chandra Mouli
|  | Stem wall & Slab on grade | Completed | 02-20-2026 | 1.335 | Vaishnavi | Chandra Mouli
|  | Lift - 1 Verticals, 2nd floor slab & beams | Completed | 2026-04-03 | 27.935 | Vaishnavi | Chandra Mouli
|  | Lift - 2 Verticals & Roof beams | Completed | 2026-06-03 | 2.141 | Vaishnavi | Chandra Mouli
Harrison Residence | CIP&CMU | Foundations and slab on grade | Completed | 2026-05-02 | 0.256 | Sri Lalitha | Chandra Mouli
|  | Lift - 1 Verticals and Beams | Completed | 2026-02-03 | 0.834 | Sri Lalitha | Chandra Mouli
PBIA - Revenue Control Building | CIP&CMU | Foundations and slab on grade | Completed | 02-14-2026 | 11.285 | Praveena | Anji Reddy
|  | Lift - 1 Verticals and Roof beams | Completed | 02-19-2026 | 6.364 | Praveena | Anji Reddy
127 EL Bravo Way | CIP&CMU | Basement Foundations | Completed | 02-17-2026 | 13.887 | Danush | Anji Reddy
|  | Basement Walls | Completed | 02-21-2026 | 5.577 | Danush | Anji Reddy
|  | Level - 1 Foundations | Completed | 2026-12-03 | 22.202 | Danush | Chandra Mouli
|  | Lift - 1 Verticals | Completed | 03-16-2026 | 4.159 | Danush | Chandra Mouli
|  | Lift - 1 Beams | Completed | 03-28-2026 | 10.828 | Danush | Chandra Mouli
|  | Lift - 2 Verticals | Completed | 03-31-2026 | 1.709 | Danush | Chandra Mouli
|  | Roof beams | Completed | 03-31-2026 | 1.544 | Danush | Chandra Mouli
Blue Water Cove 6 | CIP&CMU | Foundations & slab on grade | Completed | 02-25-2026 | 12.306 | Allu Sai/Nanaji
|  | Lift-1 & 2 Verticals, 2nd floor slab, & Roof beams | Completed | 03-18-2026 | 6.168 | Allu Sai | Chandra Mouli
|  | Site walls | Inprogress | 07-29-2026 |  | Praveena
1050 N Lake way | CIP&CMU | Foundations and slab on grade | Completed | 02-17-2026 | 3.991 | Lokesh Reddy/Nanaji | Narayana
|  | Lift - 1 Verticals, 2nd floor slab & beams | Completed | 02-23-2026 | 9.309 | Lokesh Reddy | Kameshwari
|  | Lift - 2 Verticals & Roof beams | Completed | 03-13-2026 | 2.787 | Praveena | Kameshwari
143 Reef Road | CIP&CMU | Foundations and slab on grade | Completed | 03-13-2026 | 16.785 | Kunal | Chandra Mouli
|  | Lift - 1 Verticals | Completed | 05-15-2026 | 1.331 | Kunal | NANAJI
|  | 2nd floor slab & Beams | Completed | 05-15-2026 | 3.234 | Kunal | NANAJI
|  | Lift-2 verticals & Roof beams | Completed | 06-20-2026 |  | Kunal
Cutler Bay SHS | CIP&CMU | Foundations and slab on grade | Completed | 2026-04-03 | 2.305 | Swathi | Rds
|  | Lift - 1 Verticals and beams | Completed | 2026-04-03 | 2.027 | Swathi | Rds
|  | Lift - 2 Verticals and Low Roof slab & beams | Completed | 2026-04-03 | 1.242 | Swathi | Rds
|  | Lift - 3 Verticals and High Roof slab & beams | Completed | 2026-04-03 | 0.786 | Swathi | Rds
Ackerman Residence | CIP&CMU | Foundations & slab on grade | Completed | 2026-03-03 |  | Lokesh Reddy
|  | Lift - 1 Verticals, 2nd floor slab & beams | Completed | 03-21-2026 | 4.853 | Lokesh Reddy | Kameshwari
|  | Lift - 2 Verticals & Roof beams | Completed | 2026-02-04 | 1.285 | Lokesh Reddy | Kameshwari
Blue Water Cove 3 | CIP&CMU | Foundations & slab on grade | Completed | 2026-06-03 | 2.592 | Vaishnavi | Kameshwari
|  | Lift - 1 Verticals and Roof beams | Completed | 03-16-2026 | 4.562 | Vaishnavi | Kameshwari
BOKOR 432 SUNSHINE BLVD | CIP&CMU | Foundations and slab on grade | Completed | 2026-07-03 | 5.062 | Eswar | Eswar
|  | Lift - 1 Verticals, 2nd floor slab & beams | Completed | 03-13-2026 | 3.298 | Vaishnavi | Chandra Mouli
|  | Lift - 2 Verticals and Roof beams | Completed | 03-13-2026 | 1.695 | Vaishnavi | Chandra Mouli
Cloyd | CIP&CMU | Foundations and slab on grade | Completed | 03-11.-2026 | 2.267 | Vaishnavi | Chandra Mouli
|  | Lift - 1 Verticals and beams | Completed | 03-20.-2026 | 1.214 | Vaishnavi | Chandra Mouli
|  | Lift - 2 Verticals and beams | Completed | 03-20.-2026 | 0.835 | Vaishnavi | Chandra Mouli
6017 Le Lac Road (Weiner Residence) | CIP&CMU | Foundations and slab on grade (East Garage) | Completed | 03-21-2026 | 0.679 | Sri lalitha | Kameshwari
|  | Lift - 1 Verticals and Roof beams (East Garage) | Completed | 03-26-2026 | 1.643 | Praveena | Kameshwari
|  | Foundations and slab on grade (Main Building) | Completed | 03-25-2026 | 2.64 | Praveena | Kameshwari
|  | Lift - 1 Verticals, 2nd floor slab and beams (Main Building) | Completed | 2026-01-05 | 5.594 | Sridevi/Vaishnavi
|  | Lift - 2 Verticals and roof beams (Main Building) | Completed | 05-28-2026 | 4.782 | Vaishnavi | Eswar
|  | Foundations and slab on grade (2-story residence) | Completed | 04-21-2026 | 4.162 | Praveena | Chandra Mouli
|  | Lift - 1 Verticals, 2nd floor slab and beams (2-story residence) | Completed | 05-19-2026 | 12.373 | Vaishnavi | NANAJI
|  | Lift - 2 Verticals and roof beams (2-story residence) | Completed | 2026-05-06 | 2.935 | Vaishnavi
|  | Foundations and slab on grade (site work) | Completed | 2026-04-04 | 1.37 | Sri lalitha | Kameshwari
Bluewater cove 11 | CIP&CMU | Foundations and slab on grade | Completed | 03-24-2026 | 3.041 | Vaishnavi
|  | Lift - 1 Verticals and Roof beams | Completed | 2026-01-05 | 4.261 | Vaishnavi
Bluewater cove 9 | CIP&CMU | Foundations and slab on grade | Completed | 03-31-2026 | 15.362 | Vaishnavi | Kameshwari
|  | Lift - 1 Verticals and Roof Beams | Completed | 2026-01-05 | 5.012 | Nanaji/pradeep
164 Seminole | CIP&CMU | Foundations | Completed | 2026-08-04 | 2.269 | Siva kumar | Chandra Mouli
|  | Slab on grade | Completed | 05-18-2026 | 9.296 | Siva kumar | NANAJI
Roy & Shelley Silverman | CIP&CMU | Foundations and slab on grade | Completed | 2026-10-04 | 3.789 | Danush | Chandra Mouli
|  | Lift - 1 Verticals | Completed | 2026-04-05 | 3.191 | Danush | Chandra Mouli
|  | Lift - 1 slab & Beams | Completed | 2026-04-05 | 5.85 | Nanaji/Sridevi
|  | Lift - 2 Verticals & Roof beams | Completed | 2026-11-05 | 2.95 | Vaishnavi/Shiva | NANAJI
50 SE OLIVE | CIP&CMU | Foundations & columns | Completed | 2026-08-04 | 0.674 | Danush | Chandra Mouli
|  | Bond beams | Completed | 2026-08-04 | 0.174 | Danush | Chandra Mouli
Valencia Del Mar Clubhouse | CIP&CMU | Foundations and slab on grade | Completed | 2026-06-04 | 22.524 | Vaishnavi | Chandra Mouli
|  | Lift - 1 Verticals and beams (pour-1) | Completed | 2026-12-05 | 5.781 | Vaishnavi/Sridevi | NANAJI
|  | Lift - 1 Verticals and beams (pour-2) | Completed | 05-16-2026 | 10.773 | Sridevi | NANAJI
|  | Lift - 1 Verticals and beams (pour-3) & (pour-4) | Completed | 05-27-2026 | 10.014 | Sridevi | NANAJI
|  | Lift - 2 Verticals and beams (pour-1) | Completed | 05-29-2026 | 4.784 | Sridevi
|  | Lift - 2 Verticals and beams (pour-2) | Completed | 2026-03-06 | 3.643 | Sridevi
|  | Lift - 2 Verticals and beams (pour-3) | Completed | 2026-12-06 | 14.818 | Sridevi | NANAJI
|  | Monument walls | Completed | 04-27-2026 | 0.576 | Vaishnavi | Chandra Mouli
|  | Tennis & Bocce Courts Restrooms | Completed | 2026-09-05 | 0.123 | Eswar
910 S Ocean | CIP&CMU | Basement Foundations | Completed | 2026-08-04 |  | Sridevi | Narayana
|  | Lift - 1 Verticals & roof beams | Completed | 2026-10-04 |  | Sridevi | Narayana
|  | Retaining wall & Planter walls & stairs | Completed | 04-21-2026 |  | Sridevi | Narayana
Burns Residence | CIP&CMU | Foundations and slab on grade | Completed | 2026-06-04 | 7.45 | Praveena | Chandra Mouli
|  | Lift - 1 Verticals and Beams | Completed | 05-21-2026 | 7.962 | Siva kumar | NANAJI
|  | Lift - 2 Verticals and beams | Completed | 05-21-2026 | 0.175 | Siva kumar | NANAJI
5940 North Bay Road (NEW SINGLE FAMILY RESIDENCE) | CIP&CMU | Foundations | Completed | 2026-08-04 | 140.399 | Balaram/Jagadeesh | Chandra Mouli
320 S atlantic Drive | CIP&CMU | Foundations | Completed | 04-18-2026 | 6.817 | Sridevi | Chandra Mouli/NNJ
|  | Stem wall & Slab on grade | Completed | 2026-01-05 | 4.869 | Sridevi | Chandra Mouli/NNJ
|  | Lift - 1 Verticals, 2nd Floor slab & beams | Completed | 06-13-2026 | 15.352 | Vaishnavi | Chandra Mouli
|  | Lift - 2 Verticals and Roof beams | Completed | 06-18-2026 |  | Vaishnavi | NANAJI
Custom Residence (515 lido drive) | CIP&CMU | Foundations and slab on grade | Completed | 04-24-2026 | 22.418 | Vaishnavi | Chandra Mouli
|  | Lift - 1 Verticals | Completed | 2026-04-06 | 4.206 | Siva kumar | NANAJI
|  | 2nd floor slab & beams | Completed | 06-18-2026 | 11.165 | Jagadeesh | NANAJI
|  | Lift - 2 Verticals & Roof beams | Completed | 06-18-2026 | 3.221 | Balaram | NANAJI
Jandrews Residence | CIP&CMU | Foundations and slab on grade | Completed | 04-23-2026 | 16.272 | Praveena | Chandra Mouli
|  | Lift - 1 Verticals and beams | Completed | 2026-05-16 | 10.859 | Lokesh Reddy
|  | Lift - 2 Verticals and beams | Completed | 2026-06-03 |  | Lokesh Reddy
6024 Lelac Rd | CIP&CMU | Foundations and slab on grade | Completed | 2026-10-04 | 1.04 | Vaishnavi | Chandra Mouli
|  | Lift - 1 Verticals, loft floor slab & beams | Completed | 2026-10-04 | 1.18 | Vaishnavi | Chandra Mouli
|  | Lift - 2 Verticals and roof beams | Completed | 2026-10-04 | 1.26 | Vaishnavi | Chandra Mouli
|  | Foundations & slab on grade (Summer kitchen) | Completed | 04-22-2026 | 1.02 | Sridevi | NANAJI
|  | Lift - 1 Verticals, slab and beams (Summer kitchen) | Completed | 04-23-2026 | 1.69 | Sridevi
5900 Powerline Garag | CIP&CMU | Grade beams | Completed | 04-20-2026 | 16.4 | Sri lalitha
|  | Slab on grade, Lift - 1 Verticals and Roof beams | Completed | 2026-09-05 | 26.761 | Pradeep | NANAJI
South Florida Jewish Cemetery | CIP&CMU | Foundations and slab on grade | Completed | 2026-05-05 | 1.661 | Vaishnavi | Eswar
|  | Lift - 1 Verticals and Roof Beams | Completed | 05-22-2026 | 2.453 | Pradeep | NANAJI
1820 S Federal Hwy - Fifth Third Bank | CIP&CMU | Foundations and slab on grade | Completed | 04-24-2026 | 2.762 | Pradeep | Narayana
|  | Lift - 1 Verticals and Roof beams | Completed | 04-24-2026 | 1.259 | Pradeep | Narayana
20 Hudson Ave | CIP&CMU | Foundations & slab on grade | Completed | 05/26/26 |  | Eswar
|  | Lift - 1 Verticals and Beams | Completed | 06-18-2026 |  | Praveena | Kameshwari
|  | Lift - 2 Verticals and Beams | Completed | 06-18-2026 |  | Swathi | Kameshwari
South Rd Office Building E | CIP&CMU | Foundations and slab on grade | Completed | 04-24-2026 | 1.577 | Vaishnavi | NANAJI
|  | Lift - 1 Verticals and beams | Completed | 2026-01-05 | 4.107 | Lokesh/vaishnavi
Baig Residence | CIP | 3rd Floor tie beams | Completed | 2026-05-06 | 0.978 | Lokesh
|  | 2nd Floor slab | Completed | 2026-05-07 |  | Lokesh
SW Ranches | CIP | Lower Roof Deck | Completed | 2026-05-15 | 29.74 | Eswar
|  | Lift - 1 verticals | Completed | 2026-06-01 | 2.45 | Pradeep | NANAJI
2651 Southcast 10th court | CIP | Pool deck slab and beams | Completed | 2026-09-05 |  | Siva kumar
Country inn Pet Resort | CIP&CMU | Foundations and slab on grade | Completed | 05-22-2026 | 3.691 | Vaishnavi | NANAJI
|  | Lift - 1 verticals and beams | Completed | 2026-05-06 |  | Vaishnavi
2960 Greenbriair | CIP&CMU | Foundations | Completed | 2026-05-06 | 20.784 | Lokesh Reddy
|  | Slab on grade | Completed | 06-19-2026 |  | Sri Lalitha | NANAJI
|  | Lift - 1 verticals, beams and 2nd floor slab | Completed | 2026-02-07 |  | Sridevi
|  | Lift - 2 verticals and roof beams | Completed | 07-13-2026 |  | Praveena
Gallery at Somi Parc Phase 1 | CIP&CMU | Foundations (Residential) part - 1 | Completed | 06-17-2026 |  | Eswar/Nanaji
|  | Foundations (Residential) part - 2 | Completed | 06-18-2026 |  | Eswar/Nanaji
|  | Slab on grade (Residential) part - 1 & 2 | Completed | 2026-03-07 |  | Eswar
|  | Columns (Residential) lift - 1 to Roof verticals | Completed | 07-23-2026 |  | Eswar
|  | Shear walls (Residential) lift - 1 to Roof verticals | Completed | 07-17-2026 |  | Eswar
|  | 2nd Floor slab (Residential) | Not Yet Started |  |  | Siva kumar
|  | Cmu walls lift - 1 verticals | Not Yet Started |  |  | Sridevi
|  | 3rd Floor slab (Residential) | Not Yet Started
Cmu walls lift - 3 verticals
|  | 3rd Floor slab (Residential) | Not Yet Started
Cmu walls lift - 4 verticals
|  | 4th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 5 verticals
|  | 5th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 6 verticals
|  | 6th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 7 verticals
|  | 7th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 8 verticals
|  | 8th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 9 verticals
|  | 9th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 10 verticals
|  | 10th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 11 verticals
|  | 11th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 12 verticals
|  | 12th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 13 verticals
|  | 13th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 14 verticals
|  | 14th Floor slab (Residential) | Not Yet Started
Cmu walls lift - 15 verticals
|  | 15th floor slab (Residential) | Not Yet Started
Cmu walls lift - 16 verticals
|  | Roof Floor slab (Residential) | Not Yet Started
|  | Parapet walls (Residential) verticals | Not Yet Started
|  | Foundations (Garage) | Not Yet Started
|  | Slab on grade (Garage) | Not Yet Started
|  | Columns (Garage) | Not Yet Started
|  | Shear walls (Garage) | Not Yet Started
|  | 2nd Floor slab (Garage) | Not Yet Started
|  | 3rd Floor slab (Garage) | Not Yet Started
|  | 4th Floor slab (Garage) | Not Yet Started
|  | 5th Floor slab (Garage) | Not Yet Started
|  | 6th Floor slab (Garage) | Not Yet Started
6007 Le Lac (Furing residence) | CIP | Foundations & Walls (scope added) | Completed | 05-16-2026 | 1.513 | Pradeep | NANAJI
|  | Cabana slab on grade | Completed | 06-25-2026 |  | Pradeep
|  | Cabana Columns & Beams | Completed | 07-21-2026 |  | Pradeep
90 Stingaree | CIP & CMU | Slab on grade | Completed | 2026-05-06 |  | siva kumar
|  | Lift - 1 verticals and beams | Completed | 2026-06-07 |  | Praveena
O.B. (Scattered Lots) | CIP & CMU | Foundaitons & sog. | Completed | 05-18-2026 | 0.725 | Lokesh Reddy | ESWAR
|  | Lift - 1 verticals and beams | Completed | 05-23-2026 |  | Lokesh Reddy
840 Denery Ln. Residence |  | Foundaitons & Slab on grade | Completed | 07-27-2026 |  | Out source (kumaran)
|  | Lift - 1 verticals and bond beams | Completed | 07-27-2026 |  | Out source (kumaran)
|  | 2nd floor slab & beams | Completed | 07-27-2026 |  | Out source (kumaran)
|  | Lift - 2 verticals and bond beams | Completed | 07-27-2026 |  | Out source (kumaran)
|  | Roof beams | Completed | 07-27-2026 |  | Out source (kumaran)
Nuvo | CIP & CMU | Bldg. Type 1 (A, C, D & G)
|  | Foundations and slab on grade | Completed | 2026-12-06 |  | siva kumar
|  | Lift - 1 verticals and beams | Completed | 06-13-2026 |  | Sridevi
|  | 2nd floor slab and beams | Completed | 2026-03-07 |  | siva kumar/sridevi
|  | Lift - 2 verticals and beams | Completed | 2026-03-07 |  | Nanaji/Sridevi
|  | 3rd floor slab and beams | Completed | 2026-03-07 |  | Lokesh reddy/Sridevi
|  | Lift - 3 verticals and beams | Completed | 2026-03-07
|  | 4th floor slab and beams | Completed | 2026-03-07
|  | Lift - 4 verticals and beams | Completed | 2026-03-07
|  | Roof slas, beams & parapet walls | Completed | 2026-03-07
Bldg. Type 2 (E & H)
|  | Foundations and slab on grade | Completed | 2026-03-07 |  | Lokesh Reddy
|  | Lift - 1 verticals and beams | Completed | 06-15-2026 |  | siva kumar
|  | 2nd floor slab and beams | Completed | 2026-10-07 |  | Lokesh Reddy
|  | Lift - 2 verticals and beams | Completed | 2026-10-07 |  | Lokesh Reddy
|  | 3rd floor slab and beams | Completed | 2026-10-07 |  | Lokesh Reddy
|  | Lift - 3 verticals and beams | Completed | 2026-10-07
|  | 4th floor slab and beams | Completed | 2026-10-07
|  | Lift - 4 verticals and beams | Completed | 2026-10-07
|  | Roof slas, beams & parapet walls | Completed
Bldg. Type 3 (B & F)
|  | Foundations and slab on grade | Completed | 2026-10-07 |  | Lokesh Reddy
|  | Lift - 1 verticals and beams | Completed | 2026-10-07 |  | siva kumar
|  | 2nd floor slab and beams | Completed | 2026-10-07 |  | Lokesh Reddy/Siva kumar
|  | Lift - 2 verticals and beams | Completed | 2026-10-07 |  | Lokesh Reddy/Siva kumar
|  | 3rd floor slab and beams | Completed | 2026-10-07
|  | Lift - 3 verticals and beams | Completed | 2026-10-07
|  | 4th floor slab and beams | Completed | 2026-10-07
|  | Lift - 4 verticals and beams | Completed | 2026-10-07
|  | Roof slas, beams & parapet walls | Completed | 2026-10-07
Bus Shelter - Footings
|  | Bg Thru 1st lift | Not Yet Started |  |  | Pradeep
Clubhouse
|  | Bg Thru Abv Roof beams | Completed | 2026-05-06 |  | siva kumar
Garage Type 1
|  | Bg Thru Abv Roof beams | Completed | 07-31-2026 |  | Pavan sai
Garage Type 2
|  | Bg Thru Abv Roof beams | Inprogress | 2026-03-08 |  | Pavan sai
Mail Kiosk - Slab on grade
|  | Slab on grade | Not Yet Started |  |  | Pradeep
Trash Compactor
|  | Bg Thru 1st lift | Completed | 07-31-2026 |  | Pavan sai
Pool Pavilion
|  | Bg Thru Roof beams | Inprogress | 2026-03-08 |  | Pavan sai
Raised Planters
|  | Bg Thru 1st lift | Not Yet Started |  |  | Pradeep
BBQ Station
|  | Bg Thru Roof beams | Not Yet Started |  |  | Pradeep
Cabana Footings
|  | Bg Thru 1st lift | Inprogress |  |  | Pradeep
Trellis Footings
|  | Bg Thru 1st lift | Inprogress |  |  | Pradeep
|  | Retaining Wall | Completed | 2026-12-06 | 29.997 | Pradeep | NANAJI
|  | Bg Thru 1st lift | Completed | 2026-12-06 |  | Pradeep
The Syed Residence | CIP & CMU | Foundations & Slab on grade | Completed | 2026-06-05 |  | Eswar
|  | Lift - 1 verticals and beams | Completed | 07-13-2026 |  | Lalitha
|  | Lift - 2 verticals and beams | Completed | 07-21-2026 |  | Nanaji
810 S Swinton Ave Residence | CIP & CMU | Foundations and slab on grade | Completed | 2026-09-06 |  | Praveena
|  | Lift - 1 verticals and beams | Completed | 07-21-2026 |  | Praveena
|  | Lift - 2 verticals and beams | Completed | 07-31-2026 |  | Praveena
Custom Residence (134 Worth CTN) | CIP & CMU | Foundations | Completed | 06-13-2026 |  | Praveena
|  | Slab on grade | Completed | 06-13-2026 |  | Vaishnavi
|  | Lift - 1 verticals and beams | Completed | 07-17-2026 |  | Jagadeesh
|  | Lift - 2 verticals and beams | Completed | 07-17-2026
Rancano | CIP & CMU | Foundations & slab on grade | Completed | 2026-11-06 | 6.108 | Eswar
|  | Lift - 1 verticals and Roof beams | Completed | 06-17-2026 | 1.66 | Sridevi | NANAJI
799 Park Drive | CIP & CMU | Foundations & Slab on grade | Completed | 2026-06-16 | 2.264 | Pradeep | Nanaji
|  | Lift - 1 verticals and beams | Completed | 2026-06-20 | 3.621 | Pradeep | Chandra mouli
|  | Lift - 2 verticals and beams | Completed | 2026-06-26 | 1.412 | Pradeep | Chandra mouli
Chateau De La Duchess (925 Hillsboro) | CIP & CMU | Entry Garages foundations and slab on grade | Completed | 07-23-2026 |  | Pradeep
|  | Entry Garages lift - 1 verticals and beams | Completed | 07-23-2026 |  | Pradeep
|  | Entry Garages lift - 2 verticals and beams | Completed | 07-23-2026 |  | Pradeep
Masucci Residence | CIP & CMU | Foundations & slab on grade | Completed | 06-26-2026
|  | Lift - 1 verticals and beams | Completed | 2026-09-07 |  | Out Source (Kumaran)
|  | 2nd floor slab and beams | Completed | 2026-09-07 |  | Out Source (Kumaran)
|  | Lift - 2 verticals and beams | Completed | 2026-11-07 |  | Out Source (Kumaran)
The Bueller family | CIP & CMU | Foundations & slab on grade | Completed | 06-26-2026 |  | siva kumar
|  | Lift - 1 verticals and beams | Completed | 06-26-2026 |  | siva kumar
SPOTLOT 28810 SW 207 AVE | CIP & CMU | Foundations & slab on grade | Completed | 06-26-2026 | 1.087 | Eswar
|  | Lift - 1 verticals and beams | Completed | 06-26-2026 | 1.032 | Lokesh
Broken Sound Club | CIP | Foundations & slab on grade | Completed | 06-23-2026 |  | siva kumar
|  | Lift - 1 verticals and beams | Completed | 06-23-2026 |  | siva kumar
128 Worth CT N | CIP & CMU | Foundations & slab on grade | Completed | 2026-11-07 |  | Pradeep
|  | Lift - 1 verticals and beams | Inprogress | 2026-07-08 |  | Pavan sai
|  | Lift - 2 verticals and beams | Not Yet Started | 2026-07-08
2235 Mangolia Drive | CIP & CMU | Foundations & slab on grade | Completed | 2026-10-07 |  | Praveena
|  | Lift - 1 verticals and beams | Inprogress | 2026-07-08 |  | Praveena
|  | Lift - 2 verticals and beams | Not Yet Started | 08-14-2026
270 Celestial Way | CIP & CMU | Slab and beams | Completed | 07-14-2026 |  | Sri lalitha
501 Diplomat - Porte Cochere | CIP & CMU | Columns, Cmu walls, tie beams & concrete caps | Completed | 07-23-2026 |  | Praveena
|  | Roof slab | Not Yet Started | 2026-10-07 |  | Praveena
Zen Elite Equestrian Center | CIP & CMU | Foundations & Slab on grade | Completed | 07-24-2026 |  | Pradeep
|  | Lift - 1 Verticals and beams | Completed | 07-24-2026
Belle Meade Residence | CIP & CMU | Foundations | Completed | 07-31-2026 |  | Sri lalitha
|  | Slab on grade | Inprogress | 2026-07-08 |  | Sri lalitha
|  | Lift - 1 Verticals and beams | Not Yet Started | 08-14-2026
|  | 2nd floor slab and beams | Not Yet Started | 08-14-2026
|  | Lift - 2 Verticals and beams | Not Yet Started | 08-14-2026
The Duhl Residence | CIP & CMU | Foundations | Completed | 07-31-2026 |  | Sridevi
|  | Slab on grade | Completed | 07-31-2026
|  | Lift - 1 Verticals and beams | Not Yet Started | 08-14-2026
|  | Lift - 2 Verticals and beams | Not Yet Started | 08-14-2026
1105 Northlake Way | CIP & CMU | Foundations and slab on grade | Completed | 07-28-2026 |  | Out Source (Kumaran)
|  | Lift - 1 Verticals and beams | Completed | 07-28-2026 |  | Out Source (Kumaran)
Miller Residence | CIP & CMU | Foundations | Completed | 07-24-2026 |  | Praveena
|  | Slab on grade | Completed | 07-28-2026
|  | Lift - 1 Verticals and beams | Not Yet Started | 2026-07-08
|  | 2nd floor slab and beams | Not Yet Started | 2026-07-08
|  | Lift - 2 Verticals and beams | Not Yet Started | 2026-07-08
Mdag Miami Dad Spot Lots | CIP & CMU | Foundations & slab on grade | Completed | 07-17-2026 |  | siva kumar
|  | Lift - 1 Verticals and beams | Not Yet Started | 2026-07-08
|  | Lift - 2 Verticals and beams | Not Yet Started | 2026-07-08
Arrigo Residence | CIP & CMU | Foundations | Completed | 07-28-2026 |  | siva kumar
|  | Slab on grade | Completed | 07-29-2026
|  | Lift - 1 Verticals and beams | Not Yet Started | 2026-07-08
|  | Lift - 2 Verticals and beams | Not Yet Started | 2026-07-08
|  | Pool house foundations & slab on grade | Completed | 07-29-2026
|  | Lift - 1 Verticals and roof beams | Not Yet Started | 2026-07-08
New Luse Residence (9401 Residence) | CIP & CMU | Foundations | Completed | 07-31-2026 |  | Lokesh Reddy
|  | Slab on grade | Completed | 07-31-2026
|  | Lift - 1 Verticals and beams | Not Yet Started | 08-14-2026
|  | Lift - 2 Verticals and beams | Not Yet Started | 08-14-2026
|  | Site walls | Not Yet Started | 08-14-2026
Riopelle Residence | CIP & CMU | Foundations & slab on grade | Completed | 07-31-2026 |  | Pradeep
|  | Lift -1 Verticals and roof beams | Completed | 07-31-2026
Coy Residence | CIP & CMU | Garage Building
|  | Foundations & slab on grade | Inprogress | 2026-06-08
|  | Lift - 1 Verticals & beams | Inprogress | 2026-11-08
|  | Lift - 2 Verticals & beams | Inprogress | 2026-11-08
Main Building
|  | Foundations & Slab on grade | Inprogress | 2026-06-08
|  | Lift - 1 Verticals & beams | Inprogress | 2026-11-08
|  | Lift - 2 Verticals and beams | Inprogress | 2026-11-08
Dolce Residence | CIP & CMU | Foundations and slab on grade | Inprogress | 2026-05-08
|  | Lift - 1 Verticals beams | Not Yet Started | 08-14-2026
|  | Lift - 2 Verticals and roof beams | Not Yet Started | 08-14-2026
Residential Duplex | CIP & CMU | Foundations and slab on grade | Inprogress | 2026-07-08 |  | siva kumar
|  | Lift - 1 Verticals beams | Not Yet Started | 08-14-2026
|  | Lift - 2 Verticals and roof beams | Not Yet Started | 08-14-2026
Gensis (Scattered Lots) | CIP & CMU | Foundations and slab on grade | Inprogress | 2026-05-08 |  | Lokesh Reddy
|  | Lift - 1 Verticals beams | Not Yet Started | 08-14-2026
|  | Lift - 2 Verticals and roof beams | Not Yet Started | 08-14-2026
1042 Palm Way rd NPB Pinsonnault Residence | CIP & CMU | Foundations and slab on grade | Not Yet Started | 08-14-2026
|  | Verticals&beams | Not Yet Started | 08-14-2026
OLD PROJECTS MODIFICATIONS
1333 Bvld | Barlists | Shear walls and columns Barlists | Completed | 2026-07-05 |  | Lokesh Reddy
Valencia Del Mar Clubhouse | Barlists | Slab on grade Barlists | Completed | 2026-05-05 |  | Vaishnavi
320 S atlantic Drive | Barlists | Foundations Barlists | Completed | 2026-05-05 |  | Sridevi
910 S Ocean | Emds | Comments received on basement R1series dwgs | Completed | 2026-06-05 |  | Sridevi
6024 Le lac Rd | Emds | Comments received on pool cabana & outdoor kitchen | Completed | 2026-07-05 |  | Sridevi / Vaishnavi
6017 Le Lac Road (Weiner Residence) | Barlists | Barlists requested for 2story building lift - 1 verticals | Completed | 2026-06-05 |  | Vaishnavi
South Rd Office Building E | Barlists | Lift - 1 Verticals and beams | Completed | 2026-07-05 |  | Vaishnavi
559 Nw 43 st | Barlists | Stairs barlists | Completed | 2026-06-05 |  | Danush
PBIA - Revenue Control Building | Emds | Rfi-029 received on foundaitons | Completed | 2026-08-05 |  | Vaishnavi
Sands residence (3223 N Ocean) | Emds | Ssk-017 Received for 2nd for slab at balcony | Completed | 2026-08-05 |  | Eswar
5900 Powerline Garage | Barlists | Foundations (Grade beams) | Completed | 2026-08-05 |  | Pradeep
1050 N Lake way | Barlists | 2nd lift - 2 verticals and beams | Completed | 2026-09-05 |  | Lokesh Reddy
Baig Residence | Barlists | 2nd floor slab | Completed | 2026-09-05 |  | Lokesh Reddy
South Rd Office Building E | Patch | Need patch lists for cmu walls at stem walls | Completed | 2026-09-05 |  | Lokesh Reddy
Valencia Del Mar Clubhouse | Barlists | Lift - 1 verticals section #3 | Completed | 05-19-2026
South Rd Office Building E | Barlists | Lift -1 verticals barlists | Completed | 05-13-2026 |  | Lokesh Reddy
2651 SE 10th Court | Barlists | Pool deck slab and beams barlists | Completed | 05-18-2026
6017 Le Lac Road (Weiner Residence) | Barlists | Orange section #2 1st lift verticals | Completed | 05-19-2026
1333 Bvld | Barlists | Stem walls barlists | Completed | 05-18-2026
2651 SE 10th Court | Emds | Update received on the pool deck | Completed | 05-19-2026
cannatelli | Barlists | Foundations and slab on grade Barlists | Completed | 05-18-2026
6017 Le Lac Road (Weiner Residence) | Barlists | Lift - 1 verticals and beams for Blue section | Completed
401 SE Atlantic Drive | Barlists | Barlists for R3 series drawings | Completed | 05-20-2026
515 Lido Drive | Barlists | Column ties for upto 4'-0" | Completed | 05-20-2026
143 Reef Road | Updated drawings | 1st floor beams and second floor slab | Completed
PBIA - Revenue Control Building | Revised drawings | Revised drawings received on cmu verticals | Completed | 05-22-2026
515 Lido Drive | Barlists | Garage slab barlists | Completed | 05-21-2026
cannatelli | Barlists | Foundations and slab on grade Barlists | Completed | 05-23-2026
1042 Palm Way Road | Revised drawings | Roof beams and slab | Completed | 05-28-2026
South Rd Office Building E | Emds | Comments received on 1st lift verticals and beams | Completed | 05-22-2026
910 S Ocean | Barlists | Basement slab barlists | Completed | 05-27-2026
Valencia Del Mar Clubhouse | Barlists | Lift - 2 verticals and beams for green section #2 | Completed | 05-28-2026
Valencia Del Mar Clubhouse | Barlists | Lift - 2 verticals and beams for Yellow section #1 | Completed | 05-28-2026
Burns Residence | Barlists | Slab on grade barlists | Completed | 05-28-2026
1900 NE 22ND Terrance | Emds | Comments received on slab on grade | Completed | 05-28-2026
975.703
Note: Submittal dates may change according to client request / RFI Clarification /Priorities