## PROJECTS
Formcrete
PROJECT NAME | SCOPE | COMPONENTS OF WORK | STATUS | SUB. DATE | CUST. REQ. DATE | DET. WT. | DETAILER | CHECKER
Modera Boca Raton | CIP & CMU | BASEMENT SLAB ON GRADE | COMPLETED | 2025-12-15 | 2025-12-15 | 4.664 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | GROUND FLOOR SLAB (GARAGE AREA) | COMPLETED | 2025-12-06 | 2025-12-06 | 28.082 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | GROUND FLOOR SLAB (RESIDENTIAL AREA) | COMPLETED | 2025-12-06 | 2025-12-06 | 8.677 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | BASEMENT RETAINIG WALLS & CMU WALLS | COMPLETED | 2026-01-08 | 2026-01-08 | 22.254 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | 2ND FLR GARAGE SLAB | COMPLETED | 2026-01-24 | 2026-01-24 | 25.559 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | 2ND FLR RESIDENTIAL SLAB | COMPLETED | 2026-01-24 | 2026-01-24 | 17.587 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | 3RD FLR GARAGE SLAB | COMPLETED | 2026-03-20 | 2026-03-20 | 17.318 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | 3RD FLR RESIDENTIAL SLAB | COMPLETED | 2026-03-20 | 2026-03-20 | 26.389 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | SHEAR WALLS (LVL-2 TO LVL-8) | COMPLETED | 2026-03-06 | 2026-03-06 | 82.779 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | SHEAR WALLS (LVL-8 TO BULK HEAD) | COMPLETED | 2026-02-28 | 2026-02-28 | 36.429 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | LEVEL-2 TO LEVEL-4 COLUMNS | COMPLETED | 2026-03-27 | 2026-03-27 | 55.059 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | 4TH FLR GARAGE SLAB | COMPLETED | 2026-04-07 | 2026-04-07 | 17.656 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | 4TH FLR RESIDENTIAL SLAB | COMPLETED | 2026-04-07 | 2026-04-07 | 23.397 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | 5TH FLR GARAGE SLAB | COMPLETED | 2026-04-07 | 2026-04-07 | 17.642 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | 5TH FLR RESIDENTIAL SLAB | COMPLETED | 2026-04-07 | 2026-04-07 | 23.397 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | 6TH FLR GARAGE SLAB | COMPLETED | 2026-04-10 | 2026-04-10 | 17.161 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | 6TH FLR RESIDENTIAL SLAB | COMPLETED | 2026-04-10 | 2026-04-10 | 23.382 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | LEVEL-4 TO LEVEL-8 COLUMNS | COMPLETED | 2026-04-13 | 2026-04-13 | 118.63 | Jagadeesh | Chandra mouli
Modera Boca Raton | CIP & CMU | 7TH FLR SLAB | COMPLETED | 2026-04-17 | 2026-04-17 | 92.114 | Nanaji | Chandra mouli
Modera Boca Raton | CIP & CMU | 8TH FLR SLAB | COMPLETED | 2026-05-01 | 2026-05-01 | 90.716 | Swathi | Chandra mouli
Modera Boca Raton | CIP & CMU | LEVEL-8 TO ROOF COLUMNS | COMPLETED | 2026-04-17 | 2026-04-17 | 30.34 | Jagadeesh | Chandra mouli
Modera Boca Raton | CIP & CMU | 9TH FLR SLAB | COMPLETED | 2026-05-06 | 2026-05-06 | 31.857 | Swathi | Chandra mouli
Modera Boca Raton | CIP & CMU | 10TH FLR SLAB | COMPLETED | 2026-05-06 | 2026-05-06 | 31.857 | Swathi | Chandra mouli
Modera Boca Raton | CIP & CMU | 11TH FLR SLAB | COMPLETED | 2026-05-14 | 2026-05-14 |  | Swathi | Chandra mouli
Modera Boca Raton | CIP & CMU | 12TH FLR SLAB | COMPLETED | 2026-05-14 | 2026-05-14 |  | Balaram & Swathi | Chandra mouli
Modera Boca Raton | CIP & CMU | 12TH MEZZ FLR SLAB | COMPLETED | 2026-05-15 | 2026-05-15 |  | Sai | Chandra mouli
Modera Boca Raton | CIP & CMU | ROOF SLAB | COMPLETED | 2026-05-18 | 2026-05-18 |  | Swathi | Chandra mouli
Modera Boca Raton | CIP & CMU | HIGH ROOF SLAB | COMPLETED | 2026-05-18 | 2026-05-18 |  | Swathi | Chandra mouli
Modera Boca Raton | CIP & CMU | GROUND LEVEL TO 2ND LEVEL TC & CMU WALLS | COMPLETED | 2026-05-19 | 2026-05-19 |  | Swathi | Chandra mouli
Modera Boca Raton | CIP & CMU | 2ND LEVEL TO 3RD LEVEL TC & CMU WALLS | COMPLETED | 2026-05-29 | 2026-05-29 | 12.755 | Balaram | Chandra mouli
Modera Boca Raton | CIP & CMU | 3RD LEVEL TO 4TH LEVEL TC & CMU WALLS | COMPLETED | 2026-06-02 | 2026-06-02 |  | Balaram | Chandra mouli
Modera Boca Raton | CIP & CMU | 4TH LEVEL TO 5TH LEVEL TC & CMU WALLS | COMPLETED | 2026-06-03 | 2026-06-03 |  | Balaram | Chandra mouli
Modera Boca Raton | CIP & CMU | 5TH LEVEL TO 6TH LEVEL TC & CMU WALLS | COMPLETED | 2026-06-04 | 2026-06-04 |  | Balaram | Chandra mouli
Modera Boca Raton | CIP & CMU | 6TH LEVEL TO 7TH LEVEL TC & CMU WALLS | COMPLETED | 2026-06-05 | 2026-06-05 |  | Balaram | Chandra mouli
Modera Boca Raton | CIP & CMU | 7TH LEVEL TO 8TH LEVEL TC & CMU WALLS | COMPLETED | 2026-06-06 | 2026-06-06 |  | Balaram | Chandra mouli
Modera Boca Raton | CIP & CMU | 8TH LEVEL TO 9TH LEVEL TC & CMU WALLS | COMPLETED | 2026-06-07 | 2026-01-07 |  | Balaram | Chandra mouli
Modera Boca Raton | CIP & CMU | 9TH LEVEL TO 10TH LEVEL TC & CMU WALLS | COMPLETED | 2026-06-06 | 2026-01-08 |  | Balaram | Chandra mouli
Modera Boca Raton | CIP & CMU | 10TH LEVEL TO 11TH LEVEL TC & CMU WALLS | COMPLETED | 2026-06-07 | 2026-01-09 |  | Balaram | Chandra mouli
Modera Boca Raton | CIP & CMU | 11TH LEVEL TO 12TH LEVEL TC & CMU WALLS | COMPLETED | 2026-06-08 | 2026-01-10 |  | Balaram | Chandra mouli
Modera Boca Raton | CIP & CMU | 12TH LEVEL TO 12TH MEZZ LEVEL TC & CMU WALLS | COMPLETED | 2026-06-09 | 2026-01-11 |  | Balaram | Chandra mouli
Modera Boca Raton | CIP & CMU | 12TH MEZZ LEVEL TO ROOF LEVEL TC & CMU WALLS | COMPLETED | 2026-06-10 | 2026-01-12 |  | Balaram | Chandra mouli
Modera Boca Raton | CIP & CMU | ROOF LEVEL TO HIGH ROOF TC & CMU WALLS | COMPLETED | 2026-06-11 | 2026-01-13 |  | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I FOUNDATIONS | COMPLETED | 2025-12-03 | 2025-12-03 | 19.937 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I SLAB ON GRADE | COMPLETED | 2026-01-02 | 2026-01-02 | 1.981 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I TUNNEL WALLS | COMPLETED | 2026-01-19 | 2026-01-19 | 30.005 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I LIFT-1 VERTICALS | COMPLETED | 2026-06-22 | 2026-06-22 | 3.51 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I 2ND FLR. SLAB & BEAMS | COMPLETED | 2025-12-03 | 2025-12-03 |  | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I LIFT-2 VERTICALS | COMPLETED | 2026-06-05 | 2026-01-11 |  | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I 3rd FLR. SLAB & BEAMS | COMPLETED | 2026-01-22 | 2026-01-22 |  | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I LIFT-3 VERTICALS | COMPLETED | 2026-06-22 | 2026-06-22 | 3.072 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I 4th FLR. SLAB & BEAMS | COMPLETED | 2026-01-22 | 2026-01-22 |  | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I LIFT-4 VERTICALS | COMPLETED | 2026-06-22 | 2026-06-22 | 3.072 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I 5th FLR. SLAB & BEAMS | COMPLETED | 2026-01-22 | 2026-01-22 |  | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I LIFT-5 VERTICALS | COMPLETED | 2026-06-22 | 2026-06-22 | 2.373 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-I ROOF SLAB & BEAMS WITH PARAPET | COMPLETED | 2026-06-23 | 2026-06-23 | 27.788 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II FOUNDATIONS | COMPLETED | 2026-01-22 | 2026-01-22 | 17.995 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II SLAB ON GRADE | COMPLETED | 2026-01-27 | 2026-01-27 | 1.461 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II TUNNEL WALLS | COMPLETED | 2026-01-22 | 2026-01-22 |  | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II LIFT-1 VERTICALS | COMPLETED | 2026-06-23 | 2026-06-23 | 2.912 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II 2ND FLR. SLAB & BEAMS | COMPLETED | 2026-01-22 | 2026-01-22 |  | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II LIFT-2 VERTICALS | COMPLETED | 2026-06-23 | 2026-06-23 | 2.597 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II 3rd FLR. SLAB & BEAMS | COMPLETED | 2026-01-22 | 2026-01-22 |  | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II LIFT-3 VERTICALS | COMPLETED | 2026-06-25 | 2026-06-25 | 2.534 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II 4th FLR. SLAB & BEAMS | COMPLETED | 2026-01-22 | 2026-01-22 |  | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II LIFT-4 VERTICALS | COMPLETED | 2026-06-25 | 2026-06-25 | 2.534 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II 5th FLR. SLAB & BEAMS | COMPLETED | 2026-01-22 | 2026-01-22 |  | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II LIFT-5 VERTICALS | COMPLETED | 2026-06-25 | 2026-06-25 | 1.971 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-II ROOF SLAB & BEAMS WITH PARAPET | COMPLETED | 2026-06-25 | 2026-06-25 | 23.39 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III FOUNDATIONS | COMPLETED | 2025-12-13 | 2025-12-13 | 17.755 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III SLAB ON GRADE | COMPLETED | 2025-12-22 | 2025-12-22 | 1.637 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III TUNNEL WALLS | COMPLETED | 2026-01-19 | 2026-01-19 | 25.123 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III LIFT-1 VERTICALS (CMU & COLUMNS) | COMPLETED | 2026-02-04 | 2026-02-04 | 3.469 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III 2ND FLR. SLAB & BEAMS | COMPLETED | 2026-03-23 | 2026-03-23 | 21.957 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III LIFT-2 VERTICALS | COMPLETED | 2026-06-18 | 2026-06-18 | 2.341 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III 3rd FLR. SLAB & BEAMS | COMPLETED | 2026-05-18 | 2026-05-18 |  | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III LIFT-3 VERTICALS | COMPLETED | 2026-06-18 | 2026-06-18 | 2.341 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III 4th FLR. SLAB & BEAMS | COMPLETED | 2026-05-18 | 2026-05-18 |  | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III LIFT-4 VERTICALS | COMPLETED | 2026-06-19 | 2026-06-19 | 2.341 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III 5th FLR. SLAB & BEAMS | COMPLETED | 2026-05-18 | 2026-05-18 |  | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III LIFT-5 VERTICALS | COMPLETED | 2026-06-19 | 2026-06-19 | 1.855 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-III ROOF SLAB & BEAMS WITH PARAPET | COMPLETED | 2026-05-18 | 2026-05-18 |  | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV FOUNDATIONS | COMPLETED | 2025-01-02 | 2025-01-02 | 51.958 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV SLAB ON GRADE | COMPLETED | 2025-12-24 | 2025-12-24 | 2.047 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV TUNNEL WALLS | COMPLETED | 2026-01-19 | 2026-01-19 | 41.043 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV LIFT-1 VERTICALS | COMPLETED | 2026-02-11 | 2026-02-11 | 16.144 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV 2ND FLR. SLAB & BEAMS | COMPLETED | 2026-04-10 | 2026-04-10 | 87.972 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV LIFT-2 VERTICALS | COMPLETED | 2026-06-26 | 2026-06-26 | 2.663 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV 3rd FLR. SLAB & BEAMS | COMPLETED | 2026-04-24 | 2026-04-24 | 27.95 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV LIFT-3 VERTICALS | COMPLETED | 2026-06-26 | 2026-06-26 | 2.661 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV 4th FLR. SLAB & BEAMS | COMPLETED | 2026-05-04 | 2026-05-04 |  | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV LIFT-4 VERTICALS | COMPLETED | 2026-06-26 | 2026-06-26 | 2.661 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV 5th FLR. SLAB & BEAMS | COMPLETED | 2026-05-04 | 2026-05-04 |  | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV LIFT-5 VERTICALS | COMPLETED | 2026-06-26 | 2026-06-26 | 2.011 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-IV ROOF SLAB & BEAMS WITH PARAPET | COMPLETED | 2026-02-13 | 2026-02-13 |  | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V FOUNDATIONS | COMPLETED | 2026-02-13 | 2026-02-13 | 25.382 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V SLAB ON GRADE | COMPLETED | 2026-04-14 | 2026-04-14 |  | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V TUNNEL WALLS | COMPLETED | 2026-04-18 | 2026-04-18 | 30.927 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V LIFT-1 VERTICALS | COMPLETED | 2026-06-16 | 2026-06-16 | 3.844 | Balaram | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V 2ND FLR. SLAB & BEAMS | COMPLETED | 2026-04-23 | 2026-04-23 | 24.656 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V LIFT-2 VERTICALS | COMPLETED | 2026-06-17 | 2026-06-17 | 3.405 | Swathi | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V 3rd FLR. SLAB & BEAMS | COMPLETED | 2026-04-25 | 2026-04-25 | 22.572 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V LIFT-3 VERTICALS | COMPLETED | 2026-06-17 | 2026-06-17 | 3.345 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V 4th FLR. SLAB & BEAMS | COMPLETED | 2026-04-28 | 2026-04-28 | 22.607 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V LIFT-4 VERTICALS | COMPLETED | 2026-06-17 | 2026-06-17 | 3.346 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V 5th FLR. SLAB & BEAMS | COMPLETED | 2026-04-28 | 2026-04-28 | 22.893 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V LIFT-5 VERTICALS | COMPLETED | 2026-06-17 | 2026-06-17 | 2.618 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BUILDING TYPE-V ROOF SLAB & BEAMS WITH PARAPET | COMPLETED | 2026-05-16 | 2026-05-16 | 28.225 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | BIKE STORAGE & PET SPA BLDG. | COMPLETED | 2025-12-01 | 2025-12-01 | 1.257 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | GARAGE TYPE-1 | COMPLETED | 2025-12-15 | 2025-12-15 | 3.232 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | TRASH ENCLOSURE | COMPLETED | 2026-01-02 | 2026-01-02 | 3.418 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | GARAGE TYPE-4 | COMPLETED | 2025-12-15 | 2025-12-15 | 2.088 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | GARAGE TYPE-2 | COMPLETED | 2025-12-27 | 2025-12-27 | 2.567 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | GARAGE TYPE-3 | COMPLETED | 2025-12-30 | 2025-12-30 | 2.545 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | POOL PAVILION | COMPLETED | 2026-01-02 | 2026-01-02 | 1.76 | Trisha | Chandra mouli
4541-Gables Cypress Creek | CIP & CMU | MAITAINANCE BUIDLING | COMPLETED | 2026-01-02 | 2026-01-02 | 1.187 | Trisha | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-1 COLUMN VERTICALS | COMPLETED | 2025-12-29 | 2025-12-29 | 50.079 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-1 & LIFT-2 SHEAR WALLS | COMPLETED | 2026-01-02 | 2026-01-02 | 23.387 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | STEM WALLS | COMPLETED | 2025-01-09 | 2025-01-09 | 8.493 | Sridevi | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-1 CMU VERTICALS | COMPLETED | 2025-01-10 | 2025-01-10 | 13.423 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-1 STAIRS | COMPLETED | 2025-01-10 | 2025-01-10 | 2.346 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | PIERS | COMPLETED | 2026-03-03 | 2026-03-03 | 6.595 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | 2ND FLOOR SLAB | COMPLETED | 2026-03-10 | 2026-03-10 | 45.947 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-2 & 3 Columns | COMPLETED | 2026-03-17 | 2026-03-17 | 26.878 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-2 & 3 SHEAR WALLS | COMPLETED | 2026-03-17 | 2026-03-17 | 22.937 | Jagadeesh | Chandra mouli
NOMI-6 | CIP & CMU | STAIRS (UP TO LVL.-4) | COMPLETED | 2026-03-20 | 2026-03-20 | 2.386 | Jagadeesh | Chandra mouli
NOMI-6 | CIP & CMU | 3RD FLOOR SLAB & BEAMS | COMPLETED | 2026-03-21 | 2026-03-21 | 44.076 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | 4TH FLOOR SLAB & BEAMS | COMPLETED | 2026-04-04 | 2026-04-04 | 100.479 | Sai & Swathi | Chandra mouli
NOMI-6 | CIP & CMU | 5th FLOOR SLAB & BEAMS | COMPLETED | 2026-04-24 | 2026-04-24 | 32.738 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | 6th FLOOR SLAB & BEAMS | COMPLETED | 2026-04-24 | 2026-04-24 | 32.258 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | 7th FLOOR SLAB & BEAMS | COMPLETED | 2026-04-24 | 2026-04-24 | 32.258 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | 8th FLOOR SLAB & BEAMS | COMPLETED | 2026-05-04 | 2026-05-04 | 37.186 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | 9th FLOOR SLAB & BEAMS | COMPLETED | 2026-05-04 | 2026-05-04 | 37.186 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | 10th FLOOR SLAB & BEAMS | COMPLETED | 2026-05-28 | 2026-05-28 | 38.226 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | 11th FLOOR SLAB & BEAMS | COMPLETED | 2026-06-18 | 2026-06-18 | 39.159 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | ROOF FLOOR SLAB & BEAMS | COMPLETED | 2026-06-25 | 2026-06-25 | 34.263 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-4 COLUMNS | COMPLETED | 2026-04-28 | 2026-04-28 | 13.962 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-5&6 COLUMNS | COMPLETED | 2026-05-06 | 2026-05-06 | 22.86 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-4 & 5 SHEAR WALLS | COMPLETED | 2026-02-05 | 2026-02-05 |  | Balaram | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-7 & 8 COLUMNS | COMPLETED | 2026-05-06 | 2026-05-06 | 22.86 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-6 & 7 SHEAR WALLS | COMPLETED | 2026-05-09 | 2026-05-09 | 14.422 | Sai | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-9 & 10 COLUMNS | COMPLETED |  |  |  | Sai | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-8 & 9 SHEAR WALLS | COMPLETED |  |  |  | Sai | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-11 COLUMNS | COMPLETED |  |  |  | Sai | Chandra mouli
NOMI-6 | CIP & CMU | LIFT-10 & 11 SHEAR WALLS | COMPLETED |  |  |  | Sai | Chandra mouli
NOMI-6 | CIP & CMU | STAIRS (LEVEL-4 TO LEVEL-6) | COMPLETED | 2026-04-29 | 2026-04-29 |  | Sai | Chandra mouli
NOMI-6 | CIP & CMU | STAIRS (LEVEL-6 TO ROOF) | COMPLETED | 2026-06-05 | 2026-06-05 |  | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 2ND FLOOR SLAB (RESIDENTIAL) | COMPLETED | 2026-02-05 | 2026-02-05 | 23.071 | Chandra mouli | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 2ND FLOOR SLAB (GARAGE) | COMPLETED | 2026-02-05 | 2026-02-05 | 26.205 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 3RD FLOOR SLAB (RESIDENTIAL) | COMPLETED | 2026-02-28 | 2026-02-28 | 21.963 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 3RD FLOOR SLAB (GARAGE) | COMPLETED | 2026-02-27 | 2026-02-27 | 25.524 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 4TH FLOOR SLAB (RESIDENTIAL) | COMPLETED | 2026-02-28 | 2026-02-28 | 21.534 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 4TH FLOOR SLAB (GARAGE) | COMPLETED | 2026-02-27 | 2026-02-27 | 25.367 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 5TH FLOOR SLAB (RESIDENTIAL) | COMPLETED | 2026-02-14 | 2026-02-14 | 22.122 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 5TH FLOOR SLAB (GARAGE) | COMPLETED | 2026-02-27 | 2026-02-27 | 25.353 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 6TH FLOOR SLAB (RESIDENTIAL) | COMPLETED | 2026-02-14 | 2026-02-14 | 22.123 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 6TH FLOOR SLAB (GARAGE) | COMPLETED | 2026-02-28 | 2026-02-28 | 25.385 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 7TH FLOOR SLAB (RESIDENTIAL) | COMPLETED | 2026-02-14 | 2026-02-14 | 22.124 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 7TH FLOOR SLAB (GARAGE) | COMPLETED | 2026-02-28 | 2026-02-28 | 27.222 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 8TH FLOOR SLAB (RESIDENTIAL) | COMPLETED | 2026-02-14 | 2026-02-14 | 22.123 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | 8TH FLOOR AND ROOF SLAB (GARAGE) | COMPLETED | 2026-02-28 | 2026-02-28 | 15.783 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | ROOF SLAB (RESIDENTIAL) | COMPLETED | 2026-02-16 | 2026-02-16 | 33.383 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | STAIR #1 (GROUND FLOOR TO ROOF) | COMPLETED | 2026-03-13 | 2026-03-13 | 2.56 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | STAIR #2 (GROUND FLOOR TO ROOF) | COMPLETED | 2026-03-13 | 2026-03-13 | 3.099 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | STAIR #3 (GROUND FLOOR TO ROOF) | COMPLETED | 2026-03-13 | 2026-03-13 | 2.217 | Sai | Chandra mouli
4543 DULCE VIDA | CIP & CMU | STAIR #4 (GROUND FLOOR TO ROOF) | COMPLETED | 2026-03-13 | 2026-03-13 | 2.782 | Sai | Chandra mouli
2460 Australian (Ocean Tower) | STEEL | STEEL COLUMNS | COMPLETED | 2026-02-09 | 2026-02-09 |  | Sai | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | PILE CAPS | COMPLETED | 2026-02-12 | 2026-02-12 | 82.838 | Sridevi | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | GRADE BEAMS | COMPLETED | 2026-04-02 | 2026-04-02 | 118.168 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | SLAB ON GRADE | COMPLETED | 2026-04-20 | 2026-04-20 | 51.778 | Balaram | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | LIFT -1 VERTICALS CMU & COLUMS | COMPLETED | 2026-04-21 | 2026-04-21 | 24.817 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | TUNNEL WALLS | COMPLETED | 2026-05-01 | 2026-05-01 | 71.82 | Balaram | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | 2ND FLR. SLAB & BEAMS | COMPLETED | 2026-05-08 | 2026-05-08 | 85.402 | Balaram | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | LIFT -2 VERTICALS CMU & COLUMS | COMPLETED | 2026-05-08 | 2026-05-08 | 5.969 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | RETAIINING WALL | COMPLETED | 2026-05-08 | 2026-05-08 | 2.214 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | 3RD FLR. SLAB & BEAMS | COMPLETED | 2026-05-15 | 2026-05-15 | 4.462 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | LIFT -3 VERTICALS CMU & COLUMS | COMPLETED | 2026-05-15 | 2026-05-15 | 34.412 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | 4TH FLR. SLAB & BEAMS | COMPLETED | 2026-05-22 | 2026-05-22 | 34.413 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | LIFT -4 VERTICALS CMU & COLUMS | COMPLETED | 2026-05-22 | 2026-05-22 | 4.381 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | 5TH FLR. SLAB & BEAMS | COMPLETED | 2026-05-28 | 2026-05-28 | 34.313 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | LIFT -5 VERTICALS CMU & COLUMS | COMPLETED | 2026-05-28 | 2026-05-28 | 4.388 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | 6TH FLR. SLAB & BEAMS | COMPLETED | 2026-05-28 | 2026-05-28 | 34.313 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | LIFT -6 VERTICALS CMU & COLUMS | COMPLETED | 2026-05-28 | 2026-05-28 | 4.388 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | 7TH FLR. SLAB & BEAMS | COMPLETED | 2026-05-28 | 2026-05-28 | 34.313 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | LIFT -7 VERTICALS CMU & COLUMS | COMPLETED | 2026-05-28 | 2026-05-28 | 4.388 | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | 8TH FLR. SLAB & BEAMS | COMPLETED | 2026-06-03 | 2026-06-03 |  | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | LIFT -8 VERTICALS CMU & COLUMS | COMPLETED | 2026-06-05 | 2026-06-05 |  | Dhanush | Chandra mouli
2460 Australian (Ocean Tower) | CIP & CMU | ROOF SLAB & BEAMS WITH PARAPET | COMPLETED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | STEEL | BLDG 1 Type II | COMPLETED | 2026-05-29 | 2026-05-29 |  | Balaram | Chandra mouli
Magnolia Point | STEEL | BLDG 2 Type VI | COMPLETED | 2026-05-29 | 2026-05-29 |  | Balaram | Chandra mouli
Magnolia Point | STEEL | BLDG 3 Type V | COMPLETED | 2026-05-29 | 2026-05-29 |  | Balaram | Chandra mouli
Magnolia Point | STEEL | BLDG 4 Type III | COMPLETED | 2026-05-29 | 2026-05-29 |  | Balaram | Chandra mouli
Magnolia Point | STEEL | BLDG 5 Type VII | COMPLETED | 2026-05-29 | 2026-05-29 |  | Balaram | Chandra mouli
Magnolia Point | STEEL | Clubhouse | COMPLETED | 2026-05-29 | 2026-05-29 |  | Balaram | Chandra mouli
Magnolia Point | CIP & CMU | Clubhouse - Foundations & SOG | COMPLETED | 2026-06-01 | 2026-06-01 | 4.171 | Chandra mouli | Chandra mouli
Magnolia Point | CIP & CMU | Clubhouse - Lift-1 verticals | COMPLETED | 2026-06-24 | 2026-06-24 |  | Chandra mouli | Chandra mouli
Magnolia Point | CIP & CMU | Clubhouse - Roof slab | COMPLETED |  |  |  | Chandra mouli | Chandra mouli
Magnolia Point | CIP & CMU | Trash enclosure | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Chandra mouli | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - Foundations & SOG | COMPLETED | 2026-06-26 | 2026-06-26 |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - 2nd floor slab | IN PROGRESS | 2026-07-20 |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - 3rd floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - 4th floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - 5th floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - 6th floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - Roof level slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - Lift-1 verticals | COMPLETED | 2026-07-15 | 2026-07-15 |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - Lift-2 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - Lift-3 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - Lift-4 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - Lift-5 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 3 Type V - Lift-6 & parapet verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - Foundations & SOG | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - 2nd floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - 3rd floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - 4th floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - 5th floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - 6th floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - Roof level slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - Lift-1 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - Lift-2 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - Lift-3 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - Lift-4 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - Lift-5 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 1 Type II - Lift-6 & parapet verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - Foundations & SOG | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - 2nd floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - 3rd floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - 4th floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - 5th floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - 6th floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - Roof level slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - Lift-1 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - Lift-2 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - Lift-3 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - Lift-4 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - Lift-5 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 2 Type VI - Lift-6 & parapet verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 5 Type VII - Foundations & SOG | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 5 Type VII - 2nd floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 5 Type VII - 3rd floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 5 Type VII - Roof level slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 5 Type VII - Lift-1 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 5 Type VII - Lift-2 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 5 Type VII - Lift-3 & parapet verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 4 Type III - Foundations & SOG | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 4 Type III - 2nd floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 4 Type III - 3rd floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 4 Type III - 4th floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 4 Type III - 5th floor slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 4 Type III - Roof level slab | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 4 Type III - Lift-1 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 4 Type III - Lift-2 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 4 Type III - Lift-3 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 4 Type III - Lift-4 verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Magnolia Point | CIP & CMU | BLDG 4 Type III - Lift-5 & parapet verticals | NOT YET STARTED |  |  |  | Dhanush | Chandra mouli
Hilltop Gardens | STEEL | Building _1 Type III | COMPLETED | 2026-05-29 | 2026-05-29 |  | Dhanush | Chandra mouli
Hilltop Gardens | STEEL | Building _2 Type II | COMPLETED | 2026-05-29 | 2026-05-29 |  | Dhanush | Chandra mouli
Hilltop Gardens | STEEL | Building _3 Type II | COMPLETED | 2026-05-29 | 2026-05-29 |  | Dhanush | Chandra mouli
Hilltop Gardens | STEEL | Building _4 Type I | COMPLETED | 2026-05-29 | 2026-05-29 |  | Dhanush | Chandra mouli
Hilltop Gardens | STEEL | Building _5 Type I | COMPLETED | 2026-05-29 | 2026-05-29 |  | Dhanush | Chandra mouli
Hilltop Gardens | STEEL | Building _6 Type I | COMPLETED | 2026-05-29 | 2026-05-29 |  | Dhanush | Chandra mouli
Hilltop Gardens | STEEL | Clubhouse | COMPLETED | 2026-05-29 | 2026-05-29 |  | Dhanush | Chandra mouli
Altis Delray | STEEL | Building Type I | COMPLETED | 2026-05-29 | 2026-05-29 |  | Dhanush | Chandra mouli
Altis Delray | STEEL | Building Type II | COMPLETED | 2026-05-29 | 2026-05-29 |  | Dhanush | Chandra mouli
Altis Delray | STEEL | Building Type IIM | COMPLETED | 2026-05-29 | 2026-05-29 |  | Dhanush | Chandra mouli
Altis Delray | STEEL | Building Type III | COMPLETED | 2026-05-29 | 2026-05-29 |  | Dhanush | Chandra mouli
Altis Delray | STEEL | Clubhouse | COMPLETED | 2026-05-29 | 2026-05-29 |  | Dhanush | Chandra mouli
Octavia | STEEL | Steel columns | COMPLETED | 2026-05-21 | 2026-05-21
Octavia | CIP & CMU | Deep footings | COMPLETED | 2026-06-15 | 2026-06-15 | 166.209 | Chandra mouli | Chandra mouli
Octavia | CIP & CMU | SHALLOW GARAGE FOUNDATIONS | COMPLETED | 2026-06-19 | 2026-06-19 | 115.849 | Chandra mouli | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL SHALLOW FOUNDATIONS | COMPLETED | 2026-07-01 | 2026-07-01 | 89.987 | Chandra mouli | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL SOG | COMPLETED | 2026-07-01 | 2026-07-01 | 8.548 | Trisha | Chandra mouli
Octavia | CIP & CMU | SHEAR WALLS RESIDENTIAL & GARAGE | COMPLETED | 2026-07-06 | 2026-07-06 | 151.865 | Swathi | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL 1ST LIFT OF COLUMNS (GRND TO 2ND) | COMPLETED | 2026-07-07 | 2026-07-07 | 24.281 | Sai | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL CMU & LINTELS (GRND TO 2ND) | COMPLETED | 2026-07-13 | 2026-07-13 | 38.366 | Sai | Chandra mouli
Octavia | CIP & CMU | GARAGE 1ST LIFT OF COLUMNS (GRND TO 1.5) | COMPLETED | 2026-07-10 | 2026-07-10 | 34.149 | Chandra mouli | Chandra mouli
Octavia | CIP & CMU | GARAGE 1.5 LVL SLAB | COMPLETED | 2026-07-07 | 2026-07-07 | 26.148 | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL 2ND LVL SLAB | COMPLETED | 2026-07-16 | 2026-07-16 | 161.933 | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL COLUMNS (2ND TO ROOF) | COMPLETED | 2026-07-14 | 2026-07-14 | 13.761 | Sai | Chandra mouli
Octavia | CIP & CMU | GARAGE COLUMNS (1.5 TO ROOF) | COMPLETED | 2026-07-20 | 2026-07-20 | 193.922 | Chandra mouli | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL CMU & LINTELS (2ND TO 3RD) | COMPLETED | 2026-07-17 | 2026-07-17 | 12.69 | Sai | Chandra mouli
Octavia | CIP & CMU | GARAGE 2ND LVL SLAB | COMPLETED | 2026-07-23 | 2026-07-17 | 29.341 | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL 3RD LVL SLAB | IN PROGRESS | 2026-07-27 | 2026-07-20 |  | Swathi | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL CMU & LINTELS (3RD TO 4TH) | COMPLETED | 2026-07-29 | 2026-07-22 | 11.166 | Sai | Chandra mouli
Octavia | CIP & CMU | GARAGE 3RD LVL SLAB | COMPLETED | 2026-07-27 | 2026-07-24 | 29.324 | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL 4TH LVL SLAB | IN PROGRESS | 2026-08-03 | 2026-07-27 |  | Swathi | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL CMU & LINTELS (4TH TO 5TH) | COMPLETED | 2026-07-29 | 2026-07-29 | 10.896 | Sai | Chandra mouli
Octavia | CIP & CMU | GARAGE 4TH LVL SLAB | COMPLETED | 2026-07-27 | 2026-07-30 | 29.043 | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL 5TH LVL SLAB | NOT YET STARTED | 2026-08-03 | 2026-08-03 |  | Swathi | Chandra mouli
Octavia | CIP & CMU | GARAGE 5TH LVL SLAB | NOT YET STARTED | 2026-08-05 | 2026-08-05 |  | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL CMU & LINTELS (5TH TO 6TH) | NOT YET STARTED | 2026-08-05 | 2026-08-05 |  | Sai | Chandra mouli
Octavia | CIP & CMU | GARAGE CMU & LINTELS (2ND TO 3RD) | NOT YET STARTED | 2026-08-07 | 2026-08-07 |  | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL 6TH LVL SLAB | NOT YET STARTED | 2026-08-10 | 2026-08-10 |  | Swathi | Chandra mouli
Octavia | CIP & CMU | GARAGE 6TH LVL SLAB | NOT YET STARTED | 2026-08-11 | 2026-08-11 |  | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL CMU & LINTELS (6TH TO 7TH) | NOT YET STARTED | 2026-08-12 | 2026-08-12 |  | Sai | Chandra mouli
Octavia | CIP & CMU | GARAGE CMU & LINTELS (3RD TO 4TH) | NOT YET STARTED | 2026-08-13 | 2026-08-13 |  | balaram | Chandra mouli
Octavia | CIP & CMU | GARAGE 7TH LVL SLAB | NOT YET STARTED | 2026-08-17 | 2026-08-17 |  | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL 7TH LVL SLAB | NOT YET STARTED | 2026-08-17 | 2026-08-17 |  | Swathi | Chandra mouli
Octavia | CIP & CMU | GARAGE CMU & LINTELS (4TH TO 5TH) | NOT YET STARTED | 2026-08-19 | 2026-08-19 |  | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL CMU & LINTELS (7TH TO 8TH) | NOT YET STARTED | 2026-08-19 | 2026-08-19 |  | Sai | Chandra mouli
Octavia | CIP & CMU | GARAGE SOG SLAB | NOT YET STARTED | 2026-08-20 | 2026-08-20 |  | balaram | Chandra mouli
Octavia | CIP & CMU | GARAGE 8TH LVL SLAB | NOT YET STARTED | 2026-08-24 | 2026-08-24 |  | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL 8TH LVL SLAB | NOT YET STARTED | 2026-08-24 | 2026-08-24 |  | Swathi | Chandra mouli
Octavia | CIP & CMU | GARAGE CMU & LINTELS (5TH TO 6TH) | NOT YET STARTED | 2026-08-25 | 2026-08-25 |  | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL CMU & LINTELS (8TH TO ROOF) | NOT YET STARTED | 2026-08-26 | 2026-08-26 |  | Sai | Chandra mouli
Octavia | CIP & CMU | GARAGE ABOVE ROOF REBAR | NOT YET STARTED | 2026-08-28 | 2026-08-28 |  | balaram | Chandra mouli
Octavia | CIP & CMU | RESIDENTIAL ROOF LVL SLAB | NOT YET STARTED | 2026-08-31 | 2026-08-31 |  | Swathi | Chandra mouli
Octavia | CIP & CMU | GARAGE CMU & LINTELS (6TH TO 7TH) | NOT YET STARTED | 2026-09-01 | 2026-09-01 |  | balaram | Chandra mouli
Octavia | CIP & CMU | GARAGE CMU & LINTELS (7TH TO 8TH) | NOT YET STARTED | 2026-09-08 | 2026-09-08 |  | balaram | Chandra mouli
Octavia | CIP & CMU | GARAGE CMU & LINTELS (GRND TO 2ND) | NOT YET STARTED | 2026-09-15 | 2026-09-15 |  | balaram | Chandra mouli
ALTON DELRAY | CIP & CMU | Clubhouse 2nd floor slab | IN PROGRESS | 2026-07-22 | 2026-07-27 |  | Trisha | Chandra mouli
ALTON DELRAY | CIP & CMU | Clubhouse Lift-1 verticals | COMPLETED | 2026-07-27 | 2026-07-27 |  | Trisha
ALTON DELRAY | CIP & CMU | Clubhouse Lift-2 verticals & Roof beams | COMPLETED | 2026-07-27 | 2026-07-27 |  | Trisha |  | Clubhouse – 07/27
ALTON DELRAY | CIP & CMU | Bldg #1 Type IIM - 2nd floor slab | COMPLETED | 2026-07-27 | 2026-07-27 |  | Sai |  | Building #1 – Type IIM – 2nd to 5th Floor Slab – 07/27
ALTON DELRAY | CIP & CMU | Bldg #1 Type IIM - 3rd floor slab | COMPLETED | 2026-07-27 | 2026-07-27 |  | Sai |  | Building #1 – Type IIM – Remaining Drawings – 08/03
ALTON DELRAY | CIP & CMU | Bldg #1 Type IIM - 4th floor slab | COMPLETED | 2026-07-27 | 2026-07-27 |  | Sai |  | Parking Garage – 08/17
ALTON DELRAY | CIP & CMU | Bldg #1 Type IIM - 5th floor slab | COMPLETED | 2026-07-27 | 2026-07-27 |  | Sai |  | Building #2 – Type II – 08/24
ALTON DELRAY | CIP & CMU | Bldg #1 Type IIM - Roof slab | NOT YET STARTED | 2026-08-03 | 2026-08-03 |  | Sai |  | Building #3 – Type III – 09/15
ALTON DELRAY | CIP & CMU | Bldg #1 Type IIM - Tunnel walls | NOT YET STARTED | 2026-08-03 | 2026-08-03 |  | balaram |  | Building #5 – Type I – 09/28
ALTON DELRAY | CIP & CMU | Bldg #1 Type IIM - Lift-1 verticals | NOT YET STARTED | 2026-08-03 | 2026-08-03 |  | Trisha |  | Building #4 – Type I – 09/30
ALTON DELRAY | CIP & CMU | Bldg #1 Type IIM - Lift-2 verticals | NOT YET STARTED | 2026-08-03 | 2026-08-03 |  | Trisha
ALTON DELRAY | CIP & CMU | Bldg #1 Type IIM - Lift-3 verticals | NOT YET STARTED | 2026-08-03 | 2026-08-03 |  | Trisha
ALTON DELRAY | CIP & CMU | Bldg #1 Type IIM - Lift-4 verticals | NOT YET STARTED | 2026-08-03 | 2026-08-03 |  | Trisha
ALTON DELRAY | CIP & CMU | Bldg #1 Type IIM - Lift-5 verticals | NOT YET STARTED | 2026-08-03 | 2026-08-03 |  | Trisha
ALTON DELRAY | CIP & CMU | Parking Garage - 2nd floor slab | IN PROGRESS | 2026-08-17 | 2026-08-17 |  | Jeswanth
ALTON DELRAY | CIP & CMU | Parking Garage - Verticals | NOT YET STARTED | 2026-08-17 | 2026-08-17 |  | Jeswanth
ALTON DELRAY | CIP & CMU | Bldg #2 Type II - 2nd floor slab | NOT YET STARTED | 2026-08-24 | 2026-08-24
ALTON DELRAY | CIP & CMU | Bldg #2 Type II - 3rd floor slab | NOT YET STARTED | 2026-08-24 | 2026-08-24
ALTON DELRAY | CIP & CMU | Bldg #2 Type II - 4th floor slab | NOT YET STARTED | 2026-08-24 | 2026-08-24
ALTON DELRAY | CIP & CMU | Bldg #2 Type II - 5th floor slab | NOT YET STARTED | 2026-08-24 | 2026-08-24
ALTON DELRAY | CIP & CMU | Bldg #2 Type II - Roof slab | NOT YET STARTED | 2026-08-24 | 2026-08-24
ALTON DELRAY | CIP & CMU | Bldg #2 Type II - Tunnel walls | NOT YET STARTED | 2026-08-24 | 2026-08-24
ALTON DELRAY | CIP & CMU | Bldg #2 Type II - Lift-1 verticals | NOT YET STARTED | 2026-08-24 | 2026-08-24
ALTON DELRAY | CIP & CMU | Bldg #2 Type II - Lift-2 verticals | NOT YET STARTED | 2026-08-24 | 2026-08-24
ALTON DELRAY | CIP & CMU | Bldg #2 Type II - Lift-3 verticals | NOT YET STARTED | 2026-08-24 | 2026-08-24
ALTON DELRAY | CIP & CMU | Bldg #2 Type II - Lift-4 verticals | NOT YET STARTED | 2026-08-24 | 2026-08-24
ALTON DELRAY | CIP & CMU | Bldg #2 Type II - Lift-5 verticals | NOT YET STARTED | 2026-08-24 | 2026-08-24
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - 2nd floor slab | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - 3rd floor slab | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - 4th floor slab | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - 5th floor slab | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Roof slab | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Upper roof slab | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Tunnel walls | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Lift-1 verticals | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Lift-2 verticals | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Lift-3 verticals | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Lift-4 verticals | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Lift-5 verticals | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Lift-6 verticals | NOT YET STARTED | 2026-09-15 | 2026-09-15
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - 2nd floor slab | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - 3rd floor slab | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - 4th floor slab | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - 5th floor slab | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - 6th floor slab | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Roof slab | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Upper roof slab | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Tunnel walls | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Lift-1 verticals | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Lift-2 verticals | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Lift-3 verticals | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Lift-4 verticals | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Lift-5 verticals | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Lift-6 verticals | NOT YET STARTED | 2026-09-28 | 2026-09-28
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - 2nd floor slab | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - 3rd floor slab | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - 4th floor slab | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - 5th floor slab | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - 6th floor slab | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Roof slab | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Upper roof slab | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Tunnel walls | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Lift-1 verticals | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Lift-2 verticals | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Lift-3 verticals | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Lift-4 verticals | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Lift-5 verticals | NOT YET STARTED | 2026-09-30 | 2026-09-30
ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Lift-6 verticals | NOT YET STARTED | 2026-09-30 | 2026-09-30
Bird Arts | CIP & CMU | 2nd floor slab & beams | IN PROGRESS | 2026-08-15 | 2026-08-28 |  | Kameswari
Bird Arts | CIP & CMU | 3rd floor slab & beams | NOT YET STARTED
OLD PROJECTS MODIFICATIONS |  |  | COMPLETED
4543 DULCE VIDA | EMDS & BARLISTS | Garage Lvl-3 to 8 slabs EMDS | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
4541-Gables Cypress Creek | EMDS | BUILDING TYPE-V FOUNDATIONS (sub#26.1) | IN PROGRESS | 2026-04-14 | 2026-04-14 |  | chandra mouli | Chandra mouli
4543 DULCE VIDA | EMDS & BARLISTS | Main bldg roof slab | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
NOMI-6 | EMDS & BARLISTS | Lvl-4 slab markups & barlists | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Sai | Chandra mouli
4541-Gables Cypress Creek | EMDS & BARLISTS | Bldg. Type IV - Tunnel Walls submittal | IN PROGRESS | 2026-04-13 | 2026-04-13 |  | Swathi | Chandra mouli
NOMI-6 | BARLISTS | Satirs | COMPLETED | 2026-04-11 | 2026-04-11 |  | Sai | Chandra mouli
4541-Gables Cypress Creek | EMDS & BARLISTS | Building Type - I SOG | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
4541-Gables Cypress Creek | EMDS & BARLISTS | Building Type - I Tunnel walls | IN PROGRESS | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
4541-Gables Cypress Creek | EMDS & BARLISTS | Building Type -III Tunnel walls | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
Modera Boca Raton | EMDS | Columns lvl 4 to 8 | IN PROGRESS | 2026-01-12 | 2026-01-12 |  | Jagadeesh | Chandra mouli
NOMI-6 | EMDS | Slab edge reinf't addition | NOT YET STARTED | 2026-01-13 | 2026-01-13 |  | Swathi | Chandra mouli
Modera Boca Raton | EMDS | Columns 8th to roof | NOT YET STARTED | 2026-01-14 | 2026-01-14 |  | Swathi | Chandra mouli
4541-Gables Cypress Creek | EMDS & BARLISTS | Bldg. Type III 2nd floor slab | NOT YET STARTED | 2026-01-15 | 2026-01-15 |  | Swathi | Chandra mouli
4543 DULCE VIDA | EMDS & BARLISTS | Satirs 1&4 Grnd to L2 addition & barlists | COMPLETED | 2026-04-22 | 2026-04-22 |  | Sai | Chandra mouli
4541-Gables Cypress Creek | BARLISTS | 8"-Wall for Bldg.; Type IV - L1-L2 | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
2460 Australian (Ocean Tower) | EMAIL REQUEST | Change Elevator level -5-0" to -4'-0" & RFI 043, 20 | IN PROGRESS | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
NOMI-6 | EMAIL REQUEST | All floor balcony bars changed galvanized to black bars | COMPLETED | 2026-04-25 | 2026-04-25 |  | Sai | Chandra mouli
NOMI-6 | EMDS & BARLISTS | STAIR LEVEL 3 TO 4 | COMPLETED | 2026-04-25 | 2026-04-25 |  | Sai | Chandra mouli
NOMI-6 | PATCH LIST | Patch list for lift-3 column #60 | COMPLETED | 2026-04-25 | 2026-04-25 |  | Sai | Chandra mouli
4543 DULCE VIDA | EMDS & BARLISTS | Satirs #1 addition work | COMPLETED | 2026-04-25 | 2026-04-25 |  | Swathi | Chandra mouli
2460 Australian (Ocean Tower) | CO | Pilecaps & Gradebeams revision per RFI 24,11,12,35&39 responses | COMPLETED | 2026-05-01 | 2026-05-01 |  | Dhanush | Chandra mouli
Modera Boca Raton | BARLISTS | Ground Level Rebar Shop Drawings | COMPLETED | 2026-04-28 | 2026-04-28 |  | Nanaji | Chandra mouli
Modera Boca Raton | EMDS | Level-7 slab EMDS | COMPLETED | 2026-05-01 | 2026-05-01 |  | Nanaji | Chandra mouli
Modera Boca Raton | EMDS | Columns 35, 36, and 37 terminate below the pool slab | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
4541-Gables Cypress Creek | EMDS | Tunnel walls revision per RFI#35 | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
4541-Gables Cypress Creek | EMDS & BARLISTS | Bldg. Type II - SOG | COMPLETED | 2026-04-28 | 2026-04-28 |  | Swathi | Chandra mouli
NOMI-6 | EMDS & BARLISTS | Columns Lvl-4 to 5 pour separation | IN PROGRESS | 2026-04-29 | 2026-04-29 |  | Sai | Chandra mouli
Modera Boca Raton | EMDS | All slabs balconies galv bars. | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Nanaji | Chandra mouli
4541-Gables Cypress Creek | EMDS & BARLISTS | All bldgs tunnel walls candycane bars | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
4541-Gables Cypress Creek | EMDS & BARLISTS | Bldg. Type I & II RFI #98 fnds revision | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
NOMI-6 | EMDS & BARLISTS | columns, shear walls, slabs & stairs | COMPLETED | 2026-04-30 | 2026-04-30 |  | Sai | Chandra mouli
4541-Gables Cypress Creek | EMDS & BARLISTS | Bldg. Type IV - Level-2 | IN PROGRESS | 2026-05-05 | 2026-05-05 |  | Swathi | Chandra mouli
Modera Boca Raton | EMDS & BARLISTS | Ground Level Slab FFU drawings and bar lists. RFI #79 | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
2460 Australian (Ocean Tower) | EMDS & BARLISTS | Submittal 13- Ground Floor Slab | COMPLETED | 2026-05-04 | 2026-05-04 |  | Balaram | Chandra mouli
2460 Australian (Ocean Tower) | EMDS | Submittal 10- Steel Column Shop Drawings | COMPLETED | 2026-05-05 | 2026-05-05 |  | Sai | Chandra mouli
Adela II | EMDS | slabs markups | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
4541-Gables Cypress Creek | EMDS | remaining bldgs walls updated dwgs | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
NOMI-6 | EMDS & BARLISTS | lvl-5 barlists & lvl-4 release separation | COMPLETED | 2026-05-04 | 2026-05-04 |  | Sai | Chandra mouli
4543 DULCE VIDA | EMDS & BARLISTS | Lvl-2 drop beams for savers. | COMPLETED | 2026-05-04 | 2026-05-04 |  | Sai | Chandra mouli
Modera Boca Raton | CO | Revision per RFI #50, #67, #78 responses | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Sai | Chandra mouli
2460 Australian (Ocean Tower) | EMDS & BARLISTS | Pour separation | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Sai | Chandra mouli
Modera Boca Raton | EMDS & BARLISTS | Columns level 2 to Level 4 | COMPLETED | 2026-05-11 | 2026-05-11 |  | Nanaji | Chandra mouli
4541-Gables Cypress Creek | CO | RFI responses 86 & 95.1 | IN PROGRESS | 2026-05-11 | 2026-05-11 |  | Dhanush | Chandra mouli
Alexan margrate | EMDS | steel columns EMDS | COMPLETED | 2026-05-07 | 2026-05-07 |  | Sai | Chandra mouli
Modera Boca Raton | EMDS | Pet Wash details addition | COMPLETED | 2026-05-11 | 2026-05-11 |  | Nanaji | Chandra mouli
2460 Australian (Ocean Tower) | CO | RFI responses 25 & 27 | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Nanaji | Chandra mouli
4541-Gables Cypress Creek | EMDS & BARLISTS | Building Type V - SOG | NOT YET STARTED | 2026-05-09 | 2026-05-09 |  | Swathi | Chandra mouli
4541-Gables Cypress Creek | EMDS & BARLISTS | Building Type V - SOG | NOT YET STARTED | 2026-01-11 | 2026-01-11 |  | Swathi | Chandra mouli
4543 DULCE VIDA | EMDS & BARLISTS | male to female savers. | COMPLETED | 2026-05-12 | 2026-05-12 |  | Sai | Chandra mouli
NOMI-6 | EMDS & BARLISTS | Missing rebar for slab transitions on pool deck slab | COMPLETED | 2026-05-12 | 2026-05-12 |  | Sai | Chandra mouli
NOMI-6 | EMDS & BARLISTS | grade 80 grade 60 bars | IN PROGRESS | 2026-01-11 | 2026-01-11 |  | Sai | Chandra mouli
Modera Boca Raton | EMDS & BARLISTS | Level-7-11 verticals EMDS | COMPLETED | 2026-07-25 |  |  | Balaram
4541-Gables Cypress Creek | EMDS & BARLISTS | Patch list for Bldg. 2, 4-5 Type IV, I-II– ADD'LS @Balcony | hold | 2026-07-28 | 2026-07-24 |  | Swathi & Trisha
2460 Australian (Ocean Tower) | EMDS & BARLISTS | Precast stairs emds & Release separation | COMPLETED | 2026-07-24 | 2026-07-24 |  | Dhanush
Modera Boca Raton | EMDS & BARLISTS | Level-2 slab changes per RFI#84 | COMPLETED | 2026-07-24 |  |  | Balaram
Modera Boca Raton | EMDS & BARLISTS | Level-7 slab beam changes per email response | COMPLETED | 2026-07-24 |  |  | Sai
Modera Boca Raton | EMDS & BARLISTS | Level-3 slab changes per RFI#84 | COMPLETED | 2026-07-25 |  |  | Balaram
Modera Boca Raton | EMDS & BARLISTS | Ground slab changes and revised barlist for pour-G2 | COMPLETED | 2026-07-29 |  |  | chandra mouli
2460 Australian (Ocean Tower) | EMDS & BARLISTS | Shear walls verticals (single piece) patch list | COMPLETED | 2026-07-25 |  |  | Dhanush
Modera Boca Raton | EMDS & BARLISTS | Elevator walls EMDS | IN PROGRESS | 2026-07-28 |  |  | Swathi
Modera Boca Raton | EMDS & BARLISTS | Lift-2 to 4 CMU verticals EMDS | NOT YET STARTED | 2026-07-29 |  |  | Balaram
Modera Boca Raton | EMDS & BARLISTS | Submittal Distributed 47.1, Level 11 slab | NOT YET STARTED
Modera Boca Raton | EMDS & BARLISTS | Rebar at Placing Boom and Crane Openings Clarification | NOT YET STARTED
Modera Boca Raton | EMDS & BARLISTS | Submittal Distributed 57.1, CMU Walls Level 5 to Level 6 | NOT YET STARTED
Modera Boca Raton | EMDS & BARLISTS | Submittal Distributed 58.1, CMU Walls Level 6 to Level 7 | NOT YET STARTED
2460 Australian (Ocean Tower) | EMDS & BARLISTS | Tunnel walls pour- separation | IN PROGRESS | 2026-07-29 |  |  | Dhanush
2460 Australian (Ocean Tower) | EMDS & BARLISTS | 2nd floor slab pour separation & markups | IN PROGRESS | 2026-07-29 |  |  | Balaram
4541-Gables Cypress Creek | EMDS & BARLISTS | Bldg type-II 2nd to roof slab (patch list) | IN PROGRESS | 2026-07-30 |  |  | Trisha
Modera Boca Raton | EMDS & BARLISTS | Lift-1 verticals revision per typ detail | NOT YET STARTED | 2026-07-30 |  |  | Balaram
Modera Boca Raton | EMDS & BARLISTS | Submittal Distributed 59.1, CMU Walls Level 7 to Level 8 | NOT YET STARTED |  |  |  | Balaram
Modera Boca Raton | EMDS & BARLISTS | Submittal Distributed 72.1, Concrete Walls Elevator #4 | NOT YET STARTED | 2026-07-30 |  |  | Swathi