## PROJECTS
PROJECT STATUS
|  | Customer | Formcrete
|  | Last updated date | 2026-04-10
S.No | BILL STATUS | PROJECT NAME | SCOPE | DWG NO. | COMPONENTS OF WORK | REC. DATE | STATUS | SUB. DATE | CUST. REQ. DATE | EXP. WT/HRS | DET. WT. | HRS | C.O. | DETAILER | CHECKER | REMARKS
1 |  | Modera Boca Raton | CIP & CMU | R1 | BASEMENT SLAB ON GRADE | 2025-10-07 | COMPLETED | 2025-12-15 |  |  | 4.664
|  | Modera Boca Raton | CIP & CMU | R2 TO R2J | GROUND FLOOR SLAB (GARAGE AREA) | 2025-10-07 | COMPLETED | 2025-12-06 |  |  | 28.082
|  | Modera Boca Raton | CIP & CMU | R3 TO R3B | GROUND FLOOR SLAB (RESIDENTIAL AREA) | 2025-10-07 | COMPLETED | 2025-12-06 |  |  | 8.677
|  | Modera Boca Raton | CIP & CMU | R4 TO R4B | BASEMENT RETAINIG WALLS & CMU WALLS | 2025-10-07 | COMPLETED | 2026-01-08 |  |  | 22.254
|  | Modera Boca Raton | CIP & CMU | R5 TO R5D | 2ND FLR GARAGE SLAB | 2025-10-07 | COMPLETED | 2026-01-24 |  |  | 25.559
|  | Modera Boca Raton | CIP & CMU | R6 TO R6G | 2ND FLR RESIDENTIAL SLAB | 2025-10-07 | COMPLETED | 2026-01-24 |  |  | 17.587
|  | Modera Boca Raton | CIP & CMU | R7 TO R7D | 3RD FLR GARAGE SLAB | 2025-10-07 | COMPLETED | 2026-03-20 |  |  | 17.318
|  | Modera Boca Raton | CIP & CMU | R8 TO R8H | 3RD FLR RESIDENTIAL SLAB | 2025-10-07 | COMPLETED | 2026-03-20 |  |  | 26.389
|  | Modera Boca Raton | CIP & CMU | R9 TO R9K | SHEAR WALLS (LVL-2 TO LVL-8) | 2025-10-07 | COMPLETED | 2026-03-06 |  |  | 82.779
|  | Modera Boca Raton | CIP & CMU | R10 TO R10F | SHEAR WALLS (LVL-8 TO BULK HEAD) | 2025-10-07 | COMPLETED | 2026-02-28 |  |  | 36.429
|  | Modera Boca Raton | CIP & CMU | R11 TO R11K | LEVEL-2 TO LEVEL-4 COLUMNS | 2025-10-07 | COMPLETED | 2026-03-27 |  |  | 55.059
|  | Modera Boca Raton | CIP & CMU | R12 TO R12D | 4TH FLR GARAGE SLAB | 2025-10-07 | COMPLETED | 2026-04-07 |  |  | 17.656
|  | Modera Boca Raton | CIP & CMU | R13 TO R13H | 4TH FLR RESIDENTIAL SLAB | 2025-10-07 | COMPLETED | 2026-04-07 |  |  | 23.397
|  | Modera Boca Raton | CIP & CMU | R14 TO R14D | 5TH FLR GARAGE SLAB | 2025-10-07 | COMPLETED | 2026-04-07 |  |  | 17.642
|  | Modera Boca Raton | CIP & CMU | R15 TO R15H | 5TH FLR RESIDENTIAL SLAB | 2025-10-07 | COMPLETED | 2026-04-07 |  |  | 23.397
|  | Modera Boca Raton | CIP & CMU | R16 TO R16D | 6TH FLR GARAGE SLAB | 2025-10-07 | COMPLETED | 2026-04-10 |  |  | 17.161 |  |  | Nanaji
|  | Modera Boca Raton | CIP & CMU | R17 TO R17H | 6TH FLR RESIDENTIAL SLAB | 2025-10-07 | COMPLETED | 2026-04-10 |  |  | 23.382 |  |  | Nanaji
|  | Modera Boca Raton | CIP & CMU | R18 | LEVEL-4 TO LEVEL-8 COLUMNS | 2025-10-07 | COMPLETED | 2026-04-13 |  |  | 118.63 |  |  | Jagadeesh
|  | Modera Boca Raton | CIP & CMU | R19 | 7TH FLR SLAB | 2025-10-07 | COMPLETED | 2026-04-17 |  |  | 92.114 |  |  | Nanaji
|  | Modera Boca Raton | CIP & CMU | R20 | 8TH FLR SLAB | 2025-10-07 | COMPLETED | 2026-05-01 | 2026-04-23 |  | 90.716 |  |  | Swathi
|  | Modera Boca Raton | CIP & CMU | R21 | LEVEL-8 TO ROOF COLUMNS | 2025-10-07 | COMPLETED | 2026-04-17 |  |  | 30.34 |  |  | Jagadeesh
|  | Modera Boca Raton | CIP & CMU | R22 | 9TH FLR SLAB | 2025-10-07 | COMPLETED | 2026-05-06 | 2026-04-23 |  | 31.857 |  |  | Swathi
|  | Modera Boca Raton | CIP & CMU | R23 | 10TH FLR SLAB | 2025-10-07 | COMPLETED | 2026-05-06 | 2026-04-23 |  | 31.857 |  |  | Swathi
|  | Modera Boca Raton | CIP & CMU | R25 | 11TH FLR SLAB | 2025-10-07 | COMPLETED | 2026-05-14 | 2026-04-26 |  |  |  |  | Swathi
|  | Modera Boca Raton | CIP & CMU | R26 | 12TH FLR SLAB | 2025-10-07 | COMPLETED | 2026-05-14 | 2026-04-30 |  |  |  |  | Balaram & Swathi
|  | Modera Boca Raton | CIP & CMU | R28 | 12TH MEZZ FLR SLAB | 2025-10-07 | COMPLETED | 2026-05-15 | 2026-04-30 |  |  |  |  | Sai
|  | Modera Boca Raton | CIP & CMU | R30 | ROOF SLAB | 2025-10-07 | COMPLETED | 2026-05-18 | 2026-05-14 |  |  |  |  | Swathi
|  | Modera Boca Raton | CIP & CMU | R31 | HIGH ROOF SLAB | 2025-10-07 | COMPLETED | 2026-05-18 | 2026-05-14
|  | Modera Boca Raton | CIP & CMU | R32 | GROUND LEVEL TO 2ND LEVEL TC & CMU WALLS | 2025-10-07 | COMPLETED
|  | Modera Boca Raton | CIP & CMU | R33 | 2ND LEVEL TO 3RD LEVEL TC & CMU WALLS | 2025-10-07 | COMPLETED | 2026-05-29 |  |  | 12.755 |  |  | Balaram
|  | Modera Boca Raton | CIP & CMU | R34 | 3RD LEVEL TO 4TH LEVEL TC & CMU WALLS | 2025-10-07 | COMPLETED | 2026-06-02 | [5 empty] | Balaram
|  | Modera Boca Raton | CIP & CMU | R35 | 4TH LEVEL TO 5TH LEVEL TC & CMU WALLS | 2025-10-07 | COMPLETED | [6 empty] | Balaram
|  | Modera Boca Raton | CIP & CMU | R36 | 5TH LEVEL TO 6TH LEVEL TC & CMU WALLS | 2025-10-07 | COMPLETED | [6 empty] | Balaram
|  | Modera Boca Raton | CIP & CMU | R37 | 6TH LEVEL TO 7TH LEVEL TC & CMU WALLS | 2025-10-07 | COMPLETED | [6 empty] | Balaram
|  | Modera Boca Raton | CIP & CMU | R38 | 7TH LEVEL TO 8TH LEVEL TC & CMU WALLS | 2025-10-07 | COMPLETED | [6 empty] | Balaram
|  | Modera Boca Raton | CIP & CMU | R39 | 8TH LEVEL TO 9TH LEVEL TC & CMU WALLS | 2025-10-07 | IN PROGRESS | [6 empty] | Balaram
|  | Modera Boca Raton | CIP & CMU | R40 | 9TH LEVEL TO 10TH LEVEL TC & CMU WALLS | 2025-10-07 | NOT YET STARTED
|  | Modera Boca Raton | CIP & CMU | R41 | 10TH LEVEL TO 11TH LEVEL TC & CMU WALLS | 2025-10-07 | NOT YET STARTED
|  | Modera Boca Raton | CIP & CMU | R42 | 11TH LEVEL TO 12TH LEVEL TC & CMU WALLS | 2025-10-07 | NOT YET STARTED
|  | Modera Boca Raton | CIP & CMU | R43 | 12TH LEVEL TO 12TH MEZZ LEVEL TC & CMU WALLS | 2025-10-07 | NOT YET STARTED
|  | Modera Boca Raton | CIP & CMU | R44 | 12TH MEZZ LEVEL TO ROOF LEVEL TC & CMU WALLS | 2025-10-07 | NOT YET STARTED
|  | Modera Boca Raton | CIP & CMU | R45 | ROOF LEVEL TO HIGH ROOF TC & CMU WALLS | 2025-10-07 | NOT YET STARTED
2 |  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTI-R1 TO R1C | BUILDING TYPE-I FOUNDATIONS | 2025-11-11 | COMPLETED | 2025-12-03 |  |  | 19.937 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTI-R2 & R2A | BUILDING TYPE-I SLAB ON GRADE | 2025-11-11 | COMPLETED | 2026-01-02 |  |  | 1.981 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTI-R3 TO R3G | BUILDING TYPE-I TUNNEL WALLS | 2025-11-11 | COMPLETED | 2026-01-19 |  |  | 30.005 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-I LIFT-1 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-I 2ND FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-I LIFT-2 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-I 3rd FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-I LIFT-3 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-I 4th FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-I LIFT-4 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-I 5th FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-I LIFT-5 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-I ROOF SLAB & BEAMS WITH PARAPET | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTII-R1 TO R1C | BUILDING TYPE-II FOUNDATIONS | 2025-11-11 | COMPLETED | 2026-01-22 |  |  | 17.995 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTII-R2 | BUILDING TYPE-II SLAB ON GRADE | 2025-11-11 | COMPLETED | 2026-01-27 |  |  | 1.461 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-II TUNNEL WALLS | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-II LIFT-1 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-II 2ND FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-II LIFT-2 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-II 3rd FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-II LIFT-3 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-II 4th FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-II LIFT-4 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-II 5th FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-II LIFT-5 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-II ROOF SLAB & BEAMS WITH PARAPET | 2025-11-11 | IN PROGRESS
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTIII-R1 TO R1C | BUILDING TYPE-III FOUNDATIONS | 2025-11-11 | COMPLETED | 2025-12-13 |  |  | 17.755 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTIII-R2 | BUILDING TYPE-III SLAB ON GRADE | 2025-11-11 | COMPLETED | 2025-12-22 |  |  | 1.637 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTIII-R3 TO R3F | BUILDING TYPE-III TUNNEL WALLS | 2025-11-11 | COMPLETED | 2026-01-19 |  |  | 25.123 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTIII-R4 & R4A | BUILDING TYPE-III LIFT-1 VERTICALS (CMU & COLUMNS) | 2025-11-11 | COMPLETED | 2026-02-04 |  |  | 3.469 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTIII-R5 TO R5C | BUILDING TYPE-III 2ND FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED | 2026-03-23 |  |  | 21.957 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-III LIFT-2 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-III 3rd FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED | 2026-05-18 | [5 empty] | Trisha
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-III LIFT-3 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-III 4th FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-III LIFT-4 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-III 5th FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-III LIFT-5 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-III ROOF SLAB & BEAMS WITH PARAPET | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTIV-R1 TO R1G | BUILDING TYPE-IV FOUNDATIONS | 2025-11-11 | COMPLETED | 2025-01-02 |  |  | 51.958 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTIV-R2 & R2A | BUILDING TYPE-IV SLAB ON GRADE | 2025-11-11 | COMPLETED | 2025-12-24 |  |  | 2.047 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTIV-R3 TO R3J | BUILDING TYPE-IV TUNNEL WALLS | 2025-11-11 | COMPLETED | 2026-01-19 |  |  | 41.043 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTIV-R4 TO R4C | BUILDING TYPE-IV LIFT-1 VERTICALS | 2025-11-11 | COMPLETED | 2026-02-11 |  |  | 16.144 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-IV 2ND FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED | 2026-04-10 |  |  | 87.972 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-IV LIFT-2 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-IV 3rd FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED | 2026-04-24 |  |  | 27.95 |  |  | Trisha
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-IV LIFT-3 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-IV 4th FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED | 2026-05-04 | [5 empty] | Trisha
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-IV LIFT-4 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-IV 5th FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED | 2026-05-04 | [5 empty] | Trisha
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-IV LIFT-5 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-IV ROOF SLAB & BEAMS WITH PARAPET | 2025-11-11 | COMPLETED
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTV-R1 TO R1D | BUILDING TYPE-V FOUNDATIONS | 2025-11-11 | COMPLETED | 2026-02-13 |  |  | 25.382 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-V SLAB ON GRADE | 2025-11-11 | COMPLETED | 2026-04-14 | [5 empty] | Balaram
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BTV-R3 | BUILDING TYPE-V TUNNEL WALLS | 2025-11-11 | COMPLETED | 2026-04-18 |  |  | 30.927
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-V LIFT-1 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-V 2ND FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED | 2026-04-23 |  |  | 24.656 |  |  | Swathi
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-V LIFT-2 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-V 3rd FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED | 2026-04-25 |  |  | 22.572 |  |  | Trisha
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-V LIFT-3 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-V 4th FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED | 2026-04-28 |  |  | 22.607 |  |  | Trisha
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-V LIFT-4 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-V 5th FLR. SLAB & BEAMS | 2025-11-11 | COMPLETED | 2026-04-28 |  |  | 22.893 |  |  | Trisha
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-V LIFT-5 VERTICALS | 2025-11-11 | NOT YET STARTED
|  | 4541-Gables Cypress Creek | CIP & CMU |  | BUILDING TYPE-V ROOF SLAB & BEAMS WITH PARAPET | 2025-11-11 | COMPLETED | 2026-05-16 |  |  | 28.225 |  |  | Trisha
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-BS-R1 | BIKE STORAGE & PET SPA BLDG. | 2025-11-11 | COMPLETED | 2025-12-01 |  |  | 1.257
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-GT1-R1 | GARAGE TYPE-1 | 2025-11-11 | COMPLETED | 2025-12-15 |  |  | 3.232
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-TE-R1 | TRASH ENCLOSURE | 2025-11-11 | COMPLETED | 2026-01-02 |  |  | 3.418
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-GT4-R1 | GARAGE TYPE-4 | 2025-11-11 | COMPLETED | 2025-12-15 |  |  | 2.088
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-GT2-R1 & R1A | GARAGE TYPE-2 | 2025-11-11 | COMPLETED | 2025-12-27 |  |  | 2.567
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-GT3-R1 & R1A | GARAGE TYPE-3 | 2025-11-11 | COMPLETED | 2025-12-30 |  |  | 2.545
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-PP-R1 & R1A | POOL PAVILION | 2025-11-11 | COMPLETED | 2026-01-02 |  |  | 1.76
|  | 4541-Gables Cypress Creek | CIP & CMU | 4541_GCC-MB-R1 | MAITAINANCE BUIDLING | 2025-11-11 | COMPLETED | 2026-01-02 |  |  | 1.187
3 |  | NOMI-6 | CIP & CMU | R1 & R1A | LIFT-1 COLUMN VERTICALS | 2025-12-18 | COMPLETED | 2025-12-29 |  |  | 50.079 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R2 & R2A | LIFT-1 & LIFT-2 SHEAR WALLS | 2025-12-18 | COMPLETED | 2026-01-02 |  |  | 23.387 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R3 TO R3B | STEM WALLS | 2025-12-18 | COMPLETED | 2025-01-09 |  |  | 8.493 |  |  | Sridevi
|  | NOMI-6 | CIP & CMU | R4 TO R4B | LIFT-1 CMU VERTICALS | 2025-12-18 | COMPLETED | 2025-01-10 |  |  | 13.423 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R5 & R5A | LIFT-1 STAIRS | 2025-12-18 | COMPLETED | 2025-01-10 |  |  | 2.346 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R6 & R6A | PIERS | 2025-12-18 | COMPLETED | 2026-03-03 |  |  | 6.595 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R7 TO R7E | 2ND FLOOR SLAB | 2025-12-18 | COMPLETED | 2026-03-10 |  |  | 45.947 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R8 TO R8L | LIFT-2 & 3 Columns | 2025-12-18 | COMPLETED | 2026-03-17 |  |  | 26.878 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R9 & R9A | LIFT-2 & 3 SHEAR WALLS | 2025-12-18 | COMPLETED | 2026-03-17 |  |  | 22.937 |  |  | Jagadeesh
|  | NOMI-6 | CIP & CMU | R10 & R10A | STAIRS (UP TO LVL.-4) | 2025-12-18 | COMPLETED | 2026-03-20 |  |  | 2.386 |  |  | Jagadeesh
|  | NOMI-6 | CIP & CMU | R11 TO R11D | 3RD FLOOR SLAB & BEAMS | 2025-12-18 | COMPLETED | 2026-03-21 |  |  | 44.076 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R12 TO R12H | 4TH FLOOR SLAB & BEAMS | 2025-12-18 | COMPLETED | 2026-04-04 |  |  | 100.479 |  |  | Sai & Swathi
|  | NOMI-6 | CIP & CMU | R13 | 5th FLOOR SLAB & BEAMS | 2025-12-18 | COMPLETED | 2026-04-24 |  |  | 32.738 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R14 | 6th FLOOR SLAB & BEAMS | 2025-12-18 | COMPLETED | 2026-04-24 |  |  | 32.258 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R15 | 7th FLOOR SLAB & BEAMS | 2025-12-18 | COMPLETED | 2026-04-24 |  |  | 32.258 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R16 | 8th FLOOR SLAB & BEAMS | 2025-12-18 | COMPLETED | 2026-05-04 |  |  | 37.186 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R17 | 9th FLOOR SLAB & BEAMS | 2025-12-18 | COMPLETED | 2026-05-04 |  |  | 37.186
|  | NOMI-6 | CIP & CMU | R18 | 10th FLOOR SLAB & BEAMS | 2025-12-18 | COMPLETED | 2026-05-28 |  |  | 38.226
|  | NOMI-6 | CIP & CMU | R19 | 11th FLOOR SLAB & BEAMS | 2025-12-18 | IN PROGRESS | 2026-06-26
|  | NOMI-6 | CIP & CMU | R20 | ROOF FLOOR SLAB & BEAMS | 2025-12-18 | NOT YET STARTED |  | 2026-07-06
|  | NOMI-6 | CIP & CMU | R20 | ELEVATOR, STAIR LIDS & PARAPET WALLS | 2025-12-18 | NOT YET STARTED |  | 2026-07-24
|  | NOMI-6 | CIP & CMU | R21 | LIFT-4 COLUMNS | 2025-12-18 | COMPLETED | 2026-04-28 |  |  | 13.962 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R21 | LIFT-5&6 COLUMNS | 2025-12-18 | COMPLETED | 2026-05-06 |  |  | 22.86 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R22 | LIFT-4 & 5 SHEAR WALLS | 2025-12-18 | COMPLETED | [6 empty] | Balaram
|  | NOMI-6 | CIP & CMU | R23 | LIFT-7 & 8 COLUMNS | 2025-12-18 | COMPLETED | 2026-05-06 |  |  | 22.86 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R24 | LIFT-6 & 7 SHEAR WALLS | 2025-12-18 | COMPLETED | 2026-05-09 |  |  | 14.422 |  |  | Sai
|  | NOMI-6 | CIP & CMU | R25 | LIFT-9 & 10 COLUMNS | 2025-12-18 | NOT YET STARTED |  | 2026-06-13
|  | NOMI-6 | CIP & CMU | R26 | LIFT-8 & 9 SHEAR WALLS | 2025-12-18 | NOT YET STARTED
|  | NOMI-6 | CIP & CMU | R27 | LIFT-11 COLUMNS | 2025-12-18 | NOT YET STARTED |  | 2026-06-26
|  | NOMI-6 | CIP & CMU | R28 | LIFT-10 & 11 SHEAR WALLS | 2025-12-18 | NOT YET STARTED |  | 2026-06-23
|  | NOMI-6 | CIP & CMU | R29 | STAIRS (LEVEL-4 TO LEVEL-6) | 2025-12-18 | COMPLETED | 2026-04-29 | [5 empty] | Sai
|  | NOMI-6 | CIP & CMU | R30 | STAIRS (LEVEL-6 TO ROOF) | 2025-12-18 | COMPLETED | 2026-06-05
|  | NOMI-6 | CIP & CMU | R34 | LIFT-2 CMU VERTICALS | 2025-12-18 | NOT YET STARTED |  | 2026-06-17
|  | NOMI-6 | CIP & CMU | R35 | LIFT-3 CMU VERTICALS | 2025-12-18 | NOT YET STARTED |  | 2026-06-17
|  | NOMI-6 | CIP & CMU | R36 | LIFT-4 CMU VERTICALS | 2025-12-18 | NOT YET STARTED |  | 2026-06-19
|  | NOMI-6 | CIP & CMU | R37 | LIFT-5 CMU VERTICALS | 2025-12-18 | NOT YET STARTED |  | 2026-06-23
|  | NOMI-6 | CIP & CMU | R38 | LIFT-6 CMU VERTICALS | 2025-12-18 | NOT YET STARTED |  | 2026-06-25
|  | NOMI-6 | CIP & CMU | R39 | LIFT-7 CMU VERTICALS | 2025-12-18 | NOT YET STARTED |  | 2026-06-25
|  | NOMI-6 | CIP & CMU | R40 | LIFT-8 CMU VERTICALS | 2025-12-18 | NOT YET STARTED |  | 2026-06-29
|  | NOMI-6 | CIP & CMU | R41 | LIFT-9 CMU VERTICALS | 2025-12-18 | NOT YET STARTED |  | 2026-07-01
|  | NOMI-6 | CIP & CMU | R42 | LIFT-10 CMU VERTICALS | 2025-12-18 | NOT YET STARTED |  | 2026-07-03
|  | NOMI-6 | CIP & CMU | R43 | LIFT-11 CMU VERTICALS | 2025-12-18 | NOT YET STARTED |  | 2026-07-07
4 |  | 4543 DULCE VIDA | CIP & CMU | R1 TO R1E | 2ND FLOOR SLAB (RESIDENTIAL) | 2026-01-13 | COMPLETED | 2026-02-05 |  |  | 23.071
|  | 4543 DULCE VIDA | CIP & CMU | R2 TO R2E | 2ND FLOOR SLAB (GARAGE) | 2026-01-13 | COMPLETED | 2026-02-05 |  |  | 26.205 |  |  | Sai
|  | 4543 DULCE VIDA | CIP & CMU | R3 TO R3E | 3RD FLOOR SLAB (RESIDENTIAL) | 2026-01-13 | COMPLETED | 2026-02-28 |  |  | 21.963
|  | 4543 DULCE VIDA | CIP & CMU | R4 TO R4D | 3RD FLOOR SLAB (GARAGE) | 2026-01-13 | COMPLETED | 2026-02-27 |  |  | 25.524 |  |  | Sai
|  | 4543 DULCE VIDA | CIP & CMU | R5 TO R5E | 4TH FLOOR SLAB (RESIDENTIAL) | 2026-01-13 | COMPLETED | 2026-02-28 |  |  | 21.534
|  | 4543 DULCE VIDA | CIP & CMU | R6 TO R6D | 4TH FLOOR SLAB (GARAGE) | 2026-01-13 | COMPLETED | 2026-02-27 |  |  | 25.367 |  |  | Sai
|  | 4543 DULCE VIDA | CIP & CMU | R7 TO R7E | 5TH FLOOR SLAB (RESIDENTIAL) | 2026-01-13 | COMPLETED | 2026-02-14 |  |  | 22.122
|  | 4543 DULCE VIDA | CIP & CMU | R8 TO R8D | 5TH FLOOR SLAB (GARAGE) | 2026-01-13 | COMPLETED | 2026-02-27 |  |  | 25.353 |  |  | Sai
|  | 4543 DULCE VIDA | CIP & CMU | R9 TO R9E | 6TH FLOOR SLAB (RESIDENTIAL) | 2026-01-13 | COMPLETED | 2026-02-14 |  |  | 22.123
|  | 4543 DULCE VIDA | CIP & CMU | R10 TO R10D | 6TH FLOOR SLAB (GARAGE) | 2026-01-13 | COMPLETED | 2026-02-28 |  |  | 25.385 |  |  | Sai
|  | 4543 DULCE VIDA | CIP & CMU | R11 TO R11E | 7TH FLOOR SLAB (RESIDENTIAL) | 2026-01-13 | COMPLETED | 2026-02-14 |  |  | 22.124
|  | 4543 DULCE VIDA | CIP & CMU | R12 TO R12D | 7TH FLOOR SLAB (GARAGE) | 2026-01-13 | COMPLETED | 2026-02-28 |  |  | 27.222 |  |  | Sai
|  | 4543 DULCE VIDA | CIP & CMU | R13 TO R13E | 8TH FLOOR SLAB (RESIDENTIAL) | 2026-01-13 | COMPLETED | 2026-02-14 |  |  | 22.123
|  | 4543 DULCE VIDA | CIP & CMU | R14 TO R14D | 8TH FLOOR AND ROOF SLAB (GARAGE) | 2026-01-13 | COMPLETED | 2026-02-28 |  |  | 15.783 |  |  | Sai
|  | 4543 DULCE VIDA | CIP & CMU | R15 TO R15G | ROOF SLAB (RESIDENTIAL) | 2026-01-13 | COMPLETED | 2026-02-16 |  |  | 33.383
|  | 4543 DULCE VIDA | CIP & CMU | R16 & R16A | STAIR #1 (GROUND FLOOR TO ROOF) | 2026-01-13 | COMPLETED | 2026-03-13 |  |  | 2.56 |  |  | Sai
|  | 4543 DULCE VIDA | CIP & CMU | R17 & R17A | STAIR #2 (GROUND FLOOR TO ROOF) | 2026-01-13 | COMPLETED | 2026-03-13 |  |  | 3.099
|  | 4543 DULCE VIDA | CIP & CMU | R18 & R18A | STAIR #3 (GROUND FLOOR TO ROOF) | 2026-01-13 | COMPLETED | 2026-03-13 |  |  | 2.217
|  | 4543 DULCE VIDA | CIP & CMU | R19 & R19A | STAIR #4 (GROUND FLOOR TO ROOF) | 2026-01-13 | COMPLETED | 2026-03-13 |  |  | 2.782
5 |  | 2460 Australian (Ocean Tower) | STEEL | BOT-S1 TO S17 | STEEL COLUMNS | 2026-01-13 | COMPLETED | 2026-02-09 | [5 empty] | Sai
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R1, R1A TO R1D | PILE CAPS | 2026-01-13 | COMPLETED | 2026-02-12 | 2026-04-13 |  | 82.838 |  |  | Sridevi
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R2, R2A TO R2D | GRADE BEAMS | 2026-01-13 | IN PROGRESS | 2026-04-02 | 2026-04-13 |  | 118.168 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R3, R3A TO R3E | SLAB ON GRADE | 2026-01-13 | COMPLETED | 2026-04-20 | 2026-04-20 |  | 51.778 |  |  | Balaram
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R4, R4A TO R4C | LIFT -1 VERTICALS CMU & COLUMS | 2026-01-13 | COMPLETED |  | 2026-04-24 |  | 24.817 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R5, R5A TO R5T | TUNNEL WALLS | 2026-01-13 | COMPLETED | 2026-05-01 | 2026-04-24 |  | 71.82 |  |  | Balaram
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R6 , R6A TO R6J | 2ND FLR. SLAB & BEAMS | 2026-01-13 | COMPLETED | 2026-05-08 | 2026-04-27 |  | 85.402 |  |  | Balaram
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R7, R7A & R7B | LIFT -2 VERTICALS CMU & COLUMS | 2026-01-13 | COMPLETED | 2026-05-08 | 2026-04-30 |  | 5.969 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | SK1 | RETAIINING WALL | 2026-01-13 | COMPLETED | 2026-05-08 | 2026-04-30 |  | 2.214 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R8 , R8A TO R8F | 3RD FLR. SLAB & BEAMS | 2026-01-13 | COMPLETED | 2026-05-15 | 2026-05-04 |  | 4.462 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R9 , R9A & R9B | LIFT -3 VERTICALS CMU & COLUMS | 2026-01-13 | COMPLETED | 2026-05-15 | 2026-05-05 |  | 34.412 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R10 | 4TH FLR. SLAB & BEAMS | 2026-01-13 | COMPLETED | 2026-05-22 | 2026-05-08 |  | 34.413 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R11 | LIFT -4 VERTICALS CMU & COLUMS | 2026-01-13 | COMPLETED | 2026-05-22 | 2026-05-11 |  | 4.381 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R12 | 5TH FLR. SLAB & BEAMS | 2026-01-13 | COMPLETED | 2026-05-28 | 2026-05-15 |  | 34.313 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R13 | LIFT -5 VERTICALS CMU & COLUMS | 2026-01-13 | COMPLETED | 2026-05-28 | 2026-05-21 |  | 4.388 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R14 | 6TH FLR. SLAB & BEAMS | 2026-01-13 | COMPLETED | 2026-05-28 | 2026-05-25 |  | 34.313 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R15 | LIFT -6 VERTICALS CMU & COLUMS | 2026-01-13 | COMPLETED | 2026-05-28 | 2026-06-01 |  | 4.388 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R16 | 7TH FLR. SLAB & BEAMS | 2026-01-13 | COMPLETED | 2026-05-28 | 2026-06-03 |  | 34.313 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R17 | LIFT -7 VERTICALS CMU & COLUMS | 2026-01-13 | COMPLETED | 2026-05-28 | 2026-06-08 |  | 4.388 |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R18 | 8TH FLR. SLAB & BEAMS | 2026-01-13 | COMPLETED | 2026-06-03 | 2026-06-10 |  |  |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R19 | LIFT -8 VERTICALS CMU & COLUMS | 2026-01-13 | COMPLETED | 2026-06-05 | 2026-06-15 |  |  |  |  | Dhanush
|  | 2460 Australian (Ocean Tower) | CIP & CMU | R20 | ROOF SLAB & BEAMS WITH PARAPET | 2026-01-13 | IN PROGRESS |  | 2026-06-17 |  |  |  |  | Dhanush
6 |  | Magnolia Point | STEEL |  | BLDG 1 Type II | 2026-04-27 | COMPLETED | 2026-05-29 | 2026-05-20
|  | Magnolia Point | STEEL |  | BLDG 2 Type VI | 2026-04-27 | COMPLETED | 2026-05-29 | 2026-05-20
|  | Magnolia Point | STEEL |  | BLDG 3 Type V | 2026-04-27 | COMPLETED | 2026-05-29 | 2026-05-20
|  | Magnolia Point | STEEL |  | BLDG 4 Type III | 2026-04-27 | COMPLETED | 2026-05-29 | 2026-05-20
|  | Magnolia Point | STEEL |  | BLDG 5 Type VII | 2026-04-27 | COMPLETED | 2026-05-29 | 2026-05-20
|  | Magnolia Point | STEEL |  | Clubhouse | 2026-04-27 | COMPLETED | 2026-05-29 | 2026-05-20
|  | Magnolia Point | CIP & CMU |  | Clubhouse - Foundations & SOG | 2026-04-27 | COMPLETED | 2026-06-01 |  |  | 4.171 |  |  | Chandra mouli
|  | Magnolia Point | CIP & CMU |  | Clubhouse - Lift-1 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | Clubhouse - Roof slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | Clubhouse - Parapet & Trellis slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | Trash enclosure | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - Foundations & SOG | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - 2nd floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - 3rd floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - 4th floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - 5th floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - 6th floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - Roof level slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - Lift-1 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - Lift-2 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - Lift-3 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - Lift-4 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - Lift-5 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 3 Type V - Lift-6 & parapet verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - Foundations & SOG | 2026-04-27 | NOT YET STARTED |  |  | 700
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - 2nd floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - 3rd floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - 4th floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - 5th floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - 6th floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - Roof level slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - Lift-1 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - Lift-2 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - Lift-3 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - Lift-4 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - Lift-5 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 1 Type II - Lift-6 & parapet verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - Foundations & SOG | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - 2nd floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - 3rd floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - 4th floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - 5th floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - 6th floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - Roof level slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - Lift-1 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - Lift-2 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - Lift-3 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - Lift-4 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - Lift-5 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 2 Type VI - Lift-6 & parapet verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 5 Type VII - Foundations & SOG | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 5 Type VII - 2nd floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 5 Type VII - 3rd floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 5 Type VII - Roof level slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 5 Type VII - Lift-1 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 5 Type VII - Lift-2 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 5 Type VII - Lift-3 & parapet verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 4 Type III - Foundations & SOG | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 4 Type III - 2nd floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 4 Type III - 3rd floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 4 Type III - 4th floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 4 Type III - 5th floor slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 4 Type III - Roof level slab | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 4 Type III - Lift-1 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 4 Type III - Lift-2 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 4 Type III - Lift-3 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 4 Type III - Lift-4 verticals | 2026-04-27 | NOT YET STARTED
|  | Magnolia Point | CIP & CMU |  | BLDG 4 Type III - Lift-5 & parapet verticals | 2026-04-27 | NOT YET STARTED
7 |  | Hilltop Gardens | STEEL |  | Building _1 Type III | 2026-04-27 | COMPLETED | 2026-05-29
|  | Hilltop Gardens | STEEL |  | Building _2 Type II | 2026-04-27 | COMPLETED | 2026-05-29
|  | Hilltop Gardens | STEEL |  | Building _3 Type II | 2026-04-27 | COMPLETED | 2026-05-29
|  | Hilltop Gardens | STEEL |  | Building _4 Type I | 2026-04-27 | COMPLETED | 2026-05-29
|  | Hilltop Gardens | STEEL |  | Building _5 Type I | 2026-04-27 | COMPLETED | 2026-05-29
|  | Hilltop Gardens | STEEL |  | Building _6 Type I | 2026-04-27 | COMPLETED | 2026-05-29
|  | Hilltop Gardens | STEEL |  | Clubhouse | 2026-04-27 | COMPLETED | 2026-05-29
8 |  | Altis Delray | STEEL |  | Building Type I | 2026-04-27 | COMPLETED | 2026-05-29
|  | Altis Delray | STEEL |  | Building Type II | 2026-04-27 | COMPLETED | 2026-05-29
|  | Altis Delray | STEEL |  | Building Type IIM | 2026-04-27 | COMPLETED | 2026-05-29
|  | Altis Delray | STEEL |  | Building Type III | 2026-04-27 | COMPLETED | 2026-05-29
|  | Altis Delray | STEEL |  | Clubhouse | 2026-04-27 | COMPLETED | 2026-05-29
9 |  | Octavia | STEEL |  | Steel columns | 2026-05-01 | COMPLETED | 2026-05-21
9 |  | Octavia | STEEL |  | Elevator mat footings | 2026-05-01 | COMPLETED | 2026-05-27 |  |  | 31.278
|  | Octavia | CIP & CMU |  | Deep footings | 2026-05-01 | NOT YET STARTED |  |  | 1000
|  | Octavia | CIP & CMU |  | Garage - Cont ftgs | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence - Cont ftgs | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Garage Slab on grade | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence Slab on grade | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Garage Shear walls | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence Shear walls | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Garage Columns | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence Columns | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Garage Stairs | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence Stairs | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | GarageLevel-1.5 slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Garage 2nd floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence 2nd floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Garage 3rd floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence 3rd floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Garage 4th floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence 4th floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Garage 5th floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence 5th floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Garage 6th floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence 6th floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Garage 7th floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence7th floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Garage 8th floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence 8th floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Residence Roof floor slab & beams | 2026-05-01 | NOT YET STARTED
|  | Octavia | CIP & CMU |  | Upper roof slab & beams | 2026-05-01 | NOT YET STARTED
|  | OLD PROJECTS MODIFICATIONS |  |  |  |  | COMPLETED
1 |  | 4543 DULCE VIDA | EMDS & BARLISTS |  | Garage Lvl-3 to 8 slabs EMDS | 2026-04-09 | NOT YET STARTED
2 |  | 4541-Gables Cypress Creek | EMDS |  | BUILDING TYPE-V FOUNDATIONS (sub#26.1) | 2026-04-09 | IN PROGRESS | 2026-04-14 | [5 empty] | Swathi
4 |  | 4543 DULCE VIDA | EMDS & BARLISTS |  | Main bldg roof slab | 2026-04-10 | NOT YET STARTED
5 |  | NOMI-6 | EMDS & BARLISTS |  | Lvl-4 slab markups & barlists | 2026-04-11 | NOT YET STARTED | [6 empty] | Sai
6 |  | 4541-Gables Cypress Creek | EMDS & BARLISTS |  | Bldg. Type IV - Tunnel Walls submittal | 2026-04-11 | IN PROGRESS | 2026-04-13 | [5 empty] | Swathi
7 |  | NOMI-6 | BARLISTS |  | Satirs | 2026-04-11 | COMPLETED | 2026-04-11 | [5 empty] | Sai
8 |  | 4541-Gables Cypress Creek | EMDS & BARLISTS |  | Building Type - I SOG | 2026-04-13 | NOT YET STARTED
9 |  | 4541-Gables Cypress Creek | EMDS & BARLISTS |  | Building Type - I Tunnel walls | 2026-04-13 | IN PROGRESS | [6 empty] | Swathi
10 |  | 4541-Gables Cypress Creek | EMDS & BARLISTS |  | Building Type -III Tunnel walls | 2026-04-13 | NOT YET STARTED
11 |  | Modera Boca Raton | EMDS |  | Columns lvl 4 to 8 | 2026-04-21 | IN PROGRESS | [6 empty] | Jagadeesh
11 |  | NOMI-6 | EMDS |  | Slab edge reinf't addition | 2026-04-21 | NOT YET STARTED
12 |  | Modera Boca Raton | EMDS |  | Columns 8th to roof | 2026-04-22 | NOT YET STARTED
13 |  | 4541-Gables Cypress Creek | EMDS & BARLISTS |  | Bldg. Type III 2nd floor slab | 2026-04-22 | NOT YET STARTED
14 |  | 4543 DULCE VIDA | EMDS & BARLISTS |  | Satirs 1&4 Grnd to L2 addition & barlists | 2026-04-22 | COMPLETED | 2026-04-22 | [5 empty] | Sai
15 |  | 4541-Gables Cypress Creek | BARLISTS |  | 8"-Wall for Bldg.; Type IV - L1-L2 | 2026-04-22 | NOT YET STARTED
16 |  | 2460 Australian (Ocean Tower) | EMAIL REQUEST |  | Change Elevator level -5-0" to -4'-0" & RFI 043, 20 | 2026-04-24 | IN PROGRESS
17 |  | NOMI-6 | EMAIL REQUEST |  | All floor balcony bars changed galvanized to black bars | 2026-04-24 | COMPLETED | 2026-04-25 | [5 empty] | Sai
18 |  | NOMI-6 | EMDS & BARLISTS |  | STAIR LEVEL 3 TO 4 | 2026-04-25 | COMPLETED | 2026-04-25 | [5 empty] | Sai
19 |  | NOMI-6 | PATCH LIST |  | Patch list for lift-3 column #60 | 2026-04-25 | COMPLETED | 2026-04-25 | [5 empty] | Sai
20 |  | 4543 DULCE VIDA | EMDS & BARLISTS |  | Satirs #1 addition work | 2026-04-25 | COMPLETED | 2026-04-25
21 |  | 2460 Australian (Ocean Tower) | CO |  | Pilecaps & Gradebeams revision per RFI 24,11,12,35&39 responses | 2026-04-27 | COMPLETED | 2026-05-01 | [5 empty] | Dhanush
22 |  | Modera Boca Raton | BARLISTS |  | Ground Level Rebar Shop Drawings | 2026-04-28 | COMPLETED | 2026-04-28 | [5 empty] | Nanaji
23 |  | Modera Boca Raton | EMDS |  | Level-7 slab EMDS | 2026-04-28 | COMPLETED | 2026-05-01 | [5 empty] | Nanaji
24 |  | Modera Boca Raton | EMDS |  | Columns 35, 36, and 37 terminate below the pool slab | 2026-04-28 | NOT YET STARTED
25 |  | 4541-Gables Cypress Creek | EMDS |  | Tunnel walls revision per RFI#35 | 2026-04-28 | NOT YET STARTED
26 |  | 4541-Gables Cypress Creek | EMDS & BARLISTS |  | Bldg. Type II - SOG | 2026-04-28 | COMPLETED | 2026-04-28 | [5 empty] | Swathi
27 |  | NOMI-6 | EMDS & BARLISTS |  | Columns Lvl-4 to 5 pour separation | 2026-04-28 | IN PROGRESS | 2026-04-29 | [5 empty] | Sai
28 |  | Modera Boca Raton | EMDS |  | All slabs balconies galv bars. | 2026-04-28 | NOT YET STARTED | [6 empty] | Nanaji
29 |  | 4541-Gables Cypress Creek | EMDS & BARLISTS |  | All bldgs tunnel walls candycane bars | 2026-04-28 | NOT YET STARTED | [6 empty] | Swathi
30 |  | 4541-Gables Cypress Creek | EMDS & BARLISTS |  | Bldg. Type I & II RFI #98 fnds revision | 2026-04-28 | NOT YET STARTED | [6 empty] | Swathi
31 |  | NOMI-6 | EMDS & BARLISTS |  | columns, shear walls, slabs & stairs | 2026-04-30 | COMPLETED | 2026-04-30 | [5 empty] | Sai
32 |  | 4541-Gables Cypress Creek | EMDS & BARLISTS |  | Bldg. Type IV - Level-2 | 2026-05-01 | IN PROGRESS | 2026-05-05 | [5 empty] | Swathi
33 |  | Modera Boca Raton | EMDS & BARLISTS |  | Ground Level Slab FFU drawings and bar lists. RFI #79 | 2026-05-01 | NOT YET STARTED
34 |  | 2460 Australian (Ocean Tower) | EMDS & BARLISTS |  | Submittal 13- Ground Floor Slab | 2026-05-01 | COMPLETED | 2026-05-04 | [5 empty] | Balaram
35 |  | 2460 Australian (Ocean Tower) | EMDS |  | Submittal 10- Steel Column Shop Drawings | 2026-05-01 | COMPLETED | 2026-05-05 | [5 empty] | Sai
36 |  | Adela II | EMDS |  | slabs markups | 2026-04-27 | NOT YET STARTED
37 |  | 4541-Gables Cypress Creek | EMDS |  | remaining bldgs walls updated dwgs | 2026-05-04 | NOT YET STARTED
38 |  | NOMI-6 | EMDS & BARLISTS |  | lvl-5 barlists & lvl-4 release separation | 2026-05-04 | COMPLETED | [6 empty] | Sai
39 |  | 4543 DULCE VIDA | EMDS & BARLISTS |  | Lvl-2 drop beams for savers. | 2026-05-04 | COMPLETED | [6 empty] | Sai
40 |  | Modera Boca Raton | CO |  | Revision per RFI #50, #67, #78 responses | 2026-05-06 | NOT YET STARTED
41 |  | 2460 Australian (Ocean Tower) | EMDS & BARLISTS |  | Pour separation | 2026-05-06 | NOT YET STARTED
42 |  | Modera Boca Raton | EMDS & BARLISTS |  | Columns level 2 to Level 4 | 2026-05-07 | COMPLETED | 2026-05-11 | [5 empty] | Nanaji
43 |  | 4541-Gables Cypress Creek | CO |  | RFI responses 86 & 95.1 | 2026-05-07 | IN PROGRESS | 2026-05-11 | [5 empty] | Dhanush
44 |  | Alexan margrate | EMDS |  | steel columns EMDS | 2026-05-07 | COMPLETED | 2026-05-07 | [5 empty] | Sai
45 |  | Modera Boca Raton | EMDS |  | Pet Wash details addition | 2026-05-07 | COMPLETED | 2026-05-11 | [5 empty] | Nanaji
46 |  | 2460 Australian (Ocean Tower) | CO |  | RFI responses 25 & 27 | 2026-05-08 | NOT YET STARTED
47 |  | 4541-Gables Cypress Creek | EMDS & BARLISTS |  | Building Type V - SOG | 2026-05-09 | NOT YET STARTED | 2026-05-09 | [5 empty] | Swathi
48 |  | 4541-Gables Cypress Creek | EMDS & BARLISTS |  | Building Type V - SOG | 2026-05-12 | NOT YET STARTED
49 |  | 4543 DULCE VIDA | EMDS & BARLISTS |  | male to female savers. | 2026-05-12 | COMPLETED | 2026-05-12 | [5 empty] | Sai
50 |  | NOMI-6 | EMDS & BARLISTS |  | Missing rebar for slab transitions on pool deck slab | 2026-05-12 | COMPLETED | 2026-05-12 | [5 empty] | Sai
51 |  | NOMI-6 | EMDS & BARLISTS |  | grade 80 grade 60 bars | 2026-05-16 | IN PROGRESS | [6 empty] | Sai
52
[9 empty] | Totals | 1700 | 2236.898 | 0 | 0
Note: Submittal dates may change according to client request / RFI Clarification /Priorities

## PLANNING
Tentative Submittal dates
4541-Gables Cypress Creek |  | Requsted Date |  | Modera Boca Ration | Requsted Date |  | 2460 Australian Ave | Requsted Date | Requsted Date |  | NOMI-6 | Requsted Date |  | Octavia | Requsted Date | detailing time if profiles are completed |  | Magnolia Point
BUILDING TYPE-I | LIFT-1 VERTICALS |  | 2 days | 7TH FLR SLAB | Complete |  | SLAB ON GRADE | 2026-04-20 | 2026-04-21 |  | 6th FLOOR SLAB & BEAMS | 2026-04-22 | next week | Sector-A Foundations - Deep ftgs |  | 4 days | 4 | BLDG 1 - Foundations & SOG | 6 days | 6
BUILDING TYPE-I | 2ND FLR. SLAB & BEAMS |  | 4 days | 8TH FLR SLAB | Complete | 4 days | TURNNEL WALLS Till Roof | Complete | 2026-05-01 | 6 days | 7th FLOOR SLAB & BEAMS | 2026-04-22 | next week | Sector-B Foundations - Deep ftgs |  | 4 days | 4 | BLDG 1 - 2nd floor slab | 5 days | 5
BUILDING TYPE-I | LIFT-2 VERTICALS |  | 1 days | 9TH FLR SLAB | Complete | 3 days | LIFT -1 VERTICALS CMU & COLUMS | 2026-04-24 | 2026-04-27 | 4 days | 8th FLOOR SLAB & BEAMS | 2026-04-29 | mid later next week | Sector-A Foundations - Pad ftgs |  | 4 days | 4 | BLDG 1 - 3rd floor slab | 2 days | 2
BUILDING TYPE-I | 3rd FLR. SLAB & BEAMS |  | 1 days | 10TH FLR SLAB | Complete | 1 day | 2ND FLR. SLAB & BEAMS | 2026-04-27 | 2026-05-08 | 6 days | 9th FLOOR SLAB & BEAMS | 2026-04-30 | 1 day | Sector-B Foundations - Pad ftgs |  | 4 days | 4 | BLDG 1 - 4th floor slab | 2 days | 2
BUILDING TYPE-I | LIFT-3 VERTICALS |  | 1 days | 11TH FLR SLAB | Complete | 3 days | LIFT -2 VERTICALS CMU & COLUMS | 2026-04-30 | 2026-05-15 | 2 days | 10th FLOOR SLAB & BEAMS | 2026-05-01 | 1 day | Sector-A Foundations - Cont. ftgs |  | 4 days | 4 | BLDG 1 - 5th floor slab | 2 days | 2
BUILDING TYPE-I | 4th FLR. SLAB & BEAMS |  | 1 days | 12TH FLR SLAB | Complete | 6 days | 3RD FLR. SLAB & BEAMS | 2026-05-04 |  | 3 days | 11th FLOOR SLAB & BEAMS | 2026-05-06 | 3 days | Sector-B Foundations - Cont. ftgs |  | 4 days | 4 | BLDG 1 - 6th floor slab | 2 days | 2
BUILDING TYPE-I | LIFT-4 VERTICALS |  | 1 days | 12TH MEZZ FLR SLAB | Complete | 3 days | LIFT -3 VERTICALS CMU & COLUMS | 2026-05-05 |  | 2 days | ROOF FLOOR SLAB & BEAMS | 2026-05-09 | 4 days | Sector-A Slab on grade |  | 3 days | 3 | BLDG 1 - Roof level slab | 5 days | 5
BUILDING TYPE-I | 5th FLR. SLAB & BEAMS |  | 1 days | ROOF SLAB | 2026-05-19 | 6 days | 4TH FLR. SLAB & BEAMS | 2026-05-08 | 2026-05-25 | 1 days | LIFT-4 & 5 COLUMNS | 2026-04-24 | 4 days | Sector-B Slab on grade |  | 3 days | 3 | BLDG 1 - Lift-1 verticals | 4 days | 4
BUILDING TYPE-I | LIFT-5 VERTICALS |  | 1 days | HIGH ROOF SLAB | 2026-05-19 | 2 days | LIFT -4 VERTICALS CMU & COLUMS | 2026-05-11 |  | 1 days | LIFT-4 & 5 SHEAR WALLS |  | 2 days | Sector-A Shear walls |  | 5 days | 5 | BLDG 1 - Lift-2 verticals | 1 day | 1
BUILDING TYPE-I | ROOF SLAB & BEAMS WITH PARAPET |  | 4 days | GROUND LEVEL TO 2ND LEVEL TC & CMU WALLS | 2026-05-26 | 5 days | 5TH FLR. SLAB & BEAMS | 2026-05-15 |  | 1 days | LIFT-6 & 7 COLUMNS |  | 4 days | Sector-B Shear walls |  | 5 days | 5 | BLDG 1 - Lift-3 verticals | 1 day | 1
BUILDING TYPE-II | TUNNEL WALLS |  | 4 days | 2ND LEVEL TO 3RD LEVEL TC & CMU WALLS | 2026-06-19 |  | LIFT -5 VERTICALS CMU & COLUMS | 2026-05-21 |  | 1 days | LIFT-6 & 7 SHEAR WALLS |  | 2 days | Sector-A Columns |  | 5 days | 5 | BLDG 1 - Lift-4 verticals | 1 day | 1
BUILDING TYPE-II | LIFT-1 VERTICALS |  | 2 days | 3RD LEVEL TO 4TH LEVEL TC & CMU WALLS |  |  | 6TH FLR. SLAB & BEAMS | 2026-05-25 |  | 1 days | LIFT-8 & 9 COLUMNS |  | 4 days | Sector-B Columns |  | 5 days | 5 | BLDG 1 - Lift-5 verticals | 1 day | 1
BUILDING TYPE-II | 2ND FLR. SLAB & BEAMS |  | 4 days | 4TH LEVEL TO 5TH LEVEL TC & CMU WALLS |  |  | LIFT -6 VERTICALS CMU & COLUMS | 2026-06-01 | 2026-06-17 | 1 days | LIFT-8 & 9 SHEAR WALLS |  | 2 days | Sector-A Stairs |  | 5 days | 5 | BLDG 1 - Lift-6 verticals | 1 day | 1
BUILDING TYPE-II | LIFT-2 VERTICALS |  | 1 days | 5TH LEVEL TO 6TH LEVEL TC & CMU WALLS |  |  | 7TH FLR. SLAB & BEAMS | 2026-06-03 |  | 1 days | LIFT-10 & 11 COLUMNS |  | 4 days | Sector-B Stairs |  | 5 days | 5 | BLDG 1 - Parapet walls | 3 days | 3
BUILDING TYPE-II | 3rd FLR. SLAB & BEAMS |  | 1 days | 6TH LEVEL TO 7TH LEVEL TC & CMU WALLS |  |  | LIFT -7 VERTICALS CMU & COLUMS | 2026-06-08 |  | 1 days | LIFT-10 & 11 SHEAR WALLS |  | 2 days | Sector-A Level-1.5 slab & beams |  | 5 days | 5 | BLDG 2 - Foundations & SOG | 5 days | 5
BUILDING TYPE-II | LIFT-3 VERTICALS |  | 1 days | 7TH LEVEL TO 8TH LEVEL TC & CMU WALLS |  |  | 8TH FLR. SLAB & BEAMS | 2026-06-10 |  | 1 days | STAIRS (LEVEL-4 TO LEVEL-6) |  | 2 days | Sector-A 2nd floor slab & beams |  | 14 days | 14 | BLDG 2 - 2nd floor slab | 5 days | 5
BUILDING TYPE-II | 4th FLR. SLAB & BEAMS |  | 1 days | 8TH LEVEL TO 9TH LEVEL TC & CMU WALLS |  |  | LIFT -8 VERTICALS CMU & COLUMS | 2026-06-15 |  | 2 days | STAIRS (LEVEL-6 TO LEVEL-8) |  | 1 day | Sector-B 2nd floor slab & beams |  | 10 days | 10 | BLDG 2 - 3rd floor slab | 2 days | 2
BUILDING TYPE-II | LIFT-4 VERTICALS |  | 1 days | 9TH LEVEL TO 10TH LEVEL TC & CMU WALLS |  |  | ROOF SLAB & BEAMS WITH PARAPET | 2026-06-17 |  | 4 days | STAIRS (LEVEL-8 TO LEVEL-10) |  | 2 days | Sector-A 3rd floor slab & beams |  | 4 days | 4 | BLDG 2 - 4th floor slab | 2 days | 2
BUILDING TYPE-II | 5th FLR. SLAB & BEAMS |  | 1 days | 10TH LEVEL TO 11TH LEVEL TC & CMU WALLS | [6 empty] | STAIRS (LEVEL-10 TO LEVEL-ROOF) |  | 2 days | Sector-B 3rd floor slab & beams |  | 3 days | 3 | BLDG 2 - 5th floor slab | 2 days | 2
BUILDING TYPE-II | LIFT-5 VERTICALS |  | 1 days | 11TH LEVEL TO 12TH LEVEL TC & CMU WALLS | [6 empty] | STAIRS (LEVEL-10 TO LEVEL-ROOF) |  | 2 days | Sector-A 4th floor slab & beams |  | 3 days | 3 | BLDG 2 - 6th floor slab | 2 days | 2
BUILDING TYPE-II | ROOF SLAB & BEAMS WITH PARAPET |  | 4days | 12TH LEVEL TO 12TH MEZZ LEVEL TC & CMU WALLS |  |  | Dhanush |  |  |  | LIFT-2 CMU VERTICALS |  | 2 days | Sector-B 4th floor slab & beams |  | 3 days | 3 | BLDG 2 - Roof level slab | 4 days | 4
BUILDING TYPE-III | LIFT-2 VERTICALS |  | 1 days | 12TH MEZZ LEVEL TO ROOF LEVEL TC & CMU WALLS | [6 empty] | LIFT-3 CMU VERTICALS |  | 2 days | Sector-A 5th floor slab & beams |  | 3 days | 3 | BLDG 2 - Lift-1 verticals | 4 days | 4
BUILDING TYPE-III | 3rd FLR. SLAB & BEAMS | 2026-05-18 | 1 days | ROOF LEVEL TO HIGH ROOF TC & CMU WALLS | [6 empty] | LIFT-4 CMU VERTICALS |  | 2 days | Sector-B 5th floor slab & beams |  | 3 days | 3 | BLDG 2 - Lift-2 verticals | 1 day | 1
BUILDING TYPE-III | LIFT-3 VERTICALS |  | 1 days | [7 empty] | LIFT-5 CMU VERTICALS |  | 2 days | Sector-A 6th floor slab & beams |  | 3 days | 3 | BLDG 2 - Lift-3 verticals | 1 day | 1
BUILDING TYPE-III | 4th FLR. SLAB & BEAMS |  | 1 days | [7 empty] | LIFT-6 CMU VERTICALS |  | 1 days | Sector-B 6th floor slab & beams |  | 3 days | 3 | BLDG 2 - Lift-4 verticals | 1 day | 1
BUILDING TYPE-III | LIFT-4 VERTICALS |  | 1 days | [7 empty] | LIFT-7 CMU VERTICALS |  | 1 days | Sector-A 7th floor slab & beams |  | 3 days | 3 | BLDG 2 - Lift-5 verticals | 1 day | 1
BUILDING TYPE-III | 5th FLR. SLAB & BEAMS |  | 1 days | [7 empty] | LIFT-8 CMU VERTICALS |  | 1 days | Sector-B 7th floor slab & beams |  | 3 days | 3 | BLDG 2 - Lift-6 verticals | 1 day | 1
BUILDING TYPE-III | LIFT-5 VERTICALS |  | 1 days | [7 empty] | LIFT-9 CMU VERTICALS |  | 1 days | Sector-A 8th floor slab & beams |  | 3 days | 3 | BLDG 2 - Parapet walls | 3 days | 3
BUILDING TYPE-III | ROOF SLAB & BEAMS WITH PARAPET |  | 4 days | [7 empty] | LIFT-10 CMU VERTICALS |  | 1 days | Sector-B 8th floor slab & beams |  | 3 days | 3 | BLDG 3 - Foundations & SOG | 5 days | 5
BUILDING TYPE-IV | LIFT-2 VERTICALS |  | 2 days | [7 empty] | LIFT-11 CMU VERTICALS |  | 2 days | Sector-A Roof floor slab & beams |  | 5 days | 5 | BLDG 3 - 2nd floor slab | 5 days | 5
BUILDING TYPE-IV | 3rd FLR. SLAB & BEAMS |  | 4 days | [10 empty] | Sector-B Roof floor slab & beams |  | 5 days | 5 | BLDG 3 - 3rd floor slab | 2 days | 2
BUILDING TYPE-IV | LIFT-3 VERTICALS |  | 1 days | [10 empty] | Upper roof slab & beams |  | 5 days | 5 | BLDG 3 - 4th floor slab | 2 days | 2
BUILDING TYPE-IV | 4th FLR. SLAB & BEAMS |  | 1 days | [13 empty] | 141 | BLDG 3 - 5th floor slab | 2 days | 2
BUILDING TYPE-IV | LIFT-4 VERTICALS |  | 1 days | [7 empty] | sai | [5 empty] | 6.1304 | BLDG 3 - 6th floor slab | 2 days | 2
BUILDING TYPE-IV | 5th FLR. SLAB & BEAMS |  | 1 days | [14 empty] | BLDG 3 - Roof level slab | 4 days | 4
BUILDING TYPE-IV | LIFT-5 VERTICALS |  | 1 days | [14 empty] | BLDG 3 - Lift-1 verticals | 4 days | 4
BUILDING TYPE-IV | ROOF SLAB & BEAMS WITH PARAPET |  | 4 days | [14 empty] | BLDG 3 - Lift-2 verticals | 1 day | 1
BUILDING TYPE-V | TUNNEL WALLS | 2026-04-18 | DONE | [14 empty] | BLDG 3 - Lift-3 verticals | 1 day | 1
BUILDING TYPE-V | LIFT-1 VERTICALS |  | 2 days | [14 empty] | BLDG 3 - Lift-4 verticals | 1 day | 1
BUILDING TYPE-V | 2ND FLR. SLAB & BEAMS | 2026-04-24 | 4 days | [14 empty] | BLDG 3 - Lift-5 verticals | 1 day | 1
BUILDING TYPE-V | LIFT-2 VERTICALS |  | 1 days | [14 empty] | BLDG 3 - Lift-6 verticals | 1 day | 1
BUILDING TYPE-V | 3rd FLR. SLAB & BEAMS |  | 1 days | [14 empty] | BLDG 3 - Parapet walls | 3 days | 3
BUILDING TYPE-V | LIFT-3 VERTICALS |  | 1 days | [14 empty] | BLDG 4 - Foundations & SOG | 5 days | 5
BUILDING TYPE-V | 4th FLR. SLAB & BEAMS |  | 1 days |  |  |  | Team | [10 empty] | BLDG 4 - 2nd floor slab | 5 days | 5
BUILDING TYPE-V | LIFT-4 VERTICALS |  | 1 days |  |  |  | Sai, | Boca Helping level.7 | [9 empty] | BLDG 4 - 3rd floor slab | 2 days | 2
BUILDING TYPE-V | 5th FLR. SLAB & BEAMS |  | 1 days |  |  |  | Swathi | GCC Bldg. V Tunnel (tomorrow) | [9 empty] | BLDG 4 - 4th floor slab | 2 days | 2
BUILDING TYPE-V | LIFT-5 VERTICALS |  | 1 days |  |  |  | Balaram | Austrailan SOG. 23rd | [9 empty] | BLDG 4 - 5th floor slab | 2 days | 2
BUILDING TYPE-V | ROOF SLAB & BEAMS WITH PARAPET |  | 4 days |  |  |  | Dhanush | Not yet planned. On tuesday | [9 empty] | BLDG 4 - Roof level slab | 4 days | 4
[7 empty] | Trisha | GCC. Bldg. IV. 3rd floor | [9 empty] | BLDG 4 - Lift-1 verticals | 4 days | 4
[6 empty] | balaram | [11 empty] | BLDG 4 - Lift-2 verticals | 1 day | 1
[18 empty] | BLDG 4 - Lift-3 verticals | 1 day | 1
[7 empty] | Balaram & dhanush Freez. 05/08 | [10 empty] | BLDG 4 - Lift-4 verticals | 1 day | 1
| trisha | [5 empty] | swathi 24 | [10 empty] | BLDG 4 - Lift-5 verticals | 1 day | 1
[18 empty] | BLDG 4 - Parapet verticals | 3 days | 3
[18 empty] | BLDG 5 - Foundations & SOG | 5 days | 5
[7 empty] | So far helping Nanaji and jagadheesh. | [10 empty] | BLDG 5 - 2nd floor slab | 5 days | 5
[18 empty] | BLDG 5 - 3rd floor slab | 2 days | 2
[18 empty] | BLDG 5 - Roof level slab | 4 days | 4
[18 empty] | BLDG 5 - Lift-1 verticals | 4 days | 4
[18 empty] | BLDG 5 - Lift-2 verticals | 1 day | 1
[18 empty] | BLDG 5 - Lift-3 verticals | 1 day | 1
[18 empty] | BLDG 5 - Parapet verticals | 4 days | 4
[18 empty] | Clubhouse - Foundations & SOG | 3 days | 3
[18 empty] | Clubhouse - Lift-1 verticals | 3 days | 3
[18 empty] | Clubhouse - Roof slab | 3 days | 3
[18 empty] | Clubhouse - Parapet & Trellis slab | 3 days | 3
[18 empty] | Trash enclosure | 1 day | 1
174
6.1304

## FOR QC
S.NO | PROJECT NAME | COMPONENT OF WORK | DWG# | DETAILER | SUBMITTED FOR QC DATE (MM/DD/YYYY) | SUBMITTED FOR QC TIME (HH:MM AM/PM) | CLIENT SUBMISSION DATE (MM/DD/YYYY) | QC STATUS | FILE PATH/LOCATION
1 | 4541-Gables Cypress Creek (BLDG-TYPE-4) | 2ND FLR. SLAB & BEAMS | R5 TO R5H | SWA | 2026-04-09 | 17:19 | ALREADY SUB ON 04/10 | NOT YET STARTED | M:\PROJECTS\Rebar\Projects 2026\RDS\Formcrete\4541-Gables Cypress Creek\For Qc\Building - IV\2026-04-09
2 | NOMI 6 | 4TH FLR. SLAB & BEAMS | R12 TO R12H | SWA/SAI | 2026-04-11 | 12:00 | ALREADY SUB ON 04/10 | NOT YET STARTED | M:\PROJECTS\Rebar\Projects 2026\RDS\Formcrete\NOMI-6\FOR QC\2026-04-04\4TH FLR. SLAB & BEAMS
3 | Modera Boca Raton | 4TH LEVEL TO 8TH LEVEL COLUMNS | R18 TO R18Z | JGD | 2026-04-11 | 18:00 | ALREADY SUB ON 04/13 | NOT YET STARTED | M:\PROJECTS\Rebar\Projects 2026\RDS\Formcrete\Modera Boca Raton\FOR Q.C\2026-04-11\COUMNS (LVL.-4 TO LVL-8)
4 | 4541-Gables Cypress Creek | SLAB ON GRADE | R2 | BLM | 2026-04-13 | 17:35 | ALREADY SUB ON 04/13 | NOT YET STARTED | M:\PROJECTS\Rebar\Projects 2026\RDS\Formcrete\4541-Gables Cypress Creek\For Qc\BUILDING-V\2026-04-13\Slab On Grade
5 | NOMI-6 | SHEAR WALL LIFT-4 | R14 & R14A | BLM | 2026-04-15 | 17:25 | ALREADY SUB ON 04/15 | NOT YET STARTED | M:\PROJECTS\Rebar\Projects 2026\RDS\Formcrete\NOMI-6\FOR QC\2026-04-15\Shear Walls Lift-4
6 | Modera Boca Raton | 8TH LEVEL TO ROOF COLUMNS | R19 TO R19R | JGD | 2026-04-17 | 15:30 | ALREADY SUB ON 04/17 | NOT YET STARTED | M:\PROJECTS\Rebar\Projects 2026\RDS\Formcrete\Modera Boca Raton\FOR Q.C\2026-04-17\COLUMNS 8TH TO ROOF
7 | Brakers Ocean Tower | SLAB ON GRADE | R3 TO R3E | BLM | 2026-04-20 | 17:35 | ALREADY SUB ON 04/20 | NOT YET STARTED | M:\PROJECTS\Rebar\Projects 2026\RDS\Formcrete\Brakers Ocean Tower\FOR QC\2026-04-20\Slab On Grade
8 | Brakers Ocean Tower | LIFT-1 VERTICALS | R4 TO R4C | DNS | 2026-04-24 | 12:35 | ALREADY SUB ON 04/24 | NOT YET STARTED | M:\PROJECTS\Rebar\Projects 2026\RDS\Formcrete\Brakers Ocean Tower\FOR QC\2026-04-24\LIFT-1 VERTICALS
9 | Brakers Ocean Tower | PILE CAPS | R1 TO R1D | DNS | 2026-04-20 | 17:35 | 2026-04-27 | NOT YET STARTED | M:\PROJECTS\Rebar\Projects 2026\RDS\Formcrete\2460 Australian Ave (Brakers Ocean Tower)\FOR QC\2026-04-27
10 | 2460 Australian Ave (Brakers Ocean Tower) | TUNNEL WALLS (SOG TO ROOF) | R5 TO R5T | BLM | 2026-03-30 | 19:00 | 2026-05-01 | NOT YET STARTED | M:\PROJECTS\Rebar\Projects 2026\RDS\Formcrete\2460 Australian Ave (Brakers Ocean Tower)\FOR QC\2026-04-30\Tunnel Walls (Sog To Roof)
11 | NOMI-6 | SHEAR WALL LIFT-6 & 7 | R23 & R23A | SAI | 2026-05-09 | 12:25 | 2026-05-09 | NOT YET STARTED | M:\PROJECTS\Rebar\Projects 2026\RDS\Formcrete\NOMI-6\FOR QC\2026-05-08\LIFT-6 & 7 SHEAR WALL VERT