## White Cap Work Schedule
PROJECT STATUS
| Customer | White Cap
| Last updated date | 2026-05-04
S.No | BILL STATUS | PROJECT NAME | SCOPE | Tasks | REC. DATE | STATUS | CLIENT SUB. DATE | CUST. REQ. DATE | EXP. WT/HRS | DET. WT. | EST. WT. | EST. HRS | HRS | C.O. | QC SUB. DATE2 | DETAILER STATUS | DETAILER | QC STATUS | CHECKER | REMARKS
1 |  | Felies Residence | CIP&CMU | Foundations and slab on grade | 2026-03-01 | Completed | 2026-12-01 |  |  | 2.8 | [6 empty] | Praveena |  | Chandra Mouli
|  |  |  | Lift - 1 Verticals & beams, 2nd floor slab & beams | 2026-03-01 | Completed | 01-29-2026 |  |  | 6.354 | [6 empty] | Praveena |  | Anji Reddy
|  |  |  | Lift - 2 verticals & beams, Roof slab & beams | 2026-03-01 | Completed | 2026-06-02 |  |  | 3.835 | [6 empty] | Praveena |  | Anji Reddy
2 |  | Valencia Del Mar Pickleball | CIP&CMU | Foundations and slab on grade | 2026-06-01 | Completed | 01-19-2026 |  |  | 6.057 | [6 empty] | Danush |  | Kameshwari
|  |  |  | Lift - 1 Verticals & beams | 2026-06-01 | Completed | 01-23-2026 |  |  | 8.112 | [6 empty] | Danush |  | Kameshwari
|  |  |  | Lift - 2 Verticals & beams | 2026-06-01 | Completed | 01-23-2026 |  |  | 4.434 | [6 empty] | Danush |  | Kameshwari
|  |  |  | Double Dumpster Enclosure | 2026-10-02 | Completed | 02-18-2026 |  |  | 0.251 | [6 empty] | Praveena |  | Kameshwari
|  |  |  | Single Dumpster Enclosure | 2026-10-02 | Completed | 02-18-2026 |  |  | 0.197 | [6 empty] | Praveena |  | Kameshwari
|  |  |  | Mail Pavilion | 2026-10-02 | Completed | 02-18-2026 |  |  | 1.661 | [6 empty] | Praveena |  | Kameshwari
|  |  |  | Monument sign | 05-30-2026 | Completed | 2026-01-06 |  |  | 0.131 |  |  |  |  | 05-30-2026 | Completed | Pradeep | Completed | Nanaji
3 |  | City of temple terrace-fire station #01 | CIP&CMU | Foundations | 2026-06-01 | Completed | 01-19-2026 |  |  | 13.923 | [6 empty] | Swathi |  | Chandra Mouli
|  |  |  | Slab on grade | 2026-06-01 | Completed | 02-14-2026 |  |  | 0.516 | [6 empty] | Sri Lalitha |  | Kameshwari
|  |  |  | Lift - 1 Verticals, 2nd floor slab & beams | 2026-06-01 | Completed | 02-25-2026 |  |  | 9.701 | [6 empty] | Sri Lalitha |  | Kameshwari
|  |  |  | Lift - 2 Verticals and Roof beams | 2026-06-01 | Completed | 02-25-2026 |  |  | 9.489 | [6 empty] | Sri Lalitha |  | Kameshwari
4 |  | 228 Rutland | CIP&CMU | Foundations and slab on grade | 2026-06-01 | Completed | 01-13-2026 |  |  | 2.598 | [6 empty] | Allu Sai |  | Kameshwari
|  |  |  | Lift - 1 Verticals and Bond beams | 2026-06-01 | Completed | 2026-03-02 |  |  | 2.152 | [6 empty] | Allu Sai |  | Kameshwari
|  |  |  | Low Roof beams & Slab | 2026-06-01 | Completed | 02-19-2026 |  |  | 2.587 | [6 empty] | Vaishnavi |  | Kameshwari
|  |  |  | Lift - 2 Verticals, Bond beams & Roof beams | 2026-06-01 | Completed | 2026-02-03 |  |  | 1.643 | [6 empty] | Siva Kumar |  | Kameshwari
5 |  | Palmetto Lakes Industrial Park | CIP&CMU | Foundations and slab on grade | 2026-08-01 | Completed | 01-14-26 |  |  | 5.041 | [6 empty] | Sri Lalitha |  | Chandra Mouli
|  |  |  | Lift - 1 walls, Columns & Beams | 2026-08-01 | Completed | 01-27-26 |  |  | 6.914 | [6 empty] | Sri Lalitha |  | Chandra Mouli
|  |  |  | Lift - 2 walls, Columns & Beams | 2026-08-01 | Completed | 01-27-26 |  |  | 6.722 | [6 empty] | Sri Lalitha |  | Chandra Mouli
6 |  | Frenchman's Creek Operations Center | CIP&CMU | Building - A Foundations & slab on grade | 01-13-2026 | Completed | 01-26-2026 |  |  | 16.64 | [6 empty] | Pradeep |  | Anji Reddy
|  |  |  | Building - B Foundations & slab on grade | 01-13-2026 | Completed | 01-21-2026 |  |  | 5.301 | [6 empty] | Pradeep |  | Narayana
|  |  |  | Building - C Foundations & slab on grade | 01-13-2026 | Completed | 01-21-2026 |  |  | 17.953 | [6 empty] | Praveena |  | Anji Reddy
|  |  |  | Building - D Foundations & slab on grade | 01-13-2026 | Completed | 01-26-2026 |  |  | 0.675 | [6 empty] | Pradeep |  | Anji Reddy
|  |  |  | Building - E Foundations & slab on grade | 01-13-2026 | Completed | 01-28-2026 |  |  | 7.23 | [6 empty] | Pradeep |  | Anji Reddy
|  |  |  | Building - F Foundations & slab on grade | 01-13-2026 | Completed | 01-31-2026 |  |  | 7.875 | [6 empty] | Pradeep |  | Anji Reddy
7 |  | Miami Shores Residence (R+R bluenest) | CIP&CMU | Foundations | 01-19-2026 | Completed | 01-27-2026 |  |  | 9.474 | [6 empty] | Swathi |  | Chandra Mouli
|  |  |  | Slab on grade | 01-19-2026 | Completed | 2026-03-03 |  |  | 1.208 | [6 empty] | Praveena |  | Chandra Mouli
|  |  |  | Lift - 1 Verticals, 2nd floor slab & beams | 01-19-2026 | Completed | 2026-09-03 |  |  | 15.747 | [6 empty] | Jagadeesh |  | Chandra Mouli
|  |  |  | Lift - 2 Verticals and Roof beams | 01-19-2026 | Completed | 03-20-2026 |  |  | 2.904 | [6 empty] | Praveena |  | Kameshwari
|  |  |  | Updated drawings received (Cantilever Beams) | 2026-06-24 | Inprogress | 2026-06-25 | [9 empty] | Praveena
8 |  | Licata Residence 2726 Appaloosa trail | CIP&CMU | Foundations & slab on grade | 01-20-2026 | Completed | 01-23-2026 |  |  | 0.764 | [6 empty] | Swathi |  | Anji Reddy
|  |  |  | Lift - 1 Verticals and Roof beams | 01-20-2026 | Completed | 01-23-2026 |  |  | 1.818 | [6 empty] | Swathi |  | Anji Reddy
9 |  | 4669 S. Flagler Dr | CIP&CMU | Footings & Stem Walls | 01-24-2026 | Completed | 2026-04-02 |  |  | 5.907 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  |  |  | Stem wall & Slab on grade | 01-24-2026 | Completed | 02-20-2026 |  |  | 1.335 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  |  |  | Lift - 1 Verticals, 2nd floor slab & beams | 01-24-2026 | Completed | 2026-04-03 |  |  | 27.935 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  |  |  | Lift - 2 Verticals & Roof beams | 01-24-2026 | Completed | 2026-06-03 |  |  | 2.141 | [6 empty] | Vaishnavi |  | Chandra Mouli
10 |  | Harrison Residence | CIP&CMU | Foundations and slab on grade | 01-27-2026 | Completed | 2026-05-02 |  |  | 0.256 | [6 empty] | Sri Lalitha |  | Chandra Mouli
|  |  |  | Lift - 1 Verticals and Beams | 01-27-2026 | Completed | 2026-02-03 |  |  | 0.834 | [6 empty] | Sri Lalitha |  | Chandra Mouli
11 |  | PBIA - Revenue Control Building | CIP&CMU | Foundations and slab on grade | 2026-04-02 | Completed | 02-14-2026 |  |  | 11.285 | [6 empty] | Praveena |  | Anji Reddy
|  |  |  | Lift - 1 Verticals and Roof beams | 2026-04-02 | Completed | 02-19-2026 |  |  | 6.364 | [6 empty] | Praveena |  | Anji Reddy
12 |  | 127 EL Bravo Way | CIP&CMU | Basement Foundations | 2026-04-02 | Completed | 02-17-2026 |  |  | 13.887 | [6 empty] | Danush |  | Anji Reddy
|  |  |  | Basement Walls | 2026-04-02 | Completed | 02-21-2026 |  |  | 5.577 | [6 empty] | Danush |  | Anji Reddy
|  |  |  | Level - 1 Foundations | 2026-04-02 | Completed | 2026-12-03 |  |  | 22.202 | [6 empty] | Danush |  | Chandra Mouli
|  |  |  | Lift - 1 Verticals | 2026-04-02 | Completed | 03-16-2026 |  |  | 4.159 | [6 empty] | Danush |  | Chandra Mouli
|  |  |  | Lift - 1 Beams | 2026-04-02 | Completed | 03-28-2026 |  |  | 10.828 | [6 empty] | Danush |  | Chandra Mouli
|  |  |  | Lift - 2 Verticals | 2026-04-02 | Completed | 03-31-2026 |  |  | 1.709 | [6 empty] | Danush |  | Chandra Mouli
|  |  |  | Roof beams | 2026-04-02 | Completed | 03-31-2026 |  |  | 1.544 | [6 empty] | Danush |  | Chandra Mouli
13 |  | Blue Water Cove 6 | CIP&CMU | Foundations & slab on grade | 2026-10-02 | Completed | 02-25-2026 |  |  | 12.306 | [6 empty] | Allu Sai/Nanaji
|  |  |  | Lift-1 & 2 Verticals, 2nd floor slab, & Roof beams | 2026-10-02 | Completed | 03-18-2026 |  |  | 6.168 | [6 empty] | Allu Sai |  | Chandra Mouli
14 |  | 1050 N Lake way | CIP&CMU | Foundations and slab on grade | 2026-05-02 | Completed | 02-17-2026 |  |  | 3.991 | [6 empty] | Lokesh Reddy/Nanaji |  | Narayana
|  |  |  | Lift - 1 Verticals, 2nd floor slab & beams | 2026-05-02 | Completed | 02-23-2026 |  |  | 9.309 | [6 empty] | Lokesh Reddy |  | Kameshwari
|  |  |  | Lift - 2 Verticals & Roof beams | 2026-05-02 | Completed | 03-13-2026 |  |  | 2.787 | [6 empty] | Praveena |  | Kameshwari
15 |  | 143 Reef Road | CIP&CMU | Foundations and slab on grade | 2026-12-02 | Completed | 03-13-2026 |  |  | 16.785 | [5 empty] | Completed | Kunal |  | Chandra Mouli
|  |  |  | Lift - 1 Verticals | 2026-12-02 | Completed | 05-15-2026 |  |  | 1.331 |  |  |  |  | 2026-12-05 | Completed | Kunal | COMPLETED | NANAJI | Qc not yet done
|  |  |  | 2nd floor slab & Beams | 2026-12-02 | Completed | 05-15-2026 |  |  | 3.234 |  |  |  |  | 2026-12-05 | Completed | Kunal | COMPLETED | NANAJI | Qc not yet done
|  |  |  | Lift-2 verticals & Roof beams | 2026-12-02 | Completed | 06-20-2026 | [7 empty] | 2026-12-05 | Completed | Kunal | NOT YET STARTED |  | Qc not yet done
16 |  | Cutler Bay SHS | CIP&CMU | Foundations and slab on grade | 02-16-2026 | Completed | 2026-04-03 |  |  | 2.305 | [6 empty] | Swathi | NOT YET STARTED | Narayana
|  |  |  | Lift - 1 Verticals and beams | 02-16-2026 | Completed | 2026-04-03 |  |  | 2.027 | [6 empty] | Swathi | NOT YET STARTED | Kameshwari
|  |  |  | Lift - 2 Verticals and Low Roof slab & beams | 02-16-2026 | Completed | 2026-04-03 |  |  | 1.242 | [6 empty] | Swathi | NOT YET STARTED | Kameshwari
|  |  |  | Lift - 3 Verticals and High Roof slab & beams | 02-16-2026 | Completed | 2026-04-03 |  |  | 0.786 | [6 empty] | Swathi | NOT YET STARTED | narayana
17 |  | Ackerman Residence | CIP&CMU | Foundations & slab on grade | 02-21-2026 | Completed | 2026-03-03 | [9 empty] | Lokesh Reddy
|  |  |  | Lift - 1 Verticals, 2nd floor slab & beams | 02-21-2026 | Completed | 03-21-2026 |  |  | 4.853 | [6 empty] | Lokesh Reddy |  | Kameshwari
|  |  |  | Lift - 2 Verticals & Roof beams | 02-21-2026 | Completed | 2026-02-04 |  |  | 1.285 | [6 empty] | Lokesh Reddy |  | Kameshwari
18 |  | Blue Water Cove 3 | CIP&CMU | Foundations & slab on grade | 02-24-2026 | Completed | 2026-06-03 |  |  | 2.592 | [6 empty] | Vaishnavi |  | Kameshwari
|  |  |  | Lift - 1 Verticals and Roof beams | 02-24-2026 | Completed | 03-16-2026 |  |  | 4.562 | [6 empty] | Vaishnavi |  | Kameshwari
19 |  | BOKOR 432 SUNSHINE BLVD | CIP&CMU | Foundations and slab on grade | 02-25-2026 | Completed | 2026-07-03 |  |  | 5.062 | [6 empty] | Eswar |  | Eswar
|  |  |  | Lift - 1 Verticals, 2nd floor slab & beams | 02-25-2026 | Completed | 03-13-2026 |  |  | 3.298 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  |  |  | Lift - 2 Verticals and Roof beams | 02-25-2026 | Completed | 03-13-2026 |  |  | 1.695 | [6 empty] | Vaishnavi |  | Chandra Mouli
20 |  | Cloyd | CIP&CMU | Foundations and slab on grade | 02-27-2026 | Completed | 03-11.-2026 |  |  | 2.267 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  |  |  | Lift - 1 Verticals and beams | 02-27-2026 | Completed | 03-20.-2026 |  |  | 1.214 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  |  |  | Lift - 2 Verticals and beams | 02-27-2026 | Completed | 03-20.-2026 |  |  | 0.835 | [6 empty] | Vaishnavi |  | Chandra Mouli
21 |  | 6017 Le Lac Road (Weiner Residence) | CIP&CMU | Foundations and slab on grade (East Garage) | 2026-09-03 | Completed | 03-21-2026 |  |  | 0.679 | [6 empty] | Sri lalitha |  | Kameshwari
|  |  |  | Lift - 1 Verticals and Roof beams (East Garage) | 2026-09-03 | Completed | 03-26-2026 |  |  | 1.643 | [6 empty] | Praveena |  | Kameshwari
|  |  |  | Foundations and slab on grade (Main Building) | 2026-09-03 | Completed | 03-25-2026 |  |  | 2.64 | [6 empty] | Praveena |  | Kameshwari
|  |  |  | Lift - 1 Verticals, 2nd floor slab and beams (Main Building) | 2026-09-03 | Completed | 2026-01-05 |  |  | 5.594 | [6 empty] | Sridevi/Vaishnavi | NOT YET STARTED | Nanaji
|  |  |  | Lift - 2 Verticals and roof beams (Main Building) | 2026-09-03 | Completed | 05-28-2026 |  |  | 4.782 |  |  |  |  | 05-28-2026 | COMPLETED | Vaishnavi | COMPLETED | Eswar
|  |  |  | Foundations and slab on grade (2-story residence) | 2026-09-03 | Completed | 04-21-2026 |  |  | 4.162 | [6 empty] | Praveena |  | Chandra Mouli
|  |  |  | Lift - 1 Verticals, 2nd floor slab and beams (2-story residence) | 2026-09-03 | Completed | 05-19-2026 |  |  | 12.373 |  | … |  |  | 05-18-2026 | COMPLETED | Vaishnavi | COMPLETED | NANAJI
|  |  |  | Lift - 2 Verticals and roof beams (2-story residence) | 2026-09-03 | Completed | 2026-05-06 |  |  | 2.935 | [6 empty] | Vaishnavi |  | NANAJI
|  |  |  | Foundations and slab on grade (site work) | 2026-10-03 | Completed | 2026-04-04 |  |  | 1.37 | [6 empty] | Sri lalitha |  | Kameshwari
22 |  | Bluewater cove 11 | CIP&CMU | Foundations and slab on grade | 2026-10-03 | Completed | 03-24-2026 |  |  | 3.041 | [6 empty] | Vaishnavi | NOT YET STARTED | Kameshwari
|  |  |  | Lift - 1 Verticals and Roof beams | 2026-10-03 | Completed | 2026-01-05 |  |  | 4.261 | [6 empty] | Vaishnavi | NOT YET STARTED | Kameshwari
23 |  | Bluewater cove 9 | CIP&CMU | Foundations and slab on grade | 2026-10-03 | Completed | 03-31-2026 |  |  | 15.362 | [6 empty] | Vaishnavi |  | Kameshwari
|  |  |  | Lift - 1 Verticals and Roof Beams | 2026-10-03 | Completed | 2026-01-05 |  |  | 5.012 | [6 empty] | Nanaji/pradeep | NOT YET STARTED | Kameshwari
24 |  | 164 Seminole | CIP&CMU | Foundations | 2026-12-03 | Completed | 2026-08-04 |  |  | 2.269 | [6 empty] | Siva kumar |  | Chandra Mouli
|  |  |  | Slab on grade | 2026-12-03 | Completed | 05-18-2026 |  |  | 9.296 |  |  |  |  | 04-24-2026 | COMPLETED | Siva kumar | COMPLETED | NANAJI | Qc not yet done
25 |  | Roy & Shelley Silverman | CIP&CMU | Foundations and slab on grade | 03-14-2026 | Completed | 2026-10-04 |  |  | 3.789 | [6 empty] | Danush |  | Chandra Mouli
|  |  |  | Lift - 1 Verticals | 03-14-2026 | Completed | 2026-04-05 |  |  | 3.191 | [6 empty] | Danush |  | Chandra Mouli
|  |  |  | Lift - 1 slab & Beams | 03-14-2026 | Completed | 2026-04-05 |  |  | 5.85 | [6 empty] | Nanaji/Sridevi | NOT YET STARTED | Kameshwari
|  |  |  | Lift - 2 Verticals & Roof beams | 03-14-2026 | Completed | 2026-11-05 |  |  | 2.95 | [6 empty] | Vaishnavi/Shiva | COMPLETED | NANAJI
26 |  | 50 SE OLIVE | CIP&CMU | Foundations & columns | 03-18-2026 | Completed | 2026-08-04 |  |  | 0.674 | [6 empty] | Danush |  | Chandra Mouli
|  |  |  | Bond beams | 03-18-2026 | Completed | 2026-08-04 |  |  | 0.174 | [6 empty] | Danush |  | Chandra Mouli
27 |  | Valencia Del Mar Clubhouse | CIP&CMU | Foundations and slab on grade | 03-20-2026 | Completed | 2026-06-04 |  |  | 22.524 | [6 empty] | Vaishnavi | COMPLETED | Chandra Mouli
|  |  |  | Lift - 1 Verticals and beams (pour-1) | 03-20-2026 | Completed | 2026-12-05 |  |  | 5.781 | [6 empty] | Vaishnavi/Sridevi | COMPLETED | NANAJI
|  |  |  | Lift - 1 Verticals and beams (pour-2) | 03-20-2026 | Completed | 05-16-2026 |  |  | 10.773 |  |  |  |  | 05-15-2026 | COMPLETED | Sridevi | COMPLETED | NANAJI
|  |  |  | Lift - 1 Verticals and beams (pour-3) & (pour-4) | 03-20-2026 | Completed | 05-27-2026 |  |  | 10.014 |  |  |  |  | 05-25-2026 | COMPLETED | Sridevi | COMPLETED | NANAJI
|  |  |  | Lift - 2 Verticals and beams (pour-1) | 03-20-2026 | Completed | 05-29-2026 |  |  | 4.784 |  |  |  |  | 05-15-2026 | COMPLETED | Sridevi | NOT YET STARTED | Kameshwari | Eswar/PDF CHECK ONLY & BAR LIST SEND
|  |  |  | Lift - 2 Verticals and beams (pour-2) | 03-20-2026 | Completed | 2026-03-06 |  |  | 3.643 | [6 empty] | Sridevi |  | Kameshwari
|  |  |  | Lift - 2 Verticals and beams (pour-3) | 03-20-2026 | Completed | 2026-12-06 |  |  | 14.818 |  |  |  |  | 2026-12-05 | COMPLETED | Sridevi | COMPLETED | NANAJI
|  |  |  | Monument walls | 04-23-2026 | Completed | 04-27-2026 |  |  | 0.576 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  |  |  | Tennis & Bocce Courts Restrooms | 2026-08-05 | Completed | 2026-09-05 |  |  | 0.123 | [6 empty] | Eswar
28 |  | 910 S Ocean | CIP&CMU | Basement Foundations | 03-24-2026 | Completed | 2026-08-04 | [9 empty] | Sridevi | NOT YET STARTED | Narayana
|  |  |  | Lift - 1 Verticals & roof beams | 03-24-2026 | Completed | 2026-10-04 | [9 empty] | Sridevi | NOT YET STARTED | Narayana
|  |  |  | Retaining wall & Planter walls & stairs | 03-24-2026 | Completed | 04-21-2026 | [9 empty] | Sridevi | NOT YET STARTED | Narayana
29 |  | Burns Residence | CIP&CMU | Foundations and slab on grade | 03-27-2026 | Completed | 2026-06-04 |  |  | 7.45 | [6 empty] | Praveena |  | Chandra Mouli
|  |  |  | Lift - 1 Verticals and Beams | 03-27-2026 | Completed | 05-21-2026 |  |  | 7.962 |  |  |  |  | 05-19-2026 | Completed | Siva kumar | Completed | NANAJI
|  |  |  | Lift - 2 Verticals and beams | 03-27-2026 | Completed | 05-21-2026 |  |  | 0.175 |  |  |  |  | 05-20-2026 | Completed | Siva kumar | Completed | NANAJI
30 |  | 5940 North Bay Road (NEW SINGLE FAMILY RESIDENCE) | CIP&CMU | Foundations | 03-26-2026 | Completed | 2026-08-04 |  |  | 140.399 | [6 empty] | Balaram/Jagadeesh |  | Chandra Mouli
31 |  | 320 S atlantic Drive | CIP&CMU | Foundations | 2026-02-04 | Completed | 04-18-2026 |  |  | 6.817 | [6 empty] | Sridevi | COMPLETED | Chandra Mouli/NNJ
|  |  |  | Stem wall & Slab on grade | 2026-02-04 | Completed | 2026-01-05 |  |  | 4.869 |  |  |  |  | 05-21-2026 | Completed | Sridevi | COMPLETED | Chandra Mouli/NNJ
|  |  |  | Lift - 1 Verticals, 2nd Floor slab & beams | 2026-02-04 | Completed | 06-13-2026 | 2026-12-06 |  | 15.352 |  |  |  |  | 06-13-2026 | Completed | Vaishnavi | NOT YET STARTED | Kameshwari
|  |  |  | Lift - 2 Verticals and Roof beams | 2026-02-04 | Completed | 06-18-2026 | 06-17-2026 | [6 empty] | 06-15-2026 | Completed | Vaishnavi | NOT YET STARTED | Kameshwari
32 |  | Custom Residence (515 lido drive) | CIP&CMU | Foundations and slab on grade | 2026-02-04 | Completed | 04-24-2026 |  |  | 22.418 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  |  |  | Lift - 1 Verticals | 2026-02-04 | Completed | 2026-04-06 |  |  | 4.206 |  |  |  |  | 05-25-2026 | Completed | Siva kumar | Completed | NANAJI
|  |  |  | 2nd floor slab & beams | 2026-02-04 | Completed | 06-18-2026 |  |  | 11.165 |  |  |  |  | 06-17-2026 | Completed | Jagadeesh | Completed | NANAJI
|  |  |  | Lift - 2 Verticals & Roof beams | 2026-02-04 | Completed | 06-18-2026 |  |  | 3.221 |  |  |  |  | 06-16-2026 | Completed | Balaram | Completed | NANAJI
33 |  | Jandrews Residence | CIP&CMU | Foundations and slab on grade | 2026-02-04 | Completed | 04-23-2026 |  |  | 16.272 | [6 empty] | Praveena | Completed | Chandra Mouli
|  |  |  | Lift - 1 Verticals and beams | 2026-02-04 | Completed | 2026-05-16 |  |  | 10.859 | [6 empty] | Lokesh Reddy | Completed | Kameshwari
|  |  |  | Lift - 2 Verticals and beams | 2026-02-04 | Completed | 2026-06-03 | [9 empty] | Lokesh Reddy | Completed | Kameshwari
34 |  | 6024 Lelac Rd | CIP&CMU | Foundations and slab on grade | 2026-03-04 | Completed | 2026-10-04 |  |  | 1.04 | [6 empty] | Vaishnavi | COMPLETED | Chandra Mouli
|  |  |  | Lift - 1 Verticals, loft floor slab & beams | 2026-03-04 | Completed | 2026-10-04 |  |  | 1.18 | [6 empty] | Vaishnavi | COMPLETED | Chandra Mouli
|  |  |  | Lift - 2 Verticals and roof beams | 2026-03-04 | Completed | 2026-10-04 |  |  | 1.26 | [6 empty] | Vaishnavi | COMPLETED | Chandra Mouli
|  |  |  | Foundations & slab on grade (Summer kitchen) | 2026-03-04 | Completed | 04-22-2026 |  |  | 1.02 | [6 empty] | Sridevi | COMPLETED | NANAJI
|  |  |  | Lift - 1 Verticals, slab and beams (Summer kitchen) | 2026-03-04 | Completed | 04-23-2026 |  |  | 1.69 | [6 empty] | Sridevi | NOT YET STARTED | Kameshwari
35 |  | 5900 Powerline Garag | CIP&CMU | Grade beams | 2026-07-04 | Completed | 04-20-2026 |  |  | 16.4 | [6 empty] | Sri lalitha | NOT YET STARTED | Kameshwari
|  |  |  | Slab on grade, Lift - 1 Verticals and Roof beams | 2026-07-04 | Completed | 2026-09-05 |  |  | 26.761 | [6 empty] | Pradeep | COMPLETED | NANAJI
36 |  | South Florida Jewish Cemetery | CIP&CMU | Foundations and slab on grade | 04-16-2026 | Completed | 2026-05-05 |  |  | 1.661 | [6 empty] | Vaishnavi | NOT YET STARTED | Eswar
|  |  |  | Lift - 1 Verticals and Roof Beams | 04-16-2026 | Completed | 05-22-2026 |  |  | 2.453 |  |  |  |  | 05-19-2026 | COMPLETED | Pradeep | COMPLETED | NANAJI
37 |  | 1820 S Federal Hwy - Fifth Third Bank | CIP&CMU | Foundations and slab on grade | 04-16-2026 | Completed | 04-24-2026 |  |  | 2.762 | [6 empty] | Pradeep | NOT YET STARTED | Narayana
|  |  |  | Lift - 1 Verticals and Roof beams | 04-16-2026 | Completed | 04-24-2026 |  |  | 1.259 | [6 empty] | Pradeep | NOT YET STARTED | Narayana
38 |  | 20 Hudson Ave | CIP&CMU | Foundations & slab on grade | 04-18-2026 | Completed | 05/26/26 | [9 empty] | Eswar |  | Kameshwari
|  |  |  | Lift - 1 Verticals and Beams | 04-18-2026 | Completed | 06-18-2026 | [9 empty] | Praveena |  | Kameshwari
|  |  |  | Lift - 2 Verticals and Beams | 04-18-2026 | Completed | 06-18-2026 | [7 empty] | 06-16-2026 | COMPLETED | Swathi | NOT YET STARTED | Kameshwari
39 |  | South Rd Office Building E | CIP&CMU | Foundations and slab on grade | 04-22-2026 | Completed | 04-24-2026 |  |  | 1.577 | [6 empty] | Vaishnavi | COMPLETED | NANAJI
|  |  |  | Lift - 1 Verticals and beams | 04-22-2026 | Completed | 2026-01-05 |  |  | 4.107 | [6 empty] | Lokesh/vaishnavi | NOT YET STARTED | NANAJI
40 |  | Baig Residence | CIP | 3rd Floor tie beams | 04-28-2026 | Completed | 2026-05-06 |  |  | 0.978 | [6 empty] | Lokesh | NOT YET STARTED | Kameshwari | High Priority
|  |  |  | 2nd Floor slab | 04-28-2026 | Completed | 2026-05-07 | [9 empty] | Lokesh |  | Kameshwari | High Priority
41 |  | SW Ranches | CIP | Lower Roof Deck | 04-30-2026 | Completed | 2026-05-15 |  |  | 29.74 | [6 empty] | Eswar |  | Nanaji | High Priority
|  |  |  | Lift - 1 verticals | 04-30-2026 | Completed | 2026-06-01 |  |  | 2.45 |  |  |  |  | 05-30-2026 | COMPLETED | Pradeep | COMPLETED | NANAJI
42 |  | 2651 Southcast 10th court | CIP | Pool deck slab and beams | 2026-06-05 | Completed | 2026-09-05 | [11 empty] | Kameshwari
43 |  | Country inn Pet Resort | CIP&CMU | Foundations and slab on grade | 2026-08-05 | Completed | 05-22-2026 |  |  | 3.691 | [6 empty] | Vaishnavi | COMPLETED | NANAJI | Asap Job
|  |  |  | Lift - 1 verticals and beams | 2026-08-05 | Completed | 2026-05-06 | [9 empty] | Vaishnavi | COMPLETED | NANAJI
|  |  |  | Lift - 2 verticals and beams | 2026-08-05 | Completed | 2026-05-06 | [9 empty] | Vaishnavi | COMPLETED | NANAJI
44 |  | 2960 Greenbriair | CIP&CMU | Foundations | 05-13-2026 | Completed | 2026-05-06 |  |  | 20.784 |  |  |  |  | 06-15-2026 | COMPLETED | Lokesh Reddy | NOT YET STARTED | Kameshwari
|  |  |  | Slab on grade | 05-13-2026 | Completed | 06-19-2026 | [9 empty] | Sri Lalitha | NOT YET STARTED | Kameshwari
|  |  |  | Lift - 1 verticals and beams | 05-13-2026 | Inprogress | 06-20-2026 | [9 empty] | Sridevi | NOT YET STARTED | Kameshwari
|  |  |  | Lift - 2 verticals and beams | 05-13-2026 | Inprogress | 06-23-2026 | [9 empty] | Sri Lalitha | NOT YET STARTED | Kameshwari
45 |  | Gallery at Somi Parc Phase 1 | CIP&CMU | Foundations (Residential) part - 1 | 05-14-2026 | Completed | 06-17-2026 | [9 empty] | Eswar/Nanaji |  | Kameshwari
|  |  |  | Foundations (Residential) part - 2 | 05-14-2026 | Completed | 06-18-2026 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | Slab on grade (Residential) part - 1 & 2 | 05-14-2026 | Inprogress | 06-26-2026 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Columns (Residential) lift - 1 verticals | 05-14-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | Shear walls (Residential) lift - 1 verticals | 05-14-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Eswar |  | Kameshwari
|  |  |  | Cmu walls lift - 1 verticals | 05-14-2026 | Not Yet Started | 2026-03-08 | [9 empty] | Praveena |  | Eswar
|  |  |  | 2nd Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-03-09 | [9 empty] | Swathi |  | Eswar
|  |  |  | Columns (Residential) lift - 2 verticals | 05-14-2026 | Not Yet Started | 2026-03-10 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Shear walls (Residential) lift - 2 verticals | 05-14-2026 | Not Yet Started | 2026-03-11 | [9 empty] | Vaishnavi |  | Eswar
|  |  |  | Cmu walls lift - 2 verticals | 05-14-2026 | Not Yet Started | 2026-03-12 | [9 empty] | Lokesh/vaishnavi |  | Kameshwari
|  |  |  | 3rd Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-03-13 | [11 empty] | Kameshwari
|  |  |  | Columns (Residential) lift - 3 verticals |  | Not Yet Started | 2026-03-14 | [9 empty] | Lokesh |  | Eswar
|  |  |  | Shear walls (Residential) lift - 3 verticals |  | Not Yet Started | 2026-03-15 | [9 empty] | Lokesh |  | Kameshwari
|  |  |  | Cmu walls lift - 3 verticals |  | Not Yet Started | 2026-03-16 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | 3rd Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-03-17 | [9 empty] | Eswar |  | Eswar
|  |  |  | Columns (Residential) lift - 4 verticals |  | Not Yet Started | 2026-03-18 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Shear walls (Residential) lift - 4 verticals |  | Not Yet Started | 2026-03-19 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Cmu walls lift - 4 verticals |  | Not Yet Started | 2026-03-20 | [9 empty] | Pradeep |  | Eswar
|  |  |  | 4th Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-03-21 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | Columns (Residential) lift - 5 verticals |  | Not Yet Started | 2026-03-22 | [9 empty] | Eswar |  | Kameshwari
|  |  |  | Shear walls (Residential) lift - 5 verticals |  | Not Yet Started | 2026-03-23 | [9 empty] | Praveena |  | Eswar
|  |  |  | Cmu walls lift - 5 verticals |  | Not Yet Started | 2026-03-24 | [9 empty] | Swathi |  | Kameshwari
|  |  |  | 5th Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-03-25 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | Columns (Residential) lift - 6 verticals |  | Not Yet Started | 2026-03-26 | [9 empty] | Vaishnavi |  | Kameshwari
|  |  |  | Shear walls (Residential) lift - 6 verticals |  | Not Yet Started | 2026-03-27 | [9 empty] | Lokesh |  | Kameshwari
|  |  |  | Cmu walls lift - 6 verticals |  | Not Yet Started | 2026-03-28 | [11 empty] | Eswar
|  |  |  | 6th Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-03-29 | [9 empty] | Lokesh |  | Kameshwari
|  |  |  | Columns (Residential) lift - 7 verticals |  | Not Yet Started | 2026-03-30 | [9 empty] | Lokesh |  | Kameshwari
|  |  |  | Shear walls (Residential) lift - 7 verticals |  | Not Yet Started | 2026-03-31 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Cmu walls lift - 7 verticals |  | Not Yet Started | 2026-04-01 | [9 empty] | Eswar |  | Eswar
|  |  |  | 7th Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-04-02 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Columns (Residential) lift - 8 verticals |  | Not Yet Started | 2026-04-03 | [9 empty] | Swathi |  | Eswar
|  |  |  | Shear walls (Residential) lift - 8 verticals |  | Not Yet Started | 2026-04-04 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | Cmu walls lift - 8 verticals |  | Not Yet Started | 2026-04-05 | [9 empty] | Vaishnavi |  | Kameshwari
|  |  |  | 8th Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-04-06 | [9 empty] | Lokesh |  | Eswar
|  |  |  | Columns (Residential) lift - 9 verticals |  | Not Yet Started | 2026-04-07 | [11 empty] | Kameshwari
|  |  |  | Shear walls (Residential) lift - 9 verticals |  | Not Yet Started | 2026-04-08 | [9 empty] | Lokesh |  | Kameshwari
|  |  |  | Cmu walls lift - 9 verticals |  | Not Yet Started | 2026-04-09 | [9 empty] | Lokesh |  | Kameshwari
|  |  |  | 9th Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-04-10 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | Columns (Residential) lift - 10 verticals |  | Not Yet Started | 2026-04-11 | [9 empty] | Eswar |  | Eswar
|  |  |  | Shear walls (Residential) lift - 10 verticals |  | Not Yet Started | 2026-04-12 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | Cmu walls lift - 10 verticals |  | Not Yet Started | 2026-04-13 | [9 empty] | Swathi |  | Kameshwari
|  |  |  | 10th Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-04-14 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Columns (Residential) lift - 11 verticals |  | Not Yet Started | 2026-04-15 | [9 empty] | Vaishnavi |  | Eswar
|  |  |  | Shear walls (Residential) lift - 11 verticals |  | Not Yet Started | 2026-04-16 | [9 empty] | Lokesh |  | Eswar
|  |  |  | Cmu walls lift - 11 verticals |  | Not Yet Started | 2026-04-17 | [9 empty] | Swathi |  | Eswar
|  |  |  | 11th Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-04-18 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | Columns (Residential) lift - 12 verticals |  | Not Yet Started | 2026-04-19 | [9 empty] | Vaishnavi |  | Kameshwari
|  |  |  | Shear walls (Residential) lift - 12 verticals |  | Not Yet Started | 2026-04-20 | [9 empty] | Lokesh |  | Eswar
|  |  |  | Cmu walls lift - 12 verticals |  | Not Yet Started | 2026-04-21 | [11 empty] | Kameshwari
|  |  |  | 12th Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-04-22 | [9 empty] | Lokesh |  | Kameshwari
|  |  |  | Columns (Residential) lift - 13 verticals |  | Not Yet Started | 2026-04-23 | [9 empty] | Lokesh |  | Eswar
|  |  |  | Shear walls (Residential) lift - 13 verticals |  | Not Yet Started | 2026-04-24 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Cmu walls lift - 13 verticals |  | Not Yet Started | 2026-04-25 | [9 empty] | Eswar |  | Eswar
|  |  |  | 13th Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-04-26 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Columns (Residential) lift - 14 verticals |  | Not Yet Started | 2026-04-27 | [9 empty] | Swathi |  | Kameshwari
|  |  |  | Shear walls (Residential) lift - 14 verticals |  | Not Yet Started | 2026-04-28 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | Cmu walls lift - 14 verticals |  | Not Yet Started | 2026-04-29 | [9 empty] | Vaishnavi |  | Kameshwari
|  |  |  | 14th Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-04-30 | [9 empty] | Lokesh |  | Kameshwari
|  |  |  | Columns (Residential) lift - 15 verticals |  | Not Yet Started | 2026-05-01 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Shear walls (Residential) lift - 15 verticals |  | Not Yet Started | 2026-05-02 | [9 empty] | Eswar |  | Kameshwari
|  |  |  | Cmu walls lift - 15 verticals |  | Not Yet Started | 2026-05-03 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | 15th floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-05-04 | [9 empty] | Swathi |  | Eswar
|  |  |  | Columns (Residential) lift - 16 verticals |  | Not Yet Started | 2026-05-05 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Shear walls (Residential) lift - 16 verticals |  | Not Yet Started | 2026-05-06 | [9 empty] | Vaishnavi |  | Eswar
|  |  |  | Cmu walls lift - 16 verticals |  | Not Yet Started | 2026-05-07 | [9 empty] | Lokesh |  | Eswar
|  |  |  | Roof Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-05-08 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | Parapet walls (Residential) verticals | 05-14-2026 | Not Yet Started | 2026-05-09 | [9 empty] | Eswar |  | Kameshwari
[6 empty] | Not Yet Started | 2026-05-10 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Foundations (Garage) | 05-14-2026 | Not Yet Started | 2026-05-11 | [9 empty] | Swathi |  | Kameshwari
|  |  |  | Slab on grade (Garage) | 05-14-2026 | Not Yet Started | 2026-05-12 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | Columns (Garage) | 05-14-2026 | Not Yet Started | 2026-05-13 | [9 empty] | Vaishnavi |  | Eswar
|  |  |  | Shear walls (Garage) | 05-14-2026 | Not Yet Started | 2026-05-14 | [9 empty] | Lokesh |  | Eswar
|  |  |  | 2nd Floor slab (Garage) | 05-14-2026 | Not Yet Started | 2026-05-15 | [9 empty] | Pradeep |  | Eswar
|  |  |  | 3rd Floor slab (Garage) | 05-14-2026 | Not Yet Started | 2026-05-16 | [9 empty] | Eswar |  | Eswar
|  |  |  | 4th Floor slab (Garage) | 05-14-2026 | Not Yet Started | 2026-05-17 | [9 empty] | Pradeep |  | Kameshwari
|  |  |  | 5th Floor slab (Garage) | 05-14-2026 | Not Yet Started | 2026-05-18 | [9 empty] | Swathi |  | Kameshwari
|  |  |  | 6th Floor slab (Garage) | 05-14-2026 | Not Yet Started | 2026-05-19 | [9 empty] | Pradeep |  | Eswar
46 |  | 6007 Le Lac (Furing residence) | CIP | Foundations & Walls (scope added) | 05-14-2026 | Completed | 05-16-2026 |  |  | 1.513 |  |  |  |  | 05-16-2026 | COMPLETED | Pradeep | COMPLETED | NANAJI
|  |  |  | Cabana slab on grade | 06-16-2026 | Completed | 06-25-2026 | [11 empty] | NANAJI
47 |  | 90 Stingaree | CIP & CMU | Slab on grade | 05-15-2026 | Completed | 2026-05-06 | [9 empty] | siva kumar |  | NANAJI
|  |  |  | Lift - 1 verticals and beams | 05-15-2026 | Inprogress | 06-26-2026 | [9 empty] | Praveena |  | NANAJI
48 |  | O.B. (Scattered Lots) | CIP & CMU | Foundaitons & sog. | 05-15-2026 | Completed | 05-18-2026 |  |  | 0.725 |  |  |  |  | 05-18-2026 | COMPLETED | Lokesh Reddy | COMPLETED | ESWAR | PDF CHECK ONLY
|  |  |  | Lift - 1 verticals and beams |  | Completed | 05-23-2026
49 |  | 840 Denery Ln. Residence |  | Foundaitons & Slab on grade | 05-16-2026 | Completed | 05-30-2026 |  |  | 9.9 |  |  |  |  | 05-30-2026 | COMPLETED | eswar/siav kumar | NOT YET STARTED | ESWAR | PDF CHECK ONLY
|  |  |  | Lift - 1 verticals and bond beams |  | Completed | 05-30-2026 |  |  | 4.453 |  |  |  |  | 05-30-2026 | COMPLETED | siav kumar | NOT YET STARTED | ESWAR | PDF CHECK ONLY
|  |  |  | 2nd floor slab & beams |  | Inprogress | 2026-03-07 | [9 empty] | Sridevi |  | ESWAR
|  |  |  | Lift - 2 verticals and bond beams |  | Not Yet Started | 2026-03-07 | [9 empty] | Praveena |  | ESWAR
|  |  |  | Roof beams |  | Not Yet Started | 2026-03-07 | [9 empty] | Praveena/Sridevi |  | ESWAR
50 |  | Nuvo | CIP & CMU | Bldg. Type 1 (A, C, D & G) | [14 empty] | Eswar
|  |  |  | Foundations and slab on grade | 05-22-2026 | Completed | 2026-12-06 | [9 empty] | siva kumar |  | Kameshwari
|  |  |  | Lift - 1 verticals and beams | 05-22-2026 | Completed | 06-13-2026 | 2026-12-06 | [6 empty] | 06-16-2026 | COMPLETED | Sridevi | NOT YET STARTED | Kameshwari
|  |  |  | 2nd Flr. Thru 2nd lift & 2nd floor beams | 05-22-2026 | Not Yet Started | 06-19-2026 | [9 empty] | siva kumar |  | Eswar
|  |  |  | 3rd Flr. Thru 3rd lift & 3rd floor beams | 05-22-2026 | Not Yet Started | 06-26-2026 | [9 empty] | siva kumar |  | Eswar
|  |  |  | 4th Flr. Thru Roof & Abv Roof beams | 05-22-2026 | Not Yet Started | 2026-03-07 | [9 empty] | siva kumar |  | Eswar
[17 empty] | Pradeep |  | Eswar
|  |  |  | Bldg. Type 2 (E & H) | [12 empty] | Swathi |  | Kameshwari
|  |  |  | Foundations and slab on grade | 05-22-2026 | Completed | 06-15-2026 | [9 empty] | Lokesh Reddy |  | Kameshwari
|  |  |  | Lift - 1 verticals and beams | 05-22-2026 | Completed | 06-15-2026 | [9 empty] | siva kumar |  | Eswar
|  |  |  | 2nd Flr. Thru 2nd lift & 2nd floor beams | 05-22-2026 | Not Yet Started | 06-19-2026 | [9 empty] | Lokesh Reddy |  | Kameshwari
|  |  |  | 3rd Flr. Thru 3rd lift & 3rd floor beams | 05-22-2026 | Not Yet Started | 06-26-2026 | [9 empty] | Lokesh Reddy |  | Kameshwari
|  |  |  | 4th Flr. Thru Roof & Abv Roof beams | 05-22-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Lokesh Reddy |  | Eswar
[17 empty] | Pradeep |  | Eswar
|  |  |  | Bldg. Type 3 (B & F) | [12 empty] | Swathi |  | Eswar
|  |  |  | Elevator Pits & Stairs, Bg Thru 1st lift | 05-22-2026 | Inprogress | 06-16-2026 | [9 empty] | Lokesh Reddy |  | Eswar
|  |  |  | 2nd Flr. Thru 2nd lift & 2nd floor beams | 05-22-2026 | Not Yet Started | 06-19-2026 | [9 empty] | siva kumar |  | Kameshwari
|  |  |  | 3rd Flr. Thru 3rd lift & 3rd floor beams | 05-22-2026 | Not Yet Started | 06-26-2026 | [9 empty] | Lokesh Reddy/Siva kumar |  | Kameshwari
|  |  |  | 4th Flr. Thru Roof & Abv Roof beams | 05-22-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Lokesh Reddy/Siva kumar |  | Eswar
[17 empty] | Sridevi |  | Kameshwari
|  |  |  | Bus Shelter - Footings | [12 empty] | Praveena |  | Kameshwari
|  |  |  | Bg Thru 1st lift | 05-22-2026 | Not Yet Started | 07-24-2026 | [9 empty] | Pradeep |  | Kameshwari
[17 empty] | siva kumar |  | Eswar
|  |  |  | Clubhouse | [12 empty] | Pavan sai |  | Eswar
|  |  |  | Bg Thru Abv Roof beams | 05-22-2026 | Completed | 2026-05-06 | [9 empty] | siva kumar |  | Eswar
[17 empty] | siva kumar |  | Eswar
|  |  |  | Garage Type 1 | [12 empty] | Pavan sai |  | Kameshwari
|  |  |  | Bg Thru Abv Roof beams | 05-22-2026 | Inprogress | 2026-10-07 | [9 empty] | Pavan sai |  | Kameshwari
[17 empty] | Sridevi |  | Eswar
|  |  |  | Garage Type 2 | [12 empty] | Praveena |  | Kameshwari
|  |  |  | Bg Thru Abv Roof beams | 05-22-2026 | Inprogress | 2026-10-07 | [9 empty] | Pradeep |  | Kameshwari
[17 empty] | Sridevi |  | Eswar
|  |  |  | Mail Kiosk - Slab on grade | [12 empty] | Praveena |  | Eswar
|  |  |  | Slab on grade | 05-22-2026 | Inprogress | 2026-10-07 | [9 empty] | Pradeep |  | Eswar
[17 empty] | Sridevi |  | Eswar
|  |  |  | Trash Compactor | [12 empty] | Praveena |  | Kameshwari
|  |  |  | Bg Thru 1st lift | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | Kameshwari
[17 empty] | Sridevi |  | Eswar
|  |  |  | Pool Pavilion | [12 empty] | Praveena |  | Eswar
|  |  |  | Bg Thru Roof beams | 05-22-2026 | Not Yet Started | 07-17-2026 | [9 empty] | Pradeep |  | Eswar
[17 empty] | Sridevi |  | Eswar
|  |  |  | Raised Planters | [12 empty] | Praveena |  | Kameshwari
|  |  |  | Bg Thru 1st lift | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | Kameshwari
[17 empty] | Sridevi |  | Eswar
|  |  |  | BBQ Station | [12 empty] | Praveena |  | Kameshwari
|  |  |  | Bg Thru Roof beams | 05-22-2026 | Not Yet Started | 07-17-2026 | [9 empty] | Pradeep |  | Kameshwari
[17 empty] | Sridevi |  | Eswar
|  |  |  | Cabana Footings | [12 empty] | Praveena |  | Eswar
|  |  |  | Bg Thru 1st lift | 05-22-2026 | Not Yet Started | 07-17-2026 | [9 empty] | Pradeep |  | Eswar
[17 empty] | Sridevi |  | Eswar
|  |  |  | Trellis Footings | [12 empty] | Praveena |  | Kameshwari
|  |  |  | Bg Thru 1st lift | 05-22-2026 | Not Yet Started | 07-17-2026 | [9 empty] | Pradeep |  | Kameshwari
[17 empty] | Lalitha |  | Eswar
|  |  |  | Retaining Wall | 05-22-2026 | Completed | 2026-12-06 |  |  | 29.997 |  |  |  |  | 2026-11-06 | COMPLETED | Pradeep | COMPLETED | NANAJI
|  |  |  | Bg Thru 1st lift | 05-22-2026 | Completed | 2026-12-06 | 2026-05-06 | [8 empty] | Pradeep
51 |  | The Syed Residence | CIP & CMU | Foundations & Slab on grade | 05-23-2026 | Completed | 2026-06-05 | [9 empty] | Eswar |  | Kameshwari
|  |  |  | Lift - 1 verticals and beams | 05-23-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Jagadeesh |  | Kameshwari
|  |  |  | Lift - 2 verticals and beams | 05-23-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Nanaji |  | Eswar
52 |  | 810 S Swinton Ave Residence | CIP & CMU | Foundations and slab on grade | 05-26-2026 | Inprogress | 2026-09-06 | [9 empty] | Praveena |  | Eswar
|  |  |  | Lift - 1 verticals and beams | 05-26-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Pradeep |  | Eswar
|  |  |  | Lift - 2 verticals and beams | 05-26-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Swathi |  | Kameshwari
53 |  | Custom Residence (134 Worth CTN) | CIP & CMU | Foundations | 05-29-2026 | Completed | 06-13-2026 | [9 empty] | Praveena |  | Eswar
|  |  |  | Slab on grade | 05-29-2026 | Completed | 06-13-2026 | [9 empty] | Vaishnavi |  | NANAJI
|  |  |  | Lift - 1 verticals and beams | 05-29-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Jagadeesh |  | Eswar
|  |  |  | Lift - 2 verticals and beams | 05-29-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Eswar |  | NANAJI
54 |  | Rancano | CIP & CMU | Foundations & slab on grade | 05-29-2026 | Completed | 2026-11-06 |  |  | 6.108 | [6 empty] | Eswar
|  |  |  | Lift - 1 verticals and Roof beams | 05-29-2026 | Completed | 06-17-2026 |  |  | 1.66 |  |  |  |  | 06-16-2026 | COMPLETED | Sridevi | COMPLETED | NANAJI
55 |  | 799 Park Drive | CIP & CMU | Foundations & Slab on grade | 2026-09-06 | Completed | 06-16-2026 |  |  | 2.264 |  |  |  |  | 06-16-2026 | COMPLETED | Pradeep | COMPLETED | Nanaji
|  |  |  | Lift - 1 verticals and beams | 2026-09-06 | Inprogress | 06-19-2026 | [9 empty] | Pradeep
|  |  |  | Lift - 2 verticals and beams | 2026-09-06 | Not Yet Started | 06-26-2026 | [9 empty] | Pradeep
Kameshwari
56 |  | Chateau De La Duchess (925 Hillsboro) | CIP & CMU | Entry Garages foundations and slab on grade | 08-25-2025 | Inprogress | 2026-03-07 | [9 empty] | Eswar |  | Kameshwari
|  |  |  | Entry Garages lift - 1 verticals and beams | 08-25-2025 | Not Yet Started | 2026-03-07 | [9 empty] | Sridevi |  | Eswar
|  |  |  | Entry Garages lift - 2 verticals and beams | 08-25-2025 | Not Yet Started | 2026-03-07 | [9 empty] | Praveena |  | Eswar
Eswar
57 |  | Masucci Residence | CIP & CMU | Foundations & slab on grade | 06-18-2025 | Inprogress | 06-26-2026 | [9 empty] | Eswar |  | Eswar
|  |  |  | Lift - 1 verticals and beams | 06-18-2025 | Not Yet Started | 2026-03-07 | [9 empty] | Sridevi |  | Kameshwari
|  |  |  | 2nd floor slab and beams | 06-18-2025 | Not Yet Started | 2026-03-07 | [9 empty] | Praveena |  | Kameshwari
|  |  |  | Lift - 2 verticals and beams | 06-18-2025 | Not Yet Started | 2026-03-07 | [9 empty] | Pradeep |  | Eswar
NANAJI
58 |  | The Bueller family | CIP & CMU | Foundations & slab on grade | 06-20-2025 | Inprogress | 06-26-2026 | [9 empty] | Praveena |  | Eswar
|  |  |  | Lift - 1 verticals and beams | 06-20-2025 | Not Yet Started | 06-26-2026 | [9 empty] | Pradeep |  | Eswar
Eswar
59 |  | SPOTLOT 28810 SW 207 AVE | CIP & CMU | Foundations & slab on grade | 06-20-2025 | Inprogress | 06-26-2026 | [9 empty] | Eswar |  | Kameshwari
|  |  |  | Lift - 1 verticals and beams | 06-20-2025 | Not Yet Started | 06-26-2026 | [9 empty] | Sridevi |  | Kameshwari
Eswar
60 |  | Broken Sound Club | CIP | Foundations & slab on grade | 06-20-2025 | Completed | 06-26-2026 | [9 empty] | Eswar
|  |  |  | Lift - 1 verticals and beams | 06-20-2025 | Completed | 06-26-2026 | [9 empty] | Sridevi
Praveena
Pradeep
OLD PROJECTS MODIFICATIONS
1 |  | 1333 Bvld | Barlists | Shear walls and columns Barlists | 2026-05-05 | Completed | 2026-07-05 | [9 empty] | Lokesh Reddy |  | Eswar
2 |  | Valencia Del Mar Clubhouse | Barlists | Slab on grade Barlists | 2026-05-05 | Completed | 2026-05-05 | [9 empty] | Vaishnavi |  | Kameshwari
3 |  | 320 S atlantic Drive | Barlists | Foundations Barlists | 2026-05-05 | Completed | 2026-05-05 | [9 empty] | Sridevi |  | Kameshwari
4 |  | 910 S Ocean | Emds | Comments received on basement R1series dwgs | 2026-05-05 | Completed | 2026-06-05 | [9 empty] | Sridevi |  | Eswar
5 |  | 6024 Le lac Rd | Emds | Comments received on pool cabana & outdoor kitchen | 2026-05-05 | Completed | 2026-07-05 | [9 empty] | Sridevi / Vaishnavi |  | NANAJI
6 |  | 6017 Le Lac Road (Weiner Residence) | Barlists | Barlists requested for 2story building lift - 1 verticals | 2026-05-05 | Completed | 2026-06-05 | [9 empty] | Vaishnavi |  | Eswar
7 |  | South Rd Office Building E | Barlists | Lift - 1 Verticals and beams | 2026-05-05 | Completed | 2026-07-05 | [9 empty] | Vaishnavi |  | Eswar
8 |  | 559 Nw 43 st | Barlists | Stairs barlists | 2026-05-05 | Completed | 2026-06-05 | [9 empty] | Danush |  | Eswar
9 |  | PBIA - Revenue Control Building | Emds | Rfi-029 received on foundaitons | 2026-07-05 | Completed | 2026-08-05 | [9 empty] | Vaishnavi |  | Kameshwari
10 |  | Sands residence (3223 N Ocean) | Emds | Ssk-017 Received for 2nd for slab at balcony | 2026-07-05 | Completed | 2026-08-05 | [9 empty] | Eswar |  | Kameshwari
11 |  | 5900 Powerline Garage | Barlists | Foundations (Grade beams) | 2026-07-05 | Completed | 2026-08-05 | [9 empty] | Pradeep |  | Eswar
13 |  | 1050 N Lake way | Barlists | 2nd lift - 2 verticals and beams | 2026-09-05 | Completed | 2026-09-05 | [9 empty] | Lokesh Reddy |  | Eswar
14 |  | Baig Residence | Barlists | 2nd floor slab | 2026-09-05 | Completed | 2026-09-05 | [9 empty] | Lokesh Reddy |  | Kameshwari
15 |  | South Rd Office Building E | Patch | Need patch lists for cmu walls at stem walls | 2026-11-05 | Completed | 2026-09-05 | [9 empty] | Lokesh Reddy |  | Kameshwari
16 |  | Valencia Del Mar Clubhouse | Barlists | Lift - 1 verticals section #3 | 05-19-2026 | Completed | 05-19-2026 | [9 empty] | Danush |  | Eswar
17 |  | South Rd Office Building E | Barlists | Lift -1 verticals barlists | 05-13-2026 | Completed | 05-13-2026 | [9 empty] | Lokesh Reddy |  | NANAJI
18 |  | 2651 SE 10th Court | Barlists | Pool deck slab and beams barlists | 05-14-2026 | Completed | 05-18-2026 | [9 empty] | Vaishnavi |  | Eswar
19 |  | 6017 Le Lac Road (Weiner Residence) | Barlists | Orange section #2 1st lift verticals | 05-18-2026 | Completed | 05-19-2026 | [9 empty] | Vaishnavi |  | Eswar
20 |  | 1333 Bvld | Barlists | Stem walls barlists | 05-18-2026 | Completed | 05-18-2026 | [9 empty] | Danush |  | Eswar
21 |  | 2651 SE 10th Court | Emds | Update received on the pool deck | 05-18-2026 | Completed | 05-19-2026 | [9 empty] | Danush |  | NANAJI
22 |  | cannatelli | Barlists | Foundations and slab on grade Barlists | 05-18-2026 | Completed | 05-18-2026 | [9 empty] | Lokesh Reddy |  | Eswar
23 |  | 6017 Le Lac Road (Weiner Residence) | Barlists | Lift - 1 verticals and beams for Blue section | 05-19-2026 | Completed | [10 empty] | Lokesh Reddy |  | Eswar
24 |  | 401 SE Atlantic Drive | Barlists | Barlists for R3 series drawings | 05-19-2026 | Completed | 05-20-2026 | [9 empty] | Danush |  | Eswar
25 |  | 515 Lido Drive | Barlists | Column ties for upto 4'-0" | 05-19-2026 | Completed | 05-20-2026 | [9 empty] | Lokesh Reddy |  | NANAJI
26 |  | 143 Reef Road | Updated drawings | 1st floor beams and second floor slab | 05-20-2026 | Completed | [10 empty] | Vaishnavi |  | Eswar
27 |  | PBIA - Revenue Control Building | Revised drawings | Revised drawings received on cmu verticals | 05-21-2026 | Completed | 05-22-2026 | [9 empty] | Vaishnavi |  | Eswar
28 |  | 515 Lido Drive | Barlists | Garage slab barlists | 05-21-2026 | Completed | 05-21-2026 | [9 empty] | Danush |  | Eswar
29 |  | cannatelli | Barlists | Foundations and slab on grade Barlists | 05-21-2026 | Completed | 05-23-2026 | [9 empty] | Danush |  | NANAJI
30 |  | 1042 Palm Way Road | Revised drawings | Roof beams and slab | 05-22-2026 | Completed | 05-28-2026 | [9 empty] | Lokesh Reddy |  | Eswar
31 |  | South Rd Office Building E | Emds | Comments received on 1st lift verticals and beams | 05-21-2026 | Inprogress | 05-22-2026 | [9 empty] | Lokesh Reddy |  | Eswar
32 |  | 910 S Ocean | Barlists | Basement slab barlists | 05-26-2026 | Completed | 05-27-2026 | [9 empty] | Danush |  | Eswar
33 |  | Valencia Del Mar Clubhouse | Barlists | Lift - 2 verticals and beams for green section #2 | 05-26-2026 | Inprogress | 05-28-2026 | [9 empty] | Lokesh Reddy |  | NANAJI
34 |  | Valencia Del Mar Clubhouse | Barlists | Lift - 2 verticals and beams for Yellow section #1 | 05-26-2026 | Inprogress | 05-28-2026 | [9 empty] | Vaishnavi |  | Eswar
35 |  | Burns Residence | Barlists | Slab on grade barlists | 05-28-2026 | Inprogress | 05-28-2026 | [9 empty] | Vaishnavi |  | Eswar
36 |  | 1900 NE 22ND Terrance | Emds | Comments received on slab on grade | 05-28-2026 | Inprogress | 05-28-2026 | [9 empty] | Danush |  | Eswar
[17 empty] | Danush |  | NANAJI
[17 empty] | Lokesh Reddy |  | Eswar
[17 empty] | Lokesh Reddy |  | Eswar
[8 empty] | Totals | 0 | 982.285 | 0 | 0 | 0 | 0
Note: Submittal dates may change according to client request / RFI Clarification /Priorities