## Tasks
Dimension Fab
Projects | Tasks | Sub Date | Statues | Detailer | Checker
20817- VERGENNES WATER TREATMEN | INFLUENT BLDG. Foundations & Wall dowels -1ST | 08/25/2026 | In Progress | Anji Reddy | Anji Reddy
| SBR COMPLEX Base slab & Wall dowels-2ND | 2026-01-09 | Not Yet Started | Anji Reddy | Anji Reddy
| INFLUENT WALLS-3RD | 2026-09-09 | Not Yet Started | Anji Reddy | Anji Reddy
| INFLUENT SLAB-4TH | 09/14/2026 | Not Yet Started | Anji Reddy | Anji Reddy
| SBR WALLS 5TH | 09/25/2026 | Not Yet Started | Anji Reddy | Anji Reddy
| SBR- Walkway Slab 6TH | 09/29/2026 | Not Yet Started | Anji Reddy | Anji Reddy