## Table 1
S.No | PROJECT NAME | SCOPE | COMPONENTS OF WORK | REC. DATE | STATUS | SUB. DATE
1 | ALTON DELRAY | CIP & CMU | Bldg #2 Type II - 2nd floor slab | 2026-07-06 | IN PROGRESS | 2026-08-19
| ALTON DELRAY | CIP & CMU | Bldg #2 Type II - 3rd floor slab | 2026-07-06 | IN PROGRESS | 2026-08-19
| ALTON DELRAY | CIP & CMU | Bldg #2 Type II - 4th floor slab | 2026-07-06 | IN PROGRESS | 2026-08-19
| ALTON DELRAY | CIP & CMU | Bldg #2 Type II - 5th floor slab | 2026-07-06 | IN PROGRESS | 2026-08-19
| ALTON DELRAY | CIP & CMU | Bldg #2 Type II - Roof slab | 2026-07-06 | IN PROGRESS | 2026-08-19
| ALTON DELRAY | CIP & CMU | Bldg #2 Type II - Tunnel walls | 2026-07-06 | IN PROGRESS | 2026-08-19
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - 2nd floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - 3rd floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - 4th floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - 5th floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Roof slab | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Upper roof slab | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Tunnel walls | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Lift-1 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Lift-2 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Lift-3 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Lift-4 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Lift-5 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #3 Type III - Lift-6 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-22
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - 2nd floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - 3rd floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - 4th floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - 5th floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - 6th floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Roof slab | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Upper roof slab | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Tunnel walls | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Lift-1 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Lift-2 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Lift-3 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Lift-4 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Lift-5 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #5 Type I - Lift-6 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-28
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - 2nd floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - 3rd floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - 4th floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - 5th floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - 6th floor slab | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Roof slab | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Upper roof slab | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Tunnel walls | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Lift-1 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Lift-2 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Lift-3 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Lift-4 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Lift-5 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-31
| ALTON DELRAY | CIP & CMU | Bldg #4 Type I - Lift-6 verticals | 2026-07-06 | NOT YET STARTED | 2026-08-31
2 | Octavia | CIP & CMU | GARAGE CMU & LINTELS (2ND TO 3RD) | 2026-05-01 | NOT YET STARTED | 2026-08-28
| Octavia | CIP & CMU | GARAGE CMU & LINTELS (3RD TO 4TH) | 2026-05-01 | NOT YET STARTED | 2026-08-29
| Octavia | CIP & CMU | RESIDENTIAL 7TH LVL SLAB | 2026-05-01 | IN PROGRESS | 2026-08-19
| Octavia | CIP & CMU | GARAGE CMU & LINTELS (4TH TO 5TH) | 2026-05-01 | NOT YET STARTED | 2026-08-31
| Octavia | CIP & CMU | RESIDENTIAL CMU & LINTELS (7TH TO 8TH) | 2026-05-01 | NOT YET STARTED | 2026-08-20
| Octavia | CIP & CMU | GARAGE SOG SLAB | 2026-05-01 | NOT YET STARTED | 2026-08-20
| Octavia | CIP & CMU | RESIDENTIAL 8TH LVL SLAB | 2026-05-01 | NOT YET STARTED | 2026-08-28
| Octavia | CIP & CMU | GARAGE CMU & LINTELS (5TH TO 6TH) | 2026-05-01 | NOT YET STARTED | 2026-08-25
| Octavia | CIP & CMU | RESIDENTIAL CMU & LINTELS (8TH TO ROOF) | 2026-05-01 | NOT YET STARTED | 2026-08-26
| Octavia | CIP & CMU | RESIDENTIAL ROOF LVL SLAB | 2026-05-01 | NOT YET STARTED | 2026-08-31
| Octavia | CIP & CMU | GARAGE CMU & LINTELS (6TH TO 7TH) | 2026-05-01 | NOT YET STARTED | 2026-09-01
| Octavia | CIP & CMU | GARAGE CMU & LINTELS (7TH TO 8TH) | 2026-05-01 | NOT YET STARTED | 2026-09-08
| Octavia | CIP & CMU | GARAGE CMU & LINTELS (GRND TO 2ND) | 2026-05-01 | NOT YET STARTED | 2026-09-15
3 | Magnolia Point | CIP & CMU | BLDG 1 Type II - Foundations & SOG | 2026-04-27 | NOT YET STARTED | 2026-08-28
| Magnolia Point | CIP & CMU | BLDG 1 Type II - 2nd floor slab | 2026-04-27 | NOT YET STARTED | 2026-09-04
| Magnolia Point | CIP & CMU | BLDG 1 Type II - 3rd floor slab | 2026-04-27 | NOT YET STARTED | 2026-09-09
| Magnolia Point | CIP & CMU | BLDG 1 Type II - 4th floor slab | 2026-04-27 | NOT YET STARTED | 2026-09-09
| Magnolia Point | CIP & CMU | BLDG 1 Type II - 5th floor slab | 2026-04-27 | NOT YET STARTED | 2026-09-09
| Magnolia Point | CIP & CMU | BLDG 1 Type II - 6th floor slab | 2026-04-27 | NOT YET STARTED | 2026-09-09
| Magnolia Point | CIP & CMU | BLDG 1 Type II - Roof level slab | 2026-04-27 | NOT YET STARTED | 2026-09-11
| Magnolia Point | CIP & CMU | BLDG 1 Type II - Lift-1 verticals | 2026-04-27 | NOT YET STARTED | 2026-09-16
| Magnolia Point | CIP & CMU | BLDG 1 Type II - Lift-2 verticals | 2026-04-27 | NOT YET STARTED | 2026-09-16
| Magnolia Point | CIP & CMU | BLDG 1 Type II - Lift-3 verticals | 2026-04-27 | NOT YET STARTED | 2026-09-16
| Magnolia Point | CIP & CMU | BLDG 1 Type II - Lift-4 verticals | 2026-04-27 | NOT YET STARTED | 2026-09-16
| Magnolia Point | CIP & CMU | BLDG 1 Type II - Lift-5 verticals | 2026-04-27 | NOT YET STARTED | 2026-09-16
| Magnolia Point | CIP & CMU | BLDG 1 Type II - Lift-6 & parapet verticals | 2026-04-27 | NOT YET STARTED | 2026-09-16
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - Foundations & SOG | 2026-04-27 | NOT YET STARTED | 2026-09-21
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - 2nd floor slab | 2026-04-27 | NOT YET STARTED | 2026-09-25
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - 3rd floor slab | 2026-04-27 | NOT YET STARTED | 2026-09-25
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - 4th floor slab | 2026-04-27 | NOT YET STARTED | 2026-09-25
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - 5th floor slab | 2026-04-27 | NOT YET STARTED | 2026-09-25
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - 6th floor slab | 2026-04-27 | NOT YET STARTED | 2026-09-25
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - Roof level slab | 2026-04-27 | NOT YET STARTED | 2026-09-28
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - Lift-1 verticals | 2026-04-27 | NOT YET STARTED | 2026-09-30
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - Lift-2 verticals | 2026-04-27 | NOT YET STARTED | 2026-09-30
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - Lift-3 verticals | 2026-04-27 | NOT YET STARTED | 2026-09-30
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - Lift-4 verticals | 2026-04-27 | NOT YET STARTED | 2026-09-30
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - Lift-5 verticals | 2026-04-27 | NOT YET STARTED | 2026-09-30
| Magnolia Point | CIP & CMU | BLDG 2 Type VI - Lift-6 & parapet verticals | 2026-04-27 | NOT YET STARTED | 2026-09-30
| Magnolia Point | CIP & CMU | BLDG 5 Type VII - Foundations & SOG | 2026-04-27 | NOT YET STARTED | 2026-10-07
| Magnolia Point | CIP & CMU | BLDG 5 Type VII - 2nd floor slab | 2026-04-27 | NOT YET STARTED | 2026-10-12
| Magnolia Point | CIP & CMU | BLDG 5 Type VII - 3rd floor slab | 2026-04-27 | NOT YET STARTED | 2026-10-12
| Magnolia Point | CIP & CMU | BLDG 5 Type VII - Roof level slab | 2026-04-27 | NOT YET STARTED | 2026-10-16
| Magnolia Point | CIP & CMU | BLDG 5 Type VII - Lift-1 verticals | 2026-04-27 | NOT YET STARTED | 2026-10-21
| Magnolia Point | CIP & CMU | BLDG 5 Type VII - Lift-2 verticals | 2026-04-27 | NOT YET STARTED | 2026-10-21
| Magnolia Point | CIP & CMU | BLDG 5 Type VII - Lift-3 & parapet verticals | 2026-04-27 | NOT YET STARTED | 2026-10-21
| Magnolia Point | CIP & CMU | BLDG 4 Type III - Foundations & SOG | 2026-04-27 | NOT YET STARTED | 2026-10-12
| Magnolia Point | CIP & CMU | BLDG 4 Type III - 2nd floor slab | 2026-04-27 | NOT YET STARTED | 2026-10-12
| Magnolia Point | CIP & CMU | BLDG 4 Type III - 3rd floor slab | 2026-04-27 | NOT YET STARTED | 2026-10-12
| Magnolia Point | CIP & CMU | BLDG 4 Type III - 4th floor slab | 2026-04-27 | NOT YET STARTED | 2026-10-12
| Magnolia Point | CIP & CMU | BLDG 4 Type III - 5th floor slab | 2026-04-27 | NOT YET STARTED | 2026-10-12
| Magnolia Point | CIP & CMU | BLDG 4 Type III - Roof level slab | 2026-04-27 | NOT YET STARTED | 2026-10-16
| Magnolia Point | CIP & CMU | BLDG 4 Type III - Lift-1 verticals | 2026-04-27 | NOT YET STARTED | 2026-10-21
| Magnolia Point | CIP & CMU | BLDG 4 Type III - Lift-2 verticals | 2026-04-27 | NOT YET STARTED | 2026-10-21
| Magnolia Point | CIP & CMU | BLDG 4 Type III - Lift-3 verticals | 2026-04-27 | NOT YET STARTED | 2026-10-21
| Magnolia Point | CIP & CMU | BLDG 4 Type III - Lift-4 verticals | 2026-04-27 | NOT YET STARTED | 2026-10-21
| Magnolia Point | CIP & CMU | BLDG 4 Type III - Lift-5 & parapet verticals | 2026-04-27 | NOT YET STARTED | 2026-10-21
4 | Bird Arts | CIP & CMU | 2nd floor slab & beams | 2026-07-02 | IN PROGRESS | 2026-08-27
| Bird Arts | CIP & CMU | 3rd floor slab & beams | 2026-07-02 | NOT YET STARTED | 2026-09-04
| Bird Arts | CIP & CMU | 4th floor slab & beams | 2026-07-02 | NOT YET STARTED | 2026-09-04
| Bird Arts | CIP & CMU | 5th floor slab & beams | 2026-07-02 | NOT YET STARTED | 2026-09-11
| Bird Arts | CIP & CMU | 6th floor slab & beams | 2026-07-02 | NOT YET STARTED | 2026-09-11
| Bird Arts | CIP & CMU | 7th floor slab & beams | 2026-07-02 | NOT YET STARTED | 2026-09-18
| Bird Arts | CIP & CMU | 8th floor slab & beams | 2026-07-02 | NOT YET STARTED | 2026-09-18
| Bird Arts | CIP & CMU | Roof slab & beams | 2026-07-02 | NOT YET STARTED | 2026-09-25
| Bird Arts | CIP & CMU | Lift-1 Masonry Verticals | 2026-07-02 | NOT YET STARTED | 2026-09-09
| Bird Arts | CIP & CMU | Lift-2 Masonry Verticals | 2026-07-02 | NOT YET STARTED | 2026-09-16
| Bird Arts | CIP & CMU | Lift-3 Masonry Verticals | 2026-07-02 | NOT YET STARTED | 2026-09-16
| Bird Arts | CIP & CMU | Lift-4 Masonry Verticals | 2026-07-02 | NOT YET STARTED | 2026-09-23
| Bird Arts | CIP & CMU | Lift-5 Masonry Verticals | 2026-07-02 | NOT YET STARTED | 2026-09-23
| Bird Arts | CIP & CMU | Lift-6 Masonry Verticals | 2026-07-02 | NOT YET STARTED | 2026-09-30
| Bird Arts | CIP & CMU | Lift-7 Masonry Verticals | 2026-07-02 | NOT YET STARTED | 2026-09-30
| Bird Arts | CIP & CMU | Lift-8 Masonry Verticals | 2026-07-02 | NOT YET STARTED | 2026-10-07
| Bird Arts | CIP & CMU | Lift-9 Masonry Verticals | 2026-07-02 | NOT YET STARTED | 2026-10-07