## May 1st Week
Rebar Department Weekly Project Status Report-April 2026
Date Range |  | 05/04/2026 to 05/09/2026
Projects & Actives for Above dates
S.no | Client | Project name | Description | Tonnage | Hours | Status | Remarks |  | Detaielrs
1
2
3
4
5
Total |  |  |  | 0 | 0 |  |  | 0
Projects & Actives Planned to This week
Total |  |  |  | 0 | 0 |  |  | 0
Work in hand
1 |  | 143 Reef Road | Lift - 1 Verticals
Lift - 1 Beams & 2nd floor slab
Roof beams
2 |  | 6017 Le Lac Road (Weiner Residence) | Lift - 2 Verticals and roof beams (Main Building)
Lift - 1 Verticals, 2nd floor slab and beams (2-story residence)
Lift - 2 Verticals and roof beams (2-story residence)
3 |  | 164 Seminole | Slab on grade | [5 empty] | Siva Kumar
|  |  | Lift - 1 Verticals, 2nd floor slab and beams | [5 empty] | Siva Kumar
|  |  | Lift - 2 Verticals and roof beams | [5 empty] | Siva Kumar
4 |  | Roy & Shelley Silverman | Lift - 1 Beams | [5 empty] | Nanaji
|  |  | Lift - 2 Verticals & Roof beams | [5 empty] | Sridivi/Nanaji
5 |  | Valencia Del Mar Clubhouse | Lift - 1 Verticals and beams
Lift - 2 Verticals and beams
6 |  | Burns Residence | Lift - 1 Verticals and Beams
Lift - 2 Verticals and beams
7 |  | 320 S atlantic Drive | Lift - 1 Verticals, 2nd Floor slab & beams
Lift - 2 Verticals and Roof beams
8 |  | Custom Residence (515 lido drive) | Lift - 1 Verticals, 2nd floor slab & beams
Lift - 2 Verticals & Roof beams
9 |  | Jandrews Residence | Lift - 1 Verticals and beams
Lift - 2 Verticals and beams
10 |  | 5900 Powerline Garage | Lift - 1 Verticals and Roof beams | [5 empty] | Pradeep
11 |  | South Florida Jewish Cemetery | Foundations and slab on grade | [5 empty] | Vaishnavi
Lift - 1 Verticals and Roof Beams
12 |  | 20 Hudson Ave | Foundations & slab on grade
Lift - 1 Verticals and Beams
Lift - 2 Verticals and Beams
13 |  | Baig Residence | 3rd Floor tie beams
14 |  | SW Ranches | Lower Roof Deck
Total |  |  |  | 0 | 60 |  |  | 60
Bar listing & FFU drawings. (Non billable work)
1
2
3
3
4
5
6
7
Total |  |  |  | 0 | 0
Frist Week Weight+hours |  | Second week Weight + hours | Third week weight+hours | Fourth week Weight + hours |  |  | Total
0 |  | 0 | 0 | 0 |  |  | 0
Rebar @ Structural Steel
S.No | Engineers |  | Leaves | Permissions | Over Time | Remarks
1 | Eswar | Project management
2 | Nanaji | Rebar Detailing/QC
3 | Y Siva kumar | Estimations and rebar detailing
4 | Lokesh reddy | Rebar Detailing
5 | Sridevi | Rebar Detailing
6 | Vaishnavi | Rebar Detailing
7 | Pradeep | Rebar Detailing

## White Cap Work Schedule
PROJECT STATUS
| Customer | White Cap
| Last updated date | 2026-05-04
S.No | BILL STATUS | PROJECT NAME | SCOPE | COMPONENTS OF WORK | REC. DATE | STATUS | CLIENT SUB. DATE | CUST. REQ. DATE | EXP. WT/HRS | DET. WT. | EST. WT. | EST. HRS | HRS | C.O. | QC SUB. DATE2 | DETAILER STATUS | DETAILER | QC STATUS | CHECKER | REMARKS
1 |  | Felies Residence | CIP&CMU | Foundations and slab on grade | 2026-03-01 | Completed | 2026-12-01 |  |  | 2.8 | [6 empty] | Praveena |  | Chandra Mouli
|  | Felies Residence |  | Lift - 1 Verticals & beams, 2nd floor slab & beams | 2026-03-01 | Completed | 01-29-2026 |  |  | 6.354 | [6 empty] | Praveena |  | Anji Reddy
|  | Felies Residence |  | Lift - 2 verticals & beams, Roof slab & beams | 2026-03-01 | Completed | 2026-06-02 |  |  | 3.835 | [6 empty] | Praveena |  | Anji Reddy
2 |  | Valencia Del Mar Pickleball | CIP&CMU | Foundations and slab on grade | 2026-06-01 | Completed | 01-19-2026 |  |  | 6.057 | [6 empty] | Danush |  | Kameshwari
|  | Valencia Del Mar Pickleball |  | Lift - 1 Verticals & beams | 2026-06-01 | Completed | 01-23-2026 |  |  | 8.112 | [6 empty] | Danush |  | Kameshwari
|  | Valencia Del Mar Pickleball |  | Lift - 2 Verticals & beams | 2026-06-01 | Completed | 01-23-2026 |  |  | 4.434 | [6 empty] | Danush |  | Kameshwari
|  | Valencia Del Mar Pickleball |  | Double Dumpster Enclosure | 2026-10-02 | Completed | 02-18-2026 |  |  | 0.251 | [6 empty] | Praveena |  | Kameshwari
|  | Valencia Del Mar Pickleball |  | Single Dumpster Enclosure | 2026-10-02 | Completed | 02-18-2026 |  |  | 0.197 | [6 empty] | Praveena |  | Kameshwari
|  | Valencia Del Mar Pickleball |  | Mail Pavilion | 2026-10-02 | Completed | 02-18-2026 |  |  | 1.661 | [6 empty] | Praveena |  | Kameshwari
|  | Valencia Del Mar Pickleball |  | Monument sign | 05-30-2026 | Completed | 2026-01-06 |  |  | 0.131 |  |  |  |  | 05-30-2026 | Completed | Pradeep | Completed | Nanaji
3 |  | City of temple terrace-fire station #01 | CIP&CMU | Foundations | 2026-06-01 | Completed | 01-19-2026 |  |  | 13.923 | [6 empty] | Swathi |  | Chandra Mouli
|  | City of temple terrace-fire station #02 |  | Slab on grade | 2026-06-01 | Completed | 02-14-2026 |  |  | 0.516 | [6 empty] | Sri Lalitha |  | Kameshwari
|  | City of temple terrace-fire station #03 |  | Lift - 1 Verticals, 2nd floor slab & beams | 2026-06-01 | Completed | 02-25-2026 |  |  | 9.701 | [6 empty] | Sri Lalitha |  | Kameshwari
|  | City of temple terrace-fire station #04 |  | Lift - 2 Verticals and Roof beams | 2026-06-01 | Completed | 02-25-2026 |  |  | 9.489 | [6 empty] | Sri Lalitha |  | Kameshwari
4 |  | 228 Rutland | CIP&CMU | Foundations and slab on grade | 2026-06-01 | Completed | 01-13-2026 |  |  | 2.598 | [6 empty] | Allu Sai |  | Kameshwari
|  | 229 Rutland |  | Lift - 1 Verticals and Bond beams | 2026-06-01 | Completed | 2026-03-02 |  |  | 2.152 | [6 empty] | Allu Sai |  | Kameshwari
|  | 230 Rutland |  | Low Roof beams & Slab | 2026-06-01 | Completed | 02-19-2026 |  |  | 2.587 | [6 empty] | Vaishnavi |  | Kameshwari
|  | 231 Rutland |  | Lift - 2 Verticals, Bond beams & Roof beams | 2026-06-01 | Completed | 2026-02-03 |  |  | 1.643 | [6 empty] | Siva Kumar |  | Kameshwari
5 |  | Palmetto Lakes Industrial Park | CIP&CMU | Foundations and slab on grade | 2026-08-01 | Completed | 01-14-26 |  |  | 5.041 | [6 empty] | Sri Lalitha |  | Chandra Mouli
|  | Palmetto Lakes Industrial Park |  | Lift - 1 walls, Columns & Beams | 2026-08-01 | Completed | 01-27-26 |  |  | 6.914 | [6 empty] | Sri Lalitha |  | Chandra Mouli
|  | Palmetto Lakes Industrial Park |  | Lift - 2 walls, Columns & Beams | 2026-08-01 | Completed | 01-27-26 |  |  | 6.722 | [6 empty] | Sri Lalitha |  | Chandra Mouli
6 |  | Frenchman's Creek Operations Center | CIP&CMU | Building - A Foundations & slab on grade | 01-13-2026 | Completed | 01-26-2026 |  |  | 16.64 | [6 empty] | Pradeep |  | Anji Reddy
|  | Frenchman's Creek Operations Center |  | Building - B Foundations & slab on grade | 01-13-2026 | Completed | 01-21-2026 |  |  | 5.301 | [6 empty] | Pradeep |  | Narayana
|  | Frenchman's Creek Operations Center |  | Building - C Foundations & slab on grade | 01-13-2026 | Completed | 01-21-2026 |  |  | 17.953 | [6 empty] | Praveena |  | Anji Reddy
|  | Frenchman's Creek Operations Center |  | Building - D Foundations & slab on grade | 01-13-2026 | Completed | 01-26-2026 |  |  | 0.675 | [6 empty] | Pradeep |  | Anji Reddy
|  | Frenchman's Creek Operations Center |  | Building - E Foundations & slab on grade | 01-13-2026 | Completed | 01-28-2026 |  |  | 7.23 | [6 empty] | Pradeep |  | Anji Reddy
|  | Frenchman's Creek Operations Center |  | Building - F Foundations & slab on grade | 01-13-2026 | Completed | 01-31-2026 |  |  | 7.875 | [6 empty] | Pradeep |  | Anji Reddy
7 |  | Miami Shores Residence (R+R bluenest) | CIP&CMU | Foundations | 01-19-2026 | Completed | 01-27-2026 |  |  | 9.474 | [6 empty] | Swathi |  | Chandra Mouli
|  | Miami Shores Residence (R+R bluenest) |  | Slab on grade | 01-19-2026 | Completed | 2026-03-03 |  |  | 1.208 | [6 empty] | Praveena |  | Chandra Mouli
|  | Miami Shores Residence (R+R bluenest) |  | Lift - 1 Verticals, 2nd floor slab & beams | 01-19-2026 | Completed | 2026-09-03 |  |  | 15.747 | [6 empty] | Jagadeesh |  | Chandra Mouli
|  | Miami Shores Residence (R+R bluenest) |  | Lift - 2 Verticals and Roof beams | 01-19-2026 | Completed | 03-20-2026 |  |  | 2.904 | [6 empty] | Praveena |  | Kameshwari
|  | Miami Shores Residence (R+R bluenest) |  | Updated drawings received (Cantilever Beams) | 2026-06-24 | Completed | 2026-06-26 |  |  | 0.619 | [6 empty] | Praveena |  | eswar
8 |  | Licata Residence 2726 Appaloosa trail | CIP&CMU | Foundations & slab on grade | 01-20-2026 | Completed | 01-23-2026 |  |  | 0.764 | [6 empty] | Swathi |  | Anji Reddy
|  | Licata Residence 2726 Appaloosa trail |  | Lift - 1 Verticals and Roof beams | 01-20-2026 | Completed | 01-23-2026 |  |  | 1.818 | [6 empty] | Swathi |  | Anji Reddy
9 |  | 4669 S. Flagler Dr | CIP&CMU | Footings & Stem Walls | 01-24-2026 | Completed | 2026-04-02 |  |  | 5.907 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  | 4670 S. Flagler Dr |  | Stem wall & Slab on grade | 01-24-2026 | Completed | 02-20-2026 |  |  | 1.335 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  | 4671 S. Flagler Dr |  | Lift - 1 Verticals, 2nd floor slab & beams | 01-24-2026 | Completed | 2026-04-03 |  |  | 27.935 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  | 4672 S. Flagler Dr |  | Lift - 2 Verticals & Roof beams | 01-24-2026 | Completed | 2026-06-03 |  |  | 2.141 | [6 empty] | Vaishnavi |  | Chandra Mouli
10 |  | Harrison Residence | CIP&CMU | Foundations and slab on grade | 01-27-2026 | Completed | 2026-05-02 |  |  | 0.256 | [6 empty] | Sri Lalitha |  | Chandra Mouli
|  | Harrison Residence |  | Lift - 1 Verticals and Beams | 01-27-2026 | Completed | 2026-02-03 |  |  | 0.834 | [6 empty] | Sri Lalitha |  | Chandra Mouli
11 |  | PBIA - Revenue Control Building | CIP&CMU | Foundations and slab on grade | 2026-04-02 | Completed | 02-14-2026 |  |  | 11.285 | [6 empty] | Praveena |  | Anji Reddy
|  | PBIA - Revenue Control Building |  | Lift - 1 Verticals and Roof beams | 2026-04-02 | Completed | 02-19-2026 |  |  | 6.364 | [6 empty] | Praveena |  | Anji Reddy
12 |  | 127 EL Bravo Way | CIP&CMU | Basement Foundations | 2026-04-02 | Completed | 02-17-2026 |  |  | 13.887 | [6 empty] | Danush |  | Anji Reddy
|  | 128 EL Bravo Way |  | Basement Walls | 2026-04-02 | Completed | 02-21-2026 |  |  | 5.577 | [6 empty] | Danush |  | Anji Reddy
|  | 129 EL Bravo Way |  | Level - 1 Foundations | 2026-04-02 | Completed | 2026-12-03 |  |  | 22.202 | [6 empty] | Danush |  | Chandra Mouli
|  | 130 EL Bravo Way |  | Lift - 1 Verticals | 2026-04-02 | Completed | 03-16-2026 |  |  | 4.159 | [6 empty] | Danush |  | Chandra Mouli
|  | 131 EL Bravo Way |  | Lift - 1 Beams | 2026-04-02 | Completed | 03-28-2026 |  |  | 10.828 | [6 empty] | Danush |  | Chandra Mouli
|  | 132 EL Bravo Way |  | Lift - 2 Verticals | 2026-04-02 | Completed | 03-31-2026 |  |  | 1.709 | [6 empty] | Danush |  | Chandra Mouli
|  | 133 EL Bravo Way |  | Roof beams | 2026-04-02 | Completed | 03-31-2026 |  |  | 1.544 | [6 empty] | Danush |  | Chandra Mouli
13 |  | Blue Water Cove 6 | CIP&CMU | Foundations & slab on grade | 2026-10-02 | Completed | 02-25-2026 |  |  | 12.306 | [6 empty] | Allu Sai/Nanaji
|  | Blue Water Cove 7 |  | Lift-1 & 2 Verticals, 2nd floor slab, & Roof beams | 2026-10-02 | Completed | 03-18-2026 |  |  | 6.168 | [6 empty] | Allu Sai |  | Chandra Mouli
14 |  | 1050 N Lake way | CIP&CMU | Foundations and slab on grade | 2026-05-02 | Completed | 02-17-2026 |  |  | 3.991 | [6 empty] | Lokesh Reddy/Nanaji |  | Narayana
|  | 1051 N Lake way |  | Lift - 1 Verticals, 2nd floor slab & beams | 2026-05-02 | Completed | 02-23-2026 |  |  | 9.309 | [6 empty] | Lokesh Reddy |  | Kameshwari
|  | 1052 N Lake way |  | Lift - 2 Verticals & Roof beams | 2026-05-02 | Completed | 03-13-2026 |  |  | 2.787 | [6 empty] | Praveena |  | Kameshwari
15 |  | 143 Reef Road | CIP&CMU | Foundations and slab on grade | 2026-12-02 | Completed | 03-13-2026 |  |  | 16.785 | [5 empty] | Completed | Kunal |  | Chandra Mouli
|  | 144 Reef Road |  | Lift - 1 Verticals | 2026-12-02 | Completed | 05-15-2026 |  |  | 1.331 |  |  |  |  | 2026-12-05 | Completed | Kunal | COMPLETED | NANAJI | Qc not yet done
|  | 145 Reef Road |  | 2nd floor slab & Beams | 2026-12-02 | Completed | 05-15-2026 |  |  | 3.234 |  |  |  |  | 2026-12-05 | Completed | Kunal | COMPLETED | NANAJI | Qc not yet done
|  | 146 Reef Road |  | Lift-2 verticals & Roof beams | 2026-12-02 | Completed | 06-20-2026 | [7 empty] | 2026-12-05 | Completed | Kunal | NOT YET STARTED | NANAJI | Qc not yet done
16 |  | Cutler Bay SHS | CIP&CMU | Foundations and slab on grade | 02-16-2026 | Completed | 2026-04-03 |  |  | 2.305 | [6 empty] | Swathi | NOT YET STARTED | NANAJI
|  | Cutler Bay SHS |  | Lift - 1 Verticals and beams | 02-16-2026 | Completed | 2026-04-03 |  |  | 2.027 | [6 empty] | Swathi | NOT YET STARTED | NANAJI
|  | Cutler Bay SHS |  | Lift - 2 Verticals and Low Roof slab & beams | 02-16-2026 | Completed | 2026-04-03 |  |  | 1.242 | [6 empty] | Swathi | NOT YET STARTED | NANAJI
|  | Cutler Bay SHS |  | Lift - 3 Verticals and High Roof slab & beams | 02-16-2026 | Completed | 2026-04-03 |  |  | 0.786 | [6 empty] | Swathi | NOT YET STARTED | NANAJI
17 |  | Ackerman Residence | CIP&CMU | Foundations & slab on grade | 02-21-2026 | Completed | 2026-03-03 | [9 empty] | Lokesh Reddy |  | NANAJI
|  | Ackerman Residence |  | Lift - 1 Verticals, 2nd floor slab & beams | 02-21-2026 | Completed | 03-21-2026 |  |  | 4.853 | [6 empty] | Lokesh Reddy |  | Kameshwari
|  | Ackerman Residence |  | Lift - 2 Verticals & Roof beams | 02-21-2026 | Completed | 2026-02-04 |  |  | 1.285 | [6 empty] | Lokesh Reddy |  | Kameshwari
18 |  | Blue Water Cove 3 | CIP&CMU | Foundations & slab on grade | 02-24-2026 | Completed | 2026-06-03 |  |  | 2.592 | [6 empty] | Vaishnavi |  | Kameshwari
|  | Blue Water Cove 4 |  | Lift - 1 Verticals and Roof beams | 02-24-2026 | Completed | 03-16-2026 |  |  | 4.562 | [6 empty] | Vaishnavi |  | Kameshwari
19 |  | BOKOR 432 SUNSHINE BLVD | CIP&CMU | Foundations and slab on grade | 02-25-2026 | Completed | 2026-07-03 |  |  | 5.062 | [6 empty] | Eswar |  | Eswar
|  | BOKOR 432 SUNSHINE BLVD |  | Lift - 1 Verticals, 2nd floor slab & beams | 02-25-2026 | Completed | 03-13-2026 |  |  | 3.298 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  | BOKOR 432 SUNSHINE BLVD |  | Lift - 2 Verticals and Roof beams | 02-25-2026 | Completed | 03-13-2026 |  |  | 1.695 | [6 empty] | Vaishnavi |  | Chandra Mouli
20 |  | Cloyd | CIP&CMU | Foundations and slab on grade | 02-27-2026 | Completed | 03-11.-2026 |  |  | 2.267 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  | Cloyd |  | Lift - 1 Verticals and beams | 02-27-2026 | Completed | 03-20.-2026 |  |  | 1.214 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  |  |  | Lift - 2 Verticals and beams | 02-27-2026 | Completed | 03-20.-2026 |  |  | 0.835 | [6 empty] | Vaishnavi |  | Chandra Mouli
21 |  | 6017 Le Lac Road (Weiner Residence) | CIP&CMU | Foundations and slab on grade (East Garage) | 2026-09-03 | Completed | 03-21-2026 |  |  | 0.679 | [6 empty] | Sri lalitha |  | Kameshwari
|  | 6018 Le Lac Road (Weiner Residence) |  | Lift - 1 Verticals and Roof beams (East Garage) | 2026-09-03 | Completed | 03-26-2026 |  |  | 1.643 | [6 empty] | Praveena |  | Kameshwari
|  | 6019 Le Lac Road (Weiner Residence) |  | Foundations and slab on grade (Main Building) | 2026-09-03 | Completed | 03-25-2026 |  |  | 2.64 | [6 empty] | Praveena |  | Kameshwari
|  | 6020 Le Lac Road (Weiner Residence) |  | Lift - 1 Verticals, 2nd floor slab and beams (Main Building) | 2026-09-03 | Completed | 2026-01-05 |  |  | 5.594 | [6 empty] | Sridevi/Vaishnavi | NOT YET STARTED | NANAJI
|  | 6021 Le Lac Road (Weiner Residence) |  | Lift - 2 Verticals and roof beams (Main Building) | 2026-09-03 | Completed | 05-28-2026 |  |  | 4.782 |  |  |  |  | 05-28-2026 | COMPLETED | Vaishnavi | COMPLETED | Eswar
|  | 6022 Le Lac Road (Weiner Residence) |  | Foundations and slab on grade (2-story residence) | 2026-09-03 | Completed | 04-21-2026 |  |  | 4.162 | [6 empty] | Praveena |  | Chandra Mouli
|  | 6023 Le Lac Road (Weiner Residence) |  | Lift - 1 Verticals, 2nd floor slab and beams (2-story residence) | 2026-09-03 | Completed | 05-19-2026 |  |  | 12.373 |  | … |  |  | 05-18-2026 | COMPLETED | Vaishnavi | COMPLETED | NANAJI
|  | 6024 Le Lac Road (Weiner Residence) |  | Lift - 2 Verticals and roof beams (2-story residence) | 2026-09-03 | Completed | 2026-05-06 |  |  | 2.935 | [6 empty] | Vaishnavi |  | NANAJI
|  |  |  | Foundations and slab on grade (site work) | 2026-10-03 | Completed | 2026-04-04 |  |  | 1.37 | [6 empty] | Sri lalitha |  | Kameshwari
22 |  | Bluewater cove 11 | CIP&CMU | Foundations and slab on grade | 2026-10-03 | Completed | 03-24-2026 |  |  | 3.041 | [6 empty] | Vaishnavi | NOT YET STARTED | NANAJI
|  | Bluewater cove 12 |  | Lift - 1 Verticals and Roof beams | 2026-10-03 | Completed | 2026-01-05 |  |  | 4.261 | [6 empty] | Vaishnavi | NOT YET STARTED | NANAJI
23 |  | Bluewater cove 9 | CIP&CMU | Foundations and slab on grade | 2026-10-03 | Completed | 03-31-2026 |  |  | 15.362 | [6 empty] | Vaishnavi |  | Kameshwari
|  | Bluewater cove 10 |  | Lift - 1 Verticals and Roof Beams | 2026-10-03 | Completed | 2026-01-05 |  |  | 5.012 | [6 empty] | Nanaji/pradeep | NOT YET STARTED | Kameshwari
24 |  | 164 Seminole | CIP&CMU | Foundations | 2026-12-03 | Completed | 2026-08-04 |  |  | 2.269 | [6 empty] | Siva kumar |  | Chandra Mouli
|  | 165 Seminole |  | Slab on grade | 2026-12-03 | Completed | 05-18-2026 |  |  | 9.296 |  |  |  |  | 04-24-2026 | COMPLETED | Siva kumar | COMPLETED | NANAJI | Qc not yet done
25 |  | Roy & Shelley Silverman | CIP&CMU | Foundations and slab on grade | 03-14-2026 | Completed | 2026-10-04 |  |  | 3.789 | [6 empty] | Danush |  | Chandra Mouli
|  | Roy & Shelley Silverman |  | Lift - 1 Verticals | 03-14-2026 | Completed | 2026-04-05 |  |  | 3.191 | [6 empty] | Danush |  | Chandra Mouli
|  | Roy & Shelley Silverman |  | Lift - 1 slab & Beams | 03-14-2026 | Completed | 2026-04-05 |  |  | 5.85 | [6 empty] | Nanaji/Sridevi | NOT YET STARTED | NANAJI
|  | Roy & Shelley Silverman |  | Lift - 2 Verticals & Roof beams | 03-14-2026 | Completed | 2026-11-05 |  |  | 2.95 | [6 empty] | Vaishnavi/Shiva | COMPLETED | NANAJI
26 |  | 50 SE OLIVE | CIP&CMU | Foundations & columns | 03-18-2026 | Completed | 2026-08-04 |  |  | 0.674 | [6 empty] | Danush |  | Chandra Mouli
|  | 51 SE OLIVE |  | Bond beams | 03-18-2026 | Completed | 2026-08-04 |  |  | 0.174 | [6 empty] | Danush |  | Chandra Mouli
27 |  | Valencia Del Mar Clubhouse | CIP&CMU | Foundations and slab on grade | 03-20-2026 | Completed | 2026-06-04 |  |  | 22.524 | [6 empty] | Vaishnavi | COMPLETED | Chandra Mouli
|  | Valencia Del Mar Clubhouse |  | Lift - 1 Verticals and beams (pour-1) | 03-20-2026 | Completed | 2026-12-05 |  |  | 5.781 | [6 empty] | Vaishnavi/Sridevi | COMPLETED | NANAJI
|  | Valencia Del Mar Clubhouse |  | Lift - 1 Verticals and beams (pour-2) | 03-20-2026 | Completed | 05-16-2026 |  |  | 10.773 |  |  |  |  | 05-15-2026 | COMPLETED | Sridevi | COMPLETED | NANAJI
|  | Valencia Del Mar Clubhouse |  | Lift - 1 Verticals and beams (pour-3) & (pour-4) | 03-20-2026 | Completed | 05-27-2026 |  |  | 10.014 |  |  |  |  | 05-25-2026 | COMPLETED | Sridevi | COMPLETED | NANAJI
|  | Valencia Del Mar Clubhouse |  | Lift - 2 Verticals and beams (pour-1) | 03-20-2026 | Completed | 05-29-2026 |  |  | 4.784 |  |  |  |  | 05-15-2026 | COMPLETED | Sridevi | NOT YET STARTED | Kameshwari | Eswar/PDF CHECK ONLY & BAR LIST SEND
|  | Valencia Del Mar Clubhouse |  | Lift - 2 Verticals and beams (pour-2) | 03-20-2026 | Completed | 2026-03-06 |  |  | 3.643 | [6 empty] | Sridevi |  | Kameshwari
|  | Valencia Del Mar Clubhouse |  | Lift - 2 Verticals and beams (pour-3) | 03-20-2026 | Completed | 2026-12-06 |  |  | 14.818 |  |  |  |  | 2026-12-05 | COMPLETED | Sridevi | COMPLETED | NANAJI
|  | Valencia Del Mar Clubhouse |  | Monument walls | 04-23-2026 | Completed | 04-27-2026 |  |  | 0.576 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  | Valencia Del Mar Clubhouse |  | Tennis & Bocce Courts Restrooms | 2026-08-05 | Completed | 2026-09-05 |  |  | 0.123 | [6 empty] | Eswar |  | Kameshwari
28 |  | 910 S Ocean | CIP&CMU | Basement Foundations | 03-24-2026 | Completed | 2026-08-04 | [9 empty] | Sridevi | NOT YET STARTED | Narayana
|  | 911 S Ocean |  | Lift - 1 Verticals & roof beams | 03-24-2026 | Completed | 2026-10-04 | [9 empty] | Sridevi | NOT YET STARTED | Narayana
|  | 912 S Ocean |  | Retaining wall & Planter walls & stairs | 03-24-2026 | Completed | 04-21-2026 | [9 empty] | Sridevi | NOT YET STARTED | Narayana
29 |  | Burns Residence | CIP&CMU | Foundations and slab on grade | 03-27-2026 | Completed | 2026-06-04 |  |  | 7.45 | [6 empty] | Praveena |  | Chandra Mouli
|  | Burns Residence |  | Lift - 1 Verticals and Beams | 03-27-2026 | Completed | 05-21-2026 |  |  | 7.962 |  |  |  |  | 05-19-2026 | Completed | Siva kumar | Completed | NANAJI
|  | Burns Residence |  | Lift - 2 Verticals and beams | 03-27-2026 | Completed | 05-21-2026 |  |  | 0.175 |  |  |  |  | 05-20-2026 | Completed | Siva kumar | Completed | NANAJI
30 |  | 5940 North Bay Road (NEW SINGLE FAMILY RESIDENCE) | CIP&CMU | Foundations | 03-26-2026 | Completed | 2026-08-04 |  |  | 140.399 | [6 empty] | Balaram |  | Chandra Mouli
31 |  | 320 S atlantic Drive | CIP&CMU | Foundations | 2026-02-04 | Completed | 04-18-2026 |  |  | 6.817 | [6 empty] | Sridevi | COMPLETED | Chandra Mouli/NNJ
|  | 321 S atlantic Drive |  | Stem wall & Slab on grade | 2026-02-04 | Completed | 2026-01-05 |  |  | 4.869 |  |  |  |  | 05-21-2026 | Completed | Sridevi | COMPLETED | Chandra Mouli/NNJ
|  | 322 S atlantic Drive |  | Lift - 1 Verticals, 2nd Floor slab & beams | 2026-02-04 | Completed | 06-13-2026 | 2026-12-06 |  | 15.352 |  |  |  |  | 06-13-2026 | Completed | Vaishnavi | COMPLETED | Chandra Mouli
|  | 323 S atlantic Drive |  | Lift - 2 Verticals and Roof beams | 2026-02-04 | Completed | 06-18-2026 | 06-17-2026 | [6 empty] | 06-15-2026 | Completed | Vaishnavi | COMPLETED | NANAJI
32 |  | Custom Residence (515 lido drive) | CIP&CMU | Foundations and slab on grade | 2026-02-04 | Completed | 04-24-2026 |  |  | 22.418 | [6 empty] | Vaishnavi |  | Chandra Mouli
|  | Custom Residence (515 lido drive) |  | Lift - 1 Verticals | 2026-02-04 | Completed | 2026-04-06 |  |  | 4.206 |  |  |  |  | 05-25-2026 | Completed | Siva kumar | Completed | NANAJI
|  | Custom Residence (515 lido drive) |  | 2nd floor slab & beams | 2026-02-04 | Completed | 06-18-2026 |  |  | 11.165 |  |  |  |  | 06-17-2026 | Completed | Jagadeesh | Completed | NANAJI
|  | Custom Residence (515 lido drive) |  | Lift - 2 Verticals & Roof beams | 2026-02-04 | Completed | 06-18-2026 |  |  | 3.221 |  |  |  |  | 06-16-2026 | Completed | Balaram | Completed | NANAJI
33 |  | Jandrews Residence | CIP&CMU | Foundations and slab on grade | 2026-02-04 | Completed | 04-23-2026 |  |  | 16.272 | [6 empty] | Praveena |  | Chandra Mouli
|  | Jandrews Residence |  | Lift - 1 Verticals and beams | 2026-02-04 | Completed | 2026-05-16 |  |  | 10.859 | [6 empty] | Lokesh Reddy |  | Kameshwari
|  | Jandrews Residence |  | Lift - 2 Verticals and beams | 2026-02-04 | Completed | 2026-06-03 | [9 empty] | Lokesh Reddy |  | Kameshwari
34 |  | 6024 Lelac Rd | CIP&CMU | Foundations and slab on grade | 2026-03-04 | Completed | 2026-10-04 |  |  | 1.04 | [6 empty] | Vaishnavi | COMPLETED | Chandra Mouli
|  | 6025 Lelac Rd |  | Lift - 1 Verticals, loft floor slab & beams | 2026-03-04 | Completed | 2026-10-04 |  |  | 1.18 | [6 empty] | Vaishnavi | COMPLETED | Chandra Mouli
|  | 6026 Lelac Rd |  | Lift - 2 Verticals and roof beams | 2026-03-04 | Completed | 2026-10-04 |  |  | 1.26 | [6 empty] | Vaishnavi | COMPLETED | Chandra Mouli
|  | 6027 Lelac Rd |  | Foundations & slab on grade (Summer kitchen) | 2026-03-04 | Completed | 04-22-2026 |  |  | 1.02 | [6 empty] | Sridevi | COMPLETED | NANAJI
|  | 6028 Lelac Rd |  | Lift - 1 Verticals, slab and beams (Summer kitchen) | 2026-03-04 | Completed | 04-23-2026 |  |  | 1.69 | [6 empty] | Sridevi | NOT YET STARTED | Kameshwari
35 |  | 5900 Powerline Garag | CIP&CMU | Grade beams | 2026-07-04 | Completed | 04-20-2026 |  |  | 16.4 | [6 empty] | Sri lalitha | NOT YET STARTED | Kameshwari
|  | 5901 Powerline Garag |  | Slab on grade, Lift - 1 Verticals and Roof beams | 2026-07-04 | Completed | 2026-09-05 |  |  | 26.761 | [6 empty] | Pradeep | COMPLETED | NANAJI
36 |  | South Florida Jewish Cemetery | CIP&CMU | Foundations and slab on grade | 04-16-2026 | Completed | 2026-05-05 |  |  | 1.661 | [6 empty] | Vaishnavi | NOT YET STARTED | Eswar
|  | South Florida Jewish Cemetery |  | Lift - 1 Verticals and Roof Beams | 04-16-2026 | Completed | 05-22-2026 |  |  | 2.453 |  |  |  |  | 05-19-2026 | COMPLETED | Pradeep | COMPLETED | NANAJI
37 |  | 1820 S Federal Hwy - Fifth Third Bank | CIP&CMU | Foundations and slab on grade | 04-16-2026 | Completed | 04-24-2026 |  |  | 2.762 | [6 empty] | Pradeep | NOT YET STARTED | Narayana
|  | 1821 S Federal Hwy - Fifth Third Bank |  | Lift - 1 Verticals and Roof beams | 04-16-2026 | Completed | 04-24-2026 |  |  | 1.259 | [6 empty] | Pradeep | NOT YET STARTED | Narayana
38 |  | 20 Hudson Ave | CIP&CMU | Foundations & slab on grade | 04-18-2026 | Completed | 05/26/26 | [9 empty] | Eswar |  | Kameshwari
|  | 21 Hudson Ave |  | Lift - 1 Verticals and Beams | 04-18-2026 | Completed | 06-18-2026 | [9 empty] | Praveena |  | Kameshwari
|  | 22 Hudson Ave |  | Lift - 2 Verticals and Beams | 04-18-2026 | Completed | 06-18-2026 | [7 empty] | 06-16-2026 | COMPLETED | Swathi | NOT YET STARTED | Kameshwari
39 |  | South Rd Office Building E | CIP&CMU | Foundations and slab on grade | 04-22-2026 | Completed | 04-24-2026 |  |  | 1.577 | [6 empty] | Vaishnavi | COMPLETED | Nanaji
|  | South Rd Office Building E |  | Lift - 1 Verticals and beams | 04-22-2026 | Completed | 2026-01-05 |  |  | 4.107 | [6 empty] | Lokesh/vaishnavi | NOT YET STARTED | ESWAR
40 |  | Baig Residence | CIP | 3rd Floor tie beams | 04-28-2026 | Completed | 2026-05-06 |  |  | 0.978 | [6 empty] | Lokesh | NOT YET STARTED | Nanaji | High Priority
|  | Baig Residence |  | 2nd Floor slab | 04-28-2026 | Completed | 2026-05-07 | [9 empty] | Lokesh |  | ESWAR | High Priority
41 |  | SW Ranches | CIP | Lower Roof Deck | 04-30-2026 | Completed | 2026-05-15 |  |  | 29.74 | [6 empty] | Eswar |  | Nanaji | High Priority
|  | SW Ranches |  | Lift - 1 verticals | 04-30-2026 | Completed | 2026-06-01 |  |  | 2.45 |  |  |  |  | 05-30-2026 | COMPLETED | Pradeep | COMPLETED | ESWAR
42 |  | 2651 Southcast 10th court | CIP | Pool deck slab and beams | 2026-06-05 | Completed | 2026-09-05 | [9 empty] | Pradeep |  | Kameshwari
43 |  | Country inn Pet Resort | CIP&CMU | Foundations and slab on grade | 2026-08-05 | Completed | 05-22-2026 |  |  | 3.691 |  |  |  |  | 05-22-2026 | COMPLETED | Vaishnavi | COMPLETED | Nanaji | Asap Job
|  |  |  | Lift - 1 verticals and beams | 2026-08-05 | Completed | 2026-05-06 | [7 empty] | 2026-06-02 | COMPLETED | Vaishnavi | NOT YET STARTED | ESWAR
44 |  | 2960 Greenbriair | CIP&CMU | Foundations | 05-13-2026 | Completed | 2026-05-06 |  |  | 20.784 |  |  |  |  | 06-15-2026 | COMPLETED | Lokesh | NOT YET STARTED | Kameshwari
|  | 2961 Greenbriair |  | Slab on grade | 05-13-2026 | Completed | 06-19-2026 | [8 empty] | COMPLETED | Sri Lalitha | COMPLETED | Nanaji
|  | 2962 Greenbriair |  | Lift - 1 verticals and beams | 05-13-2026 | Inprogress | 06-20-2026 | [7 empty] | 2026-06-29 | Completed | Sridevi |  | ESWAR
|  | 2963 Greenbriair |  | Lift - 2 verticals and beams | 05-13-2026 | Inprogress | 06-23-2026 | [9 empty] | Sri Lalitha |  | ESWAR
45 |  | Gallery at Somi Parc Phase 1 | CIP&CMU | Foundations (Residential) part - 1 | 05-14-2026 | Completed | 06-17-2026 | [9 empty] | Eswar/Nanaji |  | Kameshwari
|  | Gallery at Somi Parc Phase 2 |  | Foundations (Residential) part - 2 | 05-14-2026 | Completed | 06-18-2026 | [9 empty] | Sri Lalitha |  | Nanaji
|  | Gallery at Somi Parc Phase 3 |  | Slab on grade (Residential) part - 1 & 2 | 05-14-2026 | Inprogress | 06-26-2026 | [9 empty] | Sridevi |  | ESWAR
|  | Gallery at Somi Parc Phase 4 |  | Columns (Residential) lift - 1 verticals | 05-14-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Lokesh |  | Kameshwari
|  | Gallery at Somi Parc Phase 5 |  | Shear walls (Residential) lift - 1 verticals | 05-14-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Pradeep |  | Nanaji
|  | Gallery at Somi Parc Phase 6 |  | Cmu walls lift - 1 verticals | 05-14-2026 | Not Yet Started | 2026-03-08 | [9 empty] | Praveena |  | ESWAR
|  | Gallery at Somi Parc Phase 7 |  | 2nd Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-03-09 | [9 empty] | Swathi |  | Kameshwari
|  | Gallery at Somi Parc Phase 8 |  | Columns (Residential) lift - 2 verticals | 05-14-2026 | Not Yet Started | 2026-03-10 | [9 empty] | Balaram |  | Nanaji
|  | Gallery at Somi Parc Phase 9 |  | Shear walls (Residential) lift - 2 verticals | 05-14-2026 | Not Yet Started | 2026-03-11 | [9 empty] | Jagadeesh |  | ESWAR
|  | Gallery at Somi Parc Phase 10 |  | Cmu walls lift - 2 verticals | 05-14-2026 | Not Yet Started | 2026-03-12 | [9 empty] | Danush |  | Kameshwari
|  | Gallery at Somi Parc Phase 11 |  | 3rd Floor slab (Residential) | 05-14-2026 | Not Yet Started | 2026-03-13 | [9 empty] | Kunal |  | Nanaji
|  | Gallery at Somi Parc Phase 12 |  | Columns (Residential) lift - 3 verticals | 05-14-2027 | Not Yet Started | 2026-03-14 | [9 empty] | Sai |  | ESWAR
|  | Gallery at Somi Parc Phase 13 |  | Shear walls (Residential) lift - 3 verticals | 05-14-2028 | Not Yet Started | 2026-03-15 | [9 empty] | Sri Lalitha |  | Kameshwari
|  | Gallery at Somi Parc Phase 14 |  | Cmu walls lift - 3 verticals | 05-14-2029 | Not Yet Started | 2026-03-16 | [9 empty] | Sridevi |  | Nanaji
|  | Gallery at Somi Parc Phase 15 |  | 3rd Floor slab (Residential) | 05-14-2030 | Not Yet Started | 2026-03-17 | [9 empty] | Lokesh |  | ESWAR
|  | Gallery at Somi Parc Phase 16 |  | Columns (Residential) lift - 4 verticals | 05-14-2031 | Not Yet Started | 2026-03-18 | [9 empty] | Pradeep |  | Kameshwari
|  | Gallery at Somi Parc Phase 17 |  | Shear walls (Residential) lift - 4 verticals | 05-14-2032 | Not Yet Started | 2026-03-19 | [9 empty] | Praveena |  | Nanaji
|  | Gallery at Somi Parc Phase 18 |  | Cmu walls lift - 4 verticals | 05-14-2033 | Not Yet Started | 2026-03-20 | [9 empty] | Swathi |  | ESWAR
|  | Gallery at Somi Parc Phase 19 |  | 4th Floor slab (Residential) | 05-14-2034 | Not Yet Started | 2026-03-21 | [9 empty] | Balaram |  | Kameshwari
|  | Gallery at Somi Parc Phase 20 |  | Columns (Residential) lift - 5 verticals | 05-14-2035 | Not Yet Started | 2026-03-22 | [9 empty] | Jagadeesh |  | Nanaji
|  | Gallery at Somi Parc Phase 21 |  | Shear walls (Residential) lift - 5 verticals | 05-14-2036 | Not Yet Started | 2026-03-23 | [9 empty] | Danush |  | ESWAR
|  | Gallery at Somi Parc Phase 22 |  | Cmu walls lift - 5 verticals | 05-14-2037 | Not Yet Started | 2026-03-24 | [9 empty] | Kunal |  | Kameshwari
|  | Gallery at Somi Parc Phase 23 |  | 5th Floor slab (Residential) | 05-14-2038 | Not Yet Started | 2026-03-25 | [9 empty] | Sai |  | Nanaji
|  | Gallery at Somi Parc Phase 24 |  | Columns (Residential) lift - 6 verticals | 05-14-2039 | Not Yet Started | 2026-03-26 | [9 empty] | Sri Lalitha |  | Kameshwari
|  | Gallery at Somi Parc Phase 25 |  | Shear walls (Residential) lift - 6 verticals | 05-14-2040 | Not Yet Started | 2026-03-27 | [9 empty] | Sridevi |  | Nanaji
|  | Gallery at Somi Parc Phase 26 |  | Cmu walls lift - 6 verticals | 05-14-2041 | Not Yet Started | 2026-03-28 | [9 empty] | Sri Lalitha |  | ESWAR
|  | Gallery at Somi Parc Phase 27 |  | 6th Floor slab (Residential) | 05-14-2042 | Not Yet Started | 2026-03-29 | [9 empty] | Sridevi |  | Kameshwari
|  | Gallery at Somi Parc Phase 28 |  | Columns (Residential) lift - 7 verticals | 05-14-2043 | Not Yet Started | 2026-03-30 | [9 empty] | Lokesh |  | Nanaji
|  | Gallery at Somi Parc Phase 29 |  | Shear walls (Residential) lift - 7 verticals | 05-14-2044 | Not Yet Started | 2026-03-31 | [9 empty] | Pradeep |  | ESWAR
|  | Gallery at Somi Parc Phase 30 |  | Cmu walls lift - 7 verticals | 05-14-2045 | Not Yet Started | 2026-04-01 | [9 empty] | Praveena |  | Kameshwari
|  | Gallery at Somi Parc Phase 31 |  | 7th Floor slab (Residential) | 05-14-2046 | Not Yet Started | 2026-04-02 | [9 empty] | Swathi |  | Nanaji
|  | Gallery at Somi Parc Phase 32 |  | Columns (Residential) lift - 8 verticals | 05-14-2047 | Not Yet Started | 2026-04-03 | [9 empty] | Balaram |  | ESWAR
|  | Gallery at Somi Parc Phase 33 |  | Shear walls (Residential) lift - 8 verticals | 05-14-2048 | Not Yet Started | 2026-04-04 | [9 empty] | Jagadeesh |  | Kameshwari
|  | Gallery at Somi Parc Phase 34 |  | Cmu walls lift - 8 verticals | 05-14-2049 | Not Yet Started | 2026-04-05 | [9 empty] | Danush |  | Nanaji
|  | Gallery at Somi Parc Phase 35 |  | 8th Floor slab (Residential) | 05-14-2050 | Not Yet Started | 2026-04-06 | [9 empty] | Kunal |  | ESWAR
|  | Gallery at Somi Parc Phase 36 |  | Columns (Residential) lift - 9 verticals | 05-14-2051 | Not Yet Started | 2026-04-07 | [9 empty] | Sai |  | Kameshwari
|  | Gallery at Somi Parc Phase 37 |  | Shear walls (Residential) lift - 9 verticals | 05-14-2052 | Not Yet Started | 2026-04-08 | [9 empty] | Sri Lalitha |  | Nanaji
|  | Gallery at Somi Parc Phase 38 |  | Cmu walls lift - 9 verticals | 05-14-2053 | Not Yet Started | 2026-04-09 | [9 empty] | Sridevi |  | Kameshwari
|  | Gallery at Somi Parc Phase 39 |  | 9th Floor slab (Residential) | 05-14-2054 | Not Yet Started | 2026-04-10 | [9 empty] | Lokesh |  | Nanaji
|  | Gallery at Somi Parc Phase 40 |  | Columns (Residential) lift - 10 verticals | 05-14-2055 | Not Yet Started | 2026-04-11 | [9 empty] | Pradeep |  | ESWAR
|  | Gallery at Somi Parc Phase 41 |  | Shear walls (Residential) lift - 10 verticals | 05-14-2056 | Not Yet Started | 2026-04-12 | [9 empty] | Sri Lalitha |  | Kameshwari
|  | Gallery at Somi Parc Phase 42 |  | Cmu walls lift - 10 verticals | 05-14-2057 | Not Yet Started | 2026-04-13 | [9 empty] | Sridevi |  | Nanaji
|  | Gallery at Somi Parc Phase 43 |  | 10th Floor slab (Residential) | 05-14-2058 | Not Yet Started | 2026-04-14 | [9 empty] | Lokesh |  | ESWAR
|  | Gallery at Somi Parc Phase 44 |  | Columns (Residential) lift - 11 verticals | 05-14-2059 | Not Yet Started | 2026-04-15 | [9 empty] | Pradeep |  | Kameshwari
|  | Gallery at Somi Parc Phase 45 |  | Shear walls (Residential) lift - 11 verticals | 05-14-2060 | Not Yet Started | 2026-04-16 | [9 empty] | Praveena |  | Nanaji
|  | Gallery at Somi Parc Phase 46 |  | Cmu walls lift - 11 verticals | 05-14-2061 | Not Yet Started | 2026-04-17 | [9 empty] | Swathi |  | ESWAR
|  | Gallery at Somi Parc Phase 47 |  | 11th Floor slab (Residential) | 05-14-2062 | Not Yet Started | 2026-04-18 | [9 empty] | Balaram |  | Kameshwari
|  | Gallery at Somi Parc Phase 48 |  | Columns (Residential) lift - 12 verticals | 05-14-2063 | Not Yet Started | 2026-04-19 | [9 empty] | Jagadeesh |  | Nanaji
|  | Gallery at Somi Parc Phase 49 |  | Shear walls (Residential) lift - 12 verticals | 05-14-2064 | Not Yet Started | 2026-04-20 | [9 empty] | Danush |  | Kameshwari
|  | Gallery at Somi Parc Phase 50 |  | Cmu walls lift - 12 verticals | 05-14-2065 | Not Yet Started | 2026-04-21 | [9 empty] | Kunal |  | Nanaji
|  | Gallery at Somi Parc Phase 51 |  | 12th Floor slab (Residential) | 05-14-2066 | Not Yet Started | 2026-04-22 | [9 empty] | Sai |  | ESWAR
|  | Gallery at Somi Parc Phase 52 |  | Columns (Residential) lift - 13 verticals | 05-14-2067 | Not Yet Started | 2026-04-23 | [9 empty] | Sri Lalitha |  | Kameshwari
|  | Gallery at Somi Parc Phase 53 |  | Shear walls (Residential) lift - 13 verticals | 05-14-2068 | Not Yet Started | 2026-04-24 | [9 empty] | Sridevi |  | Nanaji
|  | Gallery at Somi Parc Phase 54 |  | Cmu walls lift - 13 verticals | 05-14-2069 | Not Yet Started | 2026-04-25 | [9 empty] | Lokesh |  | ESWAR
|  | Gallery at Somi Parc Phase 55 |  | 13th Floor slab (Residential) | 05-14-2070 | Not Yet Started | 2026-04-26 | [9 empty] | Pradeep |  | Kameshwari
|  | Gallery at Somi Parc Phase 56 |  | Columns (Residential) lift - 14 verticals | 05-14-2071 | Not Yet Started | 2026-04-27 | [9 empty] | Praveena |  | Nanaji
|  | Gallery at Somi Parc Phase 57 |  | Shear walls (Residential) lift - 14 verticals | 05-14-2072 | Not Yet Started | 2026-04-28 | [9 empty] | Swathi |  | ESWAR
|  | Gallery at Somi Parc Phase 58 |  | Cmu walls lift - 14 verticals | 05-14-2073 | Not Yet Started | 2026-04-29 | [9 empty] | Balaram |  | Kameshwari
|  | Gallery at Somi Parc Phase 59 |  | 14th Floor slab (Residential) | 05-14-2074 | Not Yet Started | 2026-04-30 | [9 empty] | Jagadeesh |  | Nanaji
|  | Gallery at Somi Parc Phase 60 |  | Columns (Residential) lift - 15 verticals | 05-14-2075 | Not Yet Started | 2026-05-01 | [9 empty] | Danush |  | ESWAR
|  | Gallery at Somi Parc Phase 61 |  | Shear walls (Residential) lift - 15 verticals | 05-14-2076 | Not Yet Started | 2026-05-02 | [9 empty] | Kunal |  | Kameshwari
|  | Gallery at Somi Parc Phase 62 |  | Cmu walls lift - 15 verticals | 05-14-2077 | Not Yet Started | 2026-05-03 | [9 empty] | Sai |  | Kameshwari
|  | Gallery at Somi Parc Phase 63 |  | 15th floor slab (Residential) | 05-14-2078 | Not Yet Started | 2026-05-04 | [9 empty] | Sri Lalitha |  | Nanaji
|  | Gallery at Somi Parc Phase 64 |  | Columns (Residential) lift - 16 verticals | 05-14-2079 | Not Yet Started | 2026-05-05 | [9 empty] | Sri Lalitha |  | ESWAR
|  | Gallery at Somi Parc Phase 65 |  | Shear walls (Residential) lift - 16 verticals | 05-14-2080 | Not Yet Started | 2026-05-06 | [9 empty] | Sridevi |  | Kameshwari
|  | Gallery at Somi Parc Phase 66 |  | Cmu walls lift - 16 verticals | 05-14-2081 | Not Yet Started | 2026-05-07 | [9 empty] | Lokesh |  | Nanaji
|  | Gallery at Somi Parc Phase 67 |  | Roof Floor slab (Residential) | 05-14-2082 | Not Yet Started | 2026-05-08 | [9 empty] | Pradeep |  | ESWAR
|  | Gallery at Somi Parc Phase 68 |  | Parapet walls (Residential) verticals | 05-14-2083 | Not Yet Started | 2026-05-09 | [9 empty] | Praveena |  | Kameshwari
|  | Gallery at Somi Parc Phase 69 |  |  | 05-14-2084 | Not Yet Started | 2026-05-10 | [9 empty] | Swathi |  | Nanaji
|  | Gallery at Somi Parc Phase 70 |  | Foundations (Garage) | 05-14-2026 | Not Yet Started | 2026-05-11 | [9 empty] | Balaram |  | ESWAR
|  | Gallery at Somi Parc Phase 71 |  | Slab on grade (Garage) | 05-14-2026 | Not Yet Started | 2026-05-12 | [9 empty] | Jagadeesh |  | Kameshwari
|  | Gallery at Somi Parc Phase 72 |  | Columns (Garage) | 05-14-2026 | Not Yet Started | 2026-05-13 | [9 empty] | Danush |  | Nanaji
|  | Gallery at Somi Parc Phase 73 |  | Shear walls (Garage) | 05-14-2026 | Not Yet Started | 2026-05-14 | [9 empty] | Kunal |  | ESWAR
|  | Gallery at Somi Parc Phase 74 |  | 2nd Floor slab (Garage) | 05-14-2026 | Not Yet Started | 2026-05-15 | [9 empty] | Sai |  | Kameshwari
|  | Gallery at Somi Parc Phase 75 |  | 3rd Floor slab (Garage) | 05-14-2026 | Not Yet Started | 2026-05-16 | [9 empty] | Sri Lalitha |  | Nanaji
|  | Gallery at Somi Parc Phase 76 |  | 4th Floor slab (Garage) | 05-14-2026 | Not Yet Started | 2026-05-17 | [9 empty] | Sridevi |  | ESWAR
|  | Gallery at Somi Parc Phase 77 |  | 5th Floor slab (Garage) | 05-14-2026 | Not Yet Started | 2026-05-18 | [9 empty] | Lokesh |  | Kameshwari
|  | Gallery at Somi Parc Phase 78 |  | 6th Floor slab (Garage) | 05-14-2026 | Not Yet Started | 2026-05-19 | [9 empty] | Pradeep |  | Nanaji
46 |  | 6007 Le Lac (Furing residence) | CIP | Foundations & Walls (scope added) | 05-14-2026 | Completed | 05-16-2026 |  |  | 1.513 |  |  |  |  | 05-16-2026 | COMPLETED | Pradeep | COMPLETED | Kameshwari
|  | 6008 Le Lac (Furing residence) |  | Cabana slab on grade | 06-16-2026 | Completed | 06-25-2026 | [9 empty] | siva kumar |  | Nanaji
47 |  | 90 Stingaree | CIP & CMU | Slab on grade | 05-15-2026 | Completed | 2026-05-06 | [9 empty] | siva kumar |  | Kameshwari
|  | 91 Stingaree |  | Lift - 1 verticals and beams | 05-15-2026 | Inprogress | 06-26-2026 | [7 empty] | 2026-06-29 | COMPLETED | Praveena |  | Nanaji
48 |  | O.B. (Scattered Lots) | CIP & CMU | Foundaitons & sog. | 05-15-2026 | Completed | 05-18-2026 |  |  | 0.725 |  |  |  |  | 05-18-2026 | COMPLETED | Lokesh Reddy | COMPLETED | Kameshwari | PDF CHECK ONLY
|  | O.B. (Scattered Lots) |  | Lift - 1 verticals and beams | 05-15-2027 | Completed | 05-23-2026 | [9 empty] | siva kumar |  | Nanaji
49 |  | 840 Denery Ln. Residence |  | Foundaitons & Slab on grade | 05-16-2026 | Completed | 05-30-2026 |  |  | 9.9 |  |  |  |  | 05-30-2026 | COMPLETED | eswar/siav kumar | NOT YET STARTED | ESWAR | PDF CHECK ONLY
|  | 841 Denery Ln. Residence |  | Lift - 1 verticals and bond beams | 05-16-2027 | Completed | 05-30-2026 |  |  | 4.453 |  |  |  |  | 05-30-2026 | COMPLETED | siav kumar | NOT YET STARTED | ESWAR | PDF CHECK ONLY
|  | 842 Denery Ln. Residence |  | 2nd floor slab & beams | 05-16-2028 | Inprogress | 2026-03-07 | [9 empty] | Sridevi |  | Kameshwari
|  | 843 Denery Ln. Residence |  | Lift - 2 verticals and bond beams | 05-16-2029 | Not Yet Started | 2026-03-07 | [9 empty] | Praveena |  | Nanaji
|  | 844 Denery Ln. Residence |  | Roof beams | 05-16-2030 | Not Yet Started | 2026-03-07 | [9 empty] | Praveena/Sridevi |  | Kameshwari
50 |  | Nuvo | CIP & CMU | Bldg. Type 1 (A, C, D & G) |  | Not Yet Started | [10 empty] | siva kumar |  | ESWAR
|  | Nuvo |  | Foundations and slab on grade | 05-22-2026 | Completed | 2026-12-06 | [9 empty] | siva kumar |  | Kameshwari
|  | Nuvo |  | Lift - 1 verticals and beams | 05-22-2026 | Completed | 06-13-2026 | 2026-12-06 | [6 empty] | 06-16-2026 | COMPLETED | Sridevi | NOT YET STARTED | Nanaji
|  | Nuvo |  | 2nd Flr. Thru 2nd lift & 2nd floor beams | 05-22-2026 | Not Yet Started | 06-19-2026 | [9 empty] | siva kumar |  | ESWAR
|  | Nuvo |  | 3rd Flr. Thru 3rd lift & 3rd floor beams | 05-22-2026 | Not Yet Started | 06-26-2026 | [9 empty] | siva kumar |  | Kameshwari
|  | Nuvo |  | 4th Flr. Thru Roof & Abv Roof beams | 05-22-2026 | Not Yet Started | 2026-03-07 | [9 empty] | siva kumar |  | Nanaji
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | [10 empty] | siva kumar |  | ESWAR
|  | Nuvo |  | Bldg. Type 2 (E & H) | 05-22-2026 | Not Yet Started | [10 empty] | siva kumar |  | Kameshwari
|  | Nuvo |  | Foundations and slab on grade | 05-22-2026 | Completed | 06-15-2026 | [9 empty] | Lokesh Reddy |  | Nanaji
|  | Nuvo |  | Lift - 1 verticals and beams | 05-22-2026 | Completed | 06-15-2026 | [9 empty] | siva kumar |  | ESWAR
|  | Nuvo |  | 2nd Flr. Thru 2nd lift & 2nd floor beams | 05-22-2026 | Not Yet Started | 06-19-2026 | [9 empty] | Lokesh Reddy |  | Kameshwari
|  | Nuvo |  | 3rd Flr. Thru 3rd lift & 3rd floor beams | 05-22-2026 | Not Yet Started | 06-26-2026 | [9 empty] | Lokesh Reddy |  | Nanaji
|  | Nuvo |  | 4th Flr. Thru Roof & Abv Roof beams | 05-22-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Lokesh Reddy |  | ESWAR
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | [10 empty] | Lokesh Reddy |  | Kameshwari
|  | Nuvo |  | Bldg. Type 3 (B & F) | 05-22-2026 | Not Yet Started | [10 empty] | Lokesh Reddy |  | ESWAR
|  | Nuvo |  | Elevator Pits & Stairs, Bg Thru 1st lift | 05-22-2026 | Inprogress | 06-16-2026 | [9 empty] | Lokesh Reddy |  | Kameshwari
|  | Nuvo |  | 2nd Flr. Thru 2nd lift & 2nd floor beams | 05-22-2026 | Not Yet Started | 06-19-2026 | [9 empty] | siva kumar |  | Nanaji
|  | Nuvo |  | 3rd Flr. Thru 3rd lift & 3rd floor beams | 05-22-2026 | Not Yet Started | 06-26-2026 | [9 empty] | Lokesh Reddy/Siva kumar |  | ESWAR
|  | Nuvo |  | 4th Flr. Thru Roof & Abv Roof beams | 05-22-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Lokesh Reddy/Siva kumar |  | Kameshwari
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | [10 empty] | siva kumar |  | Nanaji
|  | Nuvo |  | Bus Shelter - Footings | 05-22-2026 | Not Yet Started | [10 empty] | siva kumar |  | ESWAR
|  | Nuvo |  | Bg Thru 1st lift | 05-22-2026 | Not Yet Started | 07-24-2026 | [9 empty] | Pradeep |  | Kameshwari
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | [10 empty] | Pradeep |  | Nanaji
|  | Nuvo |  | Clubhouse | 05-22-2026 | Not Yet Started | [10 empty] | Pradeep |  | ESWAR
|  | Nuvo |  | Bg Thru Abv Roof beams | 05-22-2026 | Completed | 2026-05-06 | [9 empty] | siva kumar |  | Kameshwari
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | [10 empty] | siva kumar |  | Nanaji
|  | Nuvo |  | Garage Type 1 | 05-22-2026 | Not Yet Started | [10 empty] | siva kumar |  | ESWAR
|  | Nuvo |  | Bg Thru Abv Roof beams | 05-22-2026 | Inprogress | 2026-10-07 | [9 empty] | Pavan sai |  | Kameshwari
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pavan sai |  | ESWAR
|  | Nuvo |  | Garage Type 2 | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pavan sai |  | ESWAR
|  | Nuvo |  | Bg Thru Abv Roof beams | 05-22-2026 | Inprogress | 2026-10-07 | [9 empty] | Pradeep |  | Kameshwari
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | Nanaji
|  | Nuvo |  | Mail Kiosk - Slab on grade | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | ESWAR
|  | Nuvo |  | Slab on grade | 05-22-2026 | Inprogress | 2026-10-07 | [9 empty] | Pradeep |  | Kameshwari
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | Nanaji
|  | Nuvo |  | Trash Compactor | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | ESWAR
|  | Nuvo |  | Bg Thru 1st lift | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | Kameshwari
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | Nanaji
|  | Nuvo |  | Pool Pavilion | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | ESWAR
|  | Nuvo |  | Bg Thru Roof beams | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | Kameshwari
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | Nanaji
|  | Nuvo |  | Raised Planters | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | ESWAR
|  | Nuvo |  | Bg Thru 1st lift | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | Kameshwari
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | ESWAR
|  | Nuvo |  | BBQ Station | 05-22-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Pradeep |  | Kameshwari
|  | Nuvo |  | Bg Thru Roof beams | 05-22-2026 | Not Yet Started | 07-17-2026 | [9 empty] | Pradeep |  | ESWAR
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | 07-17-2026 | [9 empty] | Pradeep |  | Kameshwari
|  | Nuvo |  | Cabana Footings | 05-22-2026 | Not Yet Started | 07-17-2026 | [9 empty] | Pradeep |  | Nanaji
|  | Nuvo |  | Bg Thru 1st lift | 05-22-2026 | Not Yet Started | 07-17-2026 | [9 empty] | Pradeep |  | ESWAR
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | 07-17-2026 | [9 empty] | Pradeep |  | Kameshwari
|  | Nuvo |  | Trellis Footings | 05-22-2026 | Not Yet Started | 07-17-2026 | [9 empty] | Pradeep |  | Nanaji
|  | Nuvo |  | Bg Thru 1st lift | 05-22-2026 | Not Yet Started | 07-17-2026 | [9 empty] | Pradeep |  | ESWAR
|  | Nuvo |  |  | 05-22-2026 | Not Yet Started | 07-17-2026 | [9 empty] | Pradeep |  | Kameshwari
|  | Nuvo |  | Retaining Wall | 05-22-2026 | Completed | 2026-12-06 |  |  | 29.997 |  |  |  |  | 2026-11-06 | COMPLETED | Pradeep | COMPLETED | NANAJI
|  | Nuvo |  | Bg Thru 1st lift | 05-22-2026 | Completed | 2026-12-06 | 2026-05-06 | [8 empty] | Pradeep
51 |  | The Syed Residence | CIP & CMU | Foundations & Slab on grade | 05-23-2026 | Completed | 2026-06-05 | [9 empty] | Eswar |  | Kameshwari
|  | The Syed Residence |  | Lift - 1 verticals and beams | 05-23-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Jagadeesh |  | Nanaji
|  | The Syed Residence |  | Lift - 2 verticals and beams | 05-23-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Nanaji |  | ESWAR
52 |  | 810 S Swinton Ave Residence | CIP & CMU | Foundations and slab on grade | 05-26-2026 | Inprogress | 2026-09-06 | [9 empty] | Praveena |  | Kameshwari
|  | 811 S Swinton Ave Residence |  | Lift - 1 verticals and beams | 05-26-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Praveena |  | Nanaji
|  | 812 S Swinton Ave Residence |  | Lift - 2 verticals and beams | 05-26-2026 | Not Yet Started | 2026-03-07 | [9 empty] | Praveena |  | ESWAR
53 |  | Custom Residence (134 Worth CTN) | CIP & CMU | Foundations | 05-29-2026 | Completed | 06-13-2026 | [9 empty] | Praveena |  | Kameshwari
|  | Custom Residence (134 Worth CTN) |  | Slab on grade | 05-29-2026 | Completed | 06-13-2026 | [9 empty] | Vaishnavi |  | Nanaji
|  | Custom Residence (134 Worth CTN) |  | Lift - 1 verticals and beams | 05-29-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Jagadeesh |  | ESWAR
|  | Custom Residence (134 Worth CTN) |  | Lift - 2 verticals and beams | 05-29-2026 | Not Yet Started | 2026-10-07 | [9 empty] | Praveena |  | Kameshwari
54 |  | Rancano | CIP & CMU | Foundations & slab on grade | 05-29-2026 | Completed | 2026-11-06 |  |  | 6.108 | [6 empty] | Eswar |  | Kameshwari
|  | Rancano |  | Lift - 1 verticals and Roof beams | 05-29-2026 | Completed | 06-17-2026 |  |  | 1.66 |  |  |  |  | 06-16-2026 | COMPLETED | Sridevi | COMPLETED | NANAJI
55 |  | 799 Park Drive | CIP & CMU | Foundations & Slab on grade | 2026-09-06 | Completed | 2026-06-16 |  |  | 2.264 |  |  |  |  | 06-16-2026 | COMPLETED | Pradeep | COMPLETED | Nanaji
|  | 800 Park Drive |  | Lift - 1 verticals and beams | 2026-09-06 | Completed | 2026-06-20 |  |  | 3.621 | [6 empty] | Pradeep |  | Chandra mouli
|  | 801 Park Drive |  | Lift - 2 verticals and beams | 2026-09-06 | Completed | 2026-06-26 |  |  | 1.412 | [6 empty] | Pradeep |  | Chandra mouli
56 |  | Chateau De La Duchess (925 Hillsboro) | CIP & CMU | Entry Garages foundations and slab on grade | 08-25-2025 | Inprogress | 2026-03-07 | [9 empty] | Pradeep |  | Nanaji
|  | Chateau De La Duchess (925 Hillsboro) |  | Entry Garages lift - 1 verticals and beams | 08-25-2025 | Not Yet Started | 2026-03-07 | [9 empty] | Jagadeesh |  | ESWAR
|  | Chateau De La Duchess (925 Hillsboro) |  | Entry Garages lift - 2 verticals and beams | 08-25-2025 | Not Yet Started | 2026-03-07 | [9 empty] | Praveena |  | Kameshwari
57 |  | Masucci Residence | CIP & CMU | Foundations & slab on grade | 06-18-2025 | Inprogress | 06-26-2026 | [9 empty] | Pradeep |  | Nanaji
|  | Masucci Residence |  | Lift - 1 verticals and beams | 06-18-2025 | Not Yet Started | 2026-03-07 | [9 empty] | Jagadeesh |  | ESWAR
|  | Masucci Residence |  | 2nd floor slab and beams | 06-18-2025 | Not Yet Started | 2026-03-07 | [9 empty] | Praveena |  | Kameshwari
|  | Masucci Residence |  | Lift - 2 verticals and beams | 06-18-2025 | Not Yet Started | 2026-03-07 | [9 empty] | Pradeep |  | Nanaji
58 |  | The Bueller family | CIP & CMU | Foundations & slab on grade | 06-20-2025 | Inprogress | 06-26-2026 | [9 empty] | Jagadeesh |  | Kameshwari
|  | The Bueller family |  | Lift - 1 verticals and beams | 06-20-2025 | Not Yet Started | 06-26-2026 | [9 empty] | Praveena |  | Nanaji
59 |  | SPOTLOT 28810 SW 207 AVE | CIP & CMU | Foundations & slab on grade | 06-20-2025 | Completed | 2026-06-26 |  |  | 1.087 | [6 empty] | Jagadeesh |  | Kameshwari
|  | SPOTLOT 28810 SW 207 AVE |  | Lift - 1 verticals and beams | 06-20-2025 | Completed | 2026-06-26 |  |  | 1.032 | [6 empty] | Praveena |  | Nanaji
60 |  | Broken Sound Club | CIP | Foundations & slab on grade | 06-20-2025 | Completed | 2026-06-26 | [9 empty] | Pradeep |  | Kameshwari
|  | Broken Sound Club |  | Lift - 1 verticals and beams | 06-20-2025 | Completed | 2026-06-26 | [9 empty] | Jagadeesh |  | Nanaji
|  | Broken Sound Club | [14 empty] | Praveena |  | Kameshwari
|  | Broken Sound Club | [14 empty] | Pradeep |  | Nanaji
OLD PROJECTS MODIFICATIONS
1 |  | 1333 Bvld | Barlists | Shear walls and columns Barlists | 2026-05-05 | Completed | 2026-07-05 | [9 empty] | Lokesh Reddy |  | Nanaji
2 |  | Valencia Del Mar Clubhouse | Barlists | Slab on grade Barlists | 2026-05-05 | Completed | 2026-05-05 | [9 empty] | Vaishnavi |  | ESWAR
3 |  | 320 S atlantic Drive | Barlists | Foundations Barlists | 2026-05-05 | Completed | 2026-05-05 | [9 empty] | Sridevi |  | Kameshwari
4 |  | 910 S Ocean | Emds | Comments received on basement R1series dwgs | 2026-05-05 | Completed | 2026-06-05 | [9 empty] | Sridevi |  | Nanaji
5 |  | 6024 Le lac Rd | Emds | Comments received on pool cabana & outdoor kitchen | 2026-05-05 | Completed | 2026-07-05 | [9 empty] | Sridevi / Vaishnavi |  | ESWAR
6 |  | 6017 Le Lac Road (Weiner Residence) | Barlists | Barlists requested for 2story building lift - 1 verticals | 2026-05-05 | Completed | 2026-06-05 | [9 empty] | Vaishnavi |  | Kameshwari
7 |  | South Rd Office Building E | Barlists | Lift - 1 Verticals and beams | 2026-05-05 | Completed | 2026-07-05 | [9 empty] | Vaishnavi |  | Nanaji
8 |  | 559 Nw 43 st | Barlists | Stairs barlists | 2026-05-05 | Completed | 2026-06-05 | [9 empty] | Danush |  | ESWAR
9 |  | PBIA - Revenue Control Building | Emds | Rfi-029 received on foundaitons | 2026-07-05 | Completed | 2026-08-05 | [9 empty] | Vaishnavi |  | Kameshwari
10 |  | Sands residence (3223 N Ocean) | Emds | Ssk-017 Received for 2nd for slab at balcony | 2026-07-05 | Completed | 2026-08-05 | [9 empty] | Eswar |  | Nanaji
11 |  | 5900 Powerline Garage | Barlists | Foundations (Grade beams) | 2026-07-05 | Completed | 2026-08-05 | [9 empty] | Pradeep |  | ESWAR
13 |  | 1050 N Lake way | Barlists | 2nd lift - 2 verticals and beams | 2026-09-05 | Completed | 2026-09-05 | [9 empty] | Lokesh Reddy |  | Kameshwari
14 |  | Baig Residence | Barlists | 2nd floor slab | 2026-09-05 | Completed | 2026-09-05 | [9 empty] | Lokesh Reddy |  | Nanaji
15 |  | South Rd Office Building E | Patch | Need patch lists for cmu walls at stem walls | 2026-11-05 | Completed | 2026-09-05 | [9 empty] | Lokesh Reddy |  | ESWAR
16 |  | Valencia Del Mar Clubhouse | Barlists | Lift - 1 verticals section #3 | 05-19-2026 | Completed | 05-19-2026 | [9 empty] | Eswar |  | Kameshwari
17 |  | South Rd Office Building E | Barlists | Lift -1 verticals barlists | 05-13-2026 | Completed | 05-13-2026 | [9 empty] | Pradeep |  | Nanaji
18 |  | 2651 SE 10th Court | Barlists | Pool deck slab and beams barlists | 05-14-2026 | Completed | 05-18-2026 | [9 empty] | Lokesh Reddy |  | ESWAR
19 |  | 6017 Le Lac Road (Weiner Residence) | Barlists | Orange section #2 1st lift verticals | 05-18-2026 | Completed | 05-19-2026 | [9 empty] | Danush |  | Nanaji
20 |  | 1333 Bvld | Barlists | Stem walls barlists | 05-18-2026 | Completed | 05-18-2026 | [9 empty] | Sridevi |  | ESWAR
21 |  | 2651 SE 10th Court | Emds | Update received on the pool deck | 05-18-2026 | Completed | 05-19-2026 | [9 empty] | Eswar |  | Kameshwari
22 |  | cannatelli | Barlists | Foundations and slab on grade Barlists | 05-18-2026 | Completed | 05-18-2026 | [9 empty] | Pradeep |  | Nanaji
23 |  | 6017 Le Lac Road (Weiner Residence) | Barlists | Lift - 1 verticals and beams for Blue section | 05-19-2026 | Completed | 05-20-2026 | [9 empty] | Lokesh Reddy |  | ESWAR
24 |  | 401 SE Atlantic Drive | Barlists | Barlists for R3 series drawings | 05-19-2026 | Completed | 05-20-2026 | [9 empty] | Danush |  | Kameshwari
25 |  | 515 Lido Drive | Barlists | Column ties for upto 4'-0" | 05-19-2026 | Completed | 05-20-2026 | [9 empty] | Sridevi |  | Nanaji
26 |  | 143 Reef Road | Updated drawings | 1st floor beams and second floor slab | 05-20-2026 | Completed | 05-20-2026 | [9 empty] | Eswar |  | ESWAR
27 |  | PBIA - Revenue Control Building | Revised drawings | Revised drawings received on cmu verticals | 05-21-2026 | Completed | 05-22-2026 | [9 empty] | Pradeep |  | Kameshwari
28 |  | 515 Lido Drive | Barlists | Garage slab barlists | 05-21-2026 | Completed | 05-21-2026 | [9 empty] | Lokesh Reddy |  | Nanaji
29 |  | cannatelli | Barlists | Foundations and slab on grade Barlists | 05-21-2026 | Completed | 05-23-2026 | [9 empty] | Danush |  | ESWAR
30 |  | 1042 Palm Way Road | Revised drawings | Roof beams and slab | 05-22-2026 | Completed | 05-28-2026 | [9 empty] | Sridevi |  | Kameshwari
31 |  | South Rd Office Building E | Emds | Comments received on 1st lift verticals and beams | 05-21-2026 | Inprogress | 05-22-2026 | [9 empty] | Eswar |  | Nanaji
32 |  | 910 S Ocean | Barlists | Basement slab barlists | 05-26-2026 | Completed | 05-27-2026 | [9 empty] | Pradeep |  | Nanaji
33 |  | Valencia Del Mar Clubhouse | Barlists | Lift - 2 verticals and beams for green section #2 | 05-26-2026 | Inprogress | 05-28-2026 | [9 empty] | Lokesh Reddy |  | ESWAR
34 |  | Valencia Del Mar Clubhouse | Barlists | Lift - 2 verticals and beams for Yellow section #1 | 05-26-2026 | Inprogress | 05-28-2026 | [9 empty] | Danush |  | Kameshwari
35 |  | Burns Residence | Barlists | Slab on grade barlists | 05-28-2026 | Inprogress | 05-28-2026 | [9 empty] | Sridevi |  | Nanaji
36 |  | 1900 NE 22ND Terrance | Emds | Comments received on slab on grade | 05-28-2026 | Inprogress | 05-28-2026 | [9 empty] | Eswar |  | ESWAR
[8 empty] | Totals | 0 | 990.056 | 0 | 0 | 0 | 0
Note: Submittal dates may change according to client request / RFI Clarification /Priorities